## Sheet1
Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW
Selected Group :- 18th Floor | Selected Group :- 18th Floor | Selected Group :- 18th Floor | Selected Group :- 18th Floor | Selected Group :- 18th Floor | Selected Group :- 18th Floor | Selected Group :- 18th Floor | Selected Group :- 18th Floor | Selected Group :- 18th Floor | Selected Group :- 18th Floor | Selected Group :- 18th Floor | Selected Group :- 18th Floor | Selected Group :- 18th Floor | Selected Group :- 18th Floor | Selected Group :- 18th Floor | Selected Group :- 18th Floor
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
620125 | A.1801 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8300 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 20.8200 | 100.0000 | 168.001.001.002.007.001.018.001.001. | 100.0000 | Material | 0 | 0.0000
620125 | A.1801 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8300 | 89 | Cement 43 Grade | Bags | 0.4164 | 375.0000 | 168.001.001.002.007.001.018.001.001. | 375.0000 | Material | 0 | 0.0000
620125 | A.1801 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8300 | 161 | Crush Sand | Cu.Ft | 1.6656 | 33.0000 | 168.001.001.002.007.001.018.001.001. | 33.0000 | Material | 0 | 0.0000
620125 | A.1801 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8300 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 20.8200 | 100.0000 | 168.001.001.002.007.001.018.001.001. | 100.0000 | Material | 0 | 0.0000
620125 | A.1801 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8300 | 1361 | HCL Acid | Ltrs | 0.3123 | 6.0000 | 168.001.001.002.007.001.018.001.001. | 6.0000 | Material | 0 | 0.0000
620125 | A.1801 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8300 | 24440 | M Sand | Cu.Ft | 1.6656 | 65.0000 | 168.001.001.002.007.001.018.001.001. | 65.0000 | Material | 0 | 0.0000
620125 | A.1801 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8300 | 5989 | Tape Roll | No. | 0.3123 | 1327.5000 | 168.001.001.002.007.001.018.001.001. | 1327.5000 | Material | 0 | 0.0000
620125 | A.1801 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8300 | 26445 | Tile Grout | Kgs | 0.2082 | 100.0000 | 168.001.001.002.007.001.018.001.001. | 100.0000 | Material | 0 | 0.0000
620126 | A.1801 Internal Flat Flooring | Sq.Ft | 275.6900 | 275.6900 | 89 | Cement 43 Grade | Bags | 5.5138 | 375.0000 | 168.001.001.002.007.001.018.001.002. | 375.0000 | Material | 0 | 0.0000
620126 | A.1801 Internal Flat Flooring | Sq.Ft | 275.6900 | 275.6900 | 161 | Crush Sand | Cu.Ft | 22.0552 | 33.0000 | 168.001.001.002.007.001.018.001.002. | 33.0000 | Material | 0 | 0.0000
620126 | A.1801 Internal Flat Flooring | Sq.Ft | 275.6900 | 275.6900 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 275.6900 | 100.0000 | 168.001.001.002.007.001.018.001.002. | 100.0000 | Material | 0 | 0.0000
620126 | A.1801 Internal Flat Flooring | Sq.Ft | 275.6900 | 275.6900 | 1361 | HCL Acid | Ltrs | 4.1354 | 6.0000 | 168.001.001.002.007.001.018.001.002. | 6.0000 | Material | 0 | 0.0000
620126 | A.1801 Internal Flat Flooring | Sq.Ft | 275.6900 | 275.6900 | 24440 | M Sand | Cu.Ft | 22.0552 | 65.0000 | 168.001.001.002.007.001.018.001.002. | 65.0000 | Material | 0 | 0.0000
620126 | A.1801 Internal Flat Flooring | Sq.Ft | 275.6900 | 275.6900 | 5989 | Tape Roll | No. | 4.1354 | 1327.5000 | 168.001.001.002.007.001.018.001.002. | 1327.5000 | Material | 0 | 0.0000
620126 | A.1801 Internal Flat Flooring | Sq.Ft | 275.6900 | 275.6900 | 26445 | Tile Grout | Kgs | 2.7569 | 100.0000 | 168.001.001.002.007.001.018.001.002. | 100.0000 | Material | 0 | 0.0000
620126 | A.1801 Internal Flat Flooring | Sq.Ft | 275.6900 | 275.6900 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.36 | 100.0000 | 168.001.001.002.007.001.018.001.002. | 100.0000 | Material | 0 | 0.0000
620127 | A.1801 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.018.001.003. | 100.0000 | Material | 0 | 0.0000
620127 | A.1801 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 89 | Cement 43 Grade | Bags | 0.2190 | 375.0000 | 168.001.001.002.007.001.018.001.003. | 375.0000 | Material | 0 | 0.0000
620127 | A.1801 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.018.001.003. | 33.0000 | Material | 0 | 0.0000
620127 | A.1801 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.018.001.003. | 100.0000 | Material | 0 | 0.0000
620127 | A.1801 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 1361 | HCL Acid | Ltrs | 0.1643 | 6.0000 | 168.001.001.002.007.001.018.001.003. | 6.0000 | Material | 0 | 0.0000
620127 | A.1801 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 24440 | M Sand | Cu.Ft | 0.8760 | 65.0000 | 168.001.001.002.007.001.018.001.003. | 65.0000 | Material | 0 | 0.0000
620127 | A.1801 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 5989 | Tape Roll | No. | 0.1643 | 1327.5000 | 168.001.001.002.007.001.018.001.003. | 1327.5000 | Material | 0 | 0.0000
620127 | A.1801 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 26445 | Tile Grout | Kgs | 0.1095 | 100.0000 | 168.001.001.002.007.001.018.001.003. | 100.0000 | Material | 0 | 0.0000
620129 | A.1802 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 19.6900 | 100.0000 | 168.001.001.002.007.001.018.002.001. | 100.0000 | Material | 0 | 0.0000
620129 | A.1802 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 89 | Cement 43 Grade | Bags | 0.3938 | 375.0000 | 168.001.001.002.007.001.018.002.001. | 375.0000 | Material | 0 | 0.0000
620129 | A.1802 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 161 | Crush Sand | Cu.Ft | 1.5752 | 33.0000 | 168.001.001.002.007.001.018.002.001. | 33.0000 | Material | 0 | 0.0000
620129 | A.1802 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 19.6900 | 100.0000 | 168.001.001.002.007.001.018.002.001. | 100.0000 | Material | 0 | 0.0000
620129 | A.1802 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 1361 | HCL Acid | Ltrs | 0.2954 | 6.0000 | 168.001.001.002.007.001.018.002.001. | 6.0000 | Material | 0 | 0.0000
620129 | A.1802 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 24440 | M Sand | Cu.Ft | 1.5752 | 65.0000 | 168.001.001.002.007.001.018.002.001. | 65.0000 | Material | 0 | 0.0000
620129 | A.1802 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 5989 | Tape Roll | No. | 0.2954 | 1327.5000 | 168.001.001.002.007.001.018.002.001. | 1327.5000 | Material | 0 | 0.0000
620129 | A.1802 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 26445 | Tile Grout | Kgs | 0.1969 | 100.0000 | 168.001.001.002.007.001.018.002.001. | 100.0000 | Material | 0 | 0.0000
620130 | A.1802 Internal Flat Flooring | Sq.Ft | 254.3700 | 254.3700 | 89 | Cement 43 Grade | Bags | 5.0874 | 375.0000 | 168.001.001.002.007.001.018.002.002. | 375.0000 | Material | 0 | 0.0000
620130 | A.1802 Internal Flat Flooring | Sq.Ft | 254.3700 | 254.3700 | 161 | Crush Sand | Cu.Ft | 20.3496 | 33.0000 | 168.001.001.002.007.001.018.002.002. | 33.0000 | Material | 0 | 0.0000
620130 | A.1802 Internal Flat Flooring | Sq.Ft | 254.3700 | 254.3700 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 254.3700 | 100.0000 | 168.001.001.002.007.001.018.002.002. | 100.0000 | Material | 0 | 0.0000
620130 | A.1802 Internal Flat Flooring | Sq.Ft | 254.3700 | 254.3700 | 1361 | HCL Acid | Ltrs | 3.8156 | 6.0000 | 168.001.001.002.007.001.018.002.002. | 6.0000 | Material | 0 | 0.0000
620130 | A.1802 Internal Flat Flooring | Sq.Ft | 254.3700 | 254.3700 | 24440 | M Sand | Cu.Ft | 20.3496 | 65.0000 | 168.001.001.002.007.001.018.002.002. | 65.0000 | Material | 0 | 0.0000
620130 | A.1802 Internal Flat Flooring | Sq.Ft | 254.3700 | 254.3700 | 5989 | Tape Roll | No. | 3.8156 | 1327.5000 | 168.001.001.002.007.001.018.002.002. | 1327.5000 | Material | 0 | 0.0000
620130 | A.1802 Internal Flat Flooring | Sq.Ft | 254.3700 | 254.3700 | 26445 | Tile Grout | Kgs | 2.5437 | 100.0000 | 168.001.001.002.007.001.018.002.002. | 100.0000 | Material | 0 | 0.0000
620130 | A.1802 Internal Flat Flooring | Sq.Ft | 254.3700 | 254.3700 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.36 | 100.0000 | 168.001.001.002.007.001.018.002.002. | 100.0000 | Material | 0 | 0.0000
620131 | A.1802 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.018.002.003. | 100.0000 | Material | 0 | 0.0000
620131 | A.1802 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 89 | Cement 43 Grade | Bags | 0.2190 | 375.0000 | 168.001.001.002.007.001.018.002.003. | 375.0000 | Material | 0 | 0.0000
620131 | A.1802 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.018.002.003. | 33.0000 | Material | 0 | 0.0000
620131 | A.1802 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.018.002.003. | 100.0000 | Material | 0 | 0.0000
620131 | A.1802 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 1361 | HCL Acid | Ltrs | 0.1643 | 6.0000 | 168.001.001.002.007.001.018.002.003. | 6.0000 | Material | 0 | 0.0000
620131 | A.1802 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 24440 | M Sand | Cu.Ft | 0.8760 | 65.0000 | 168.001.001.002.007.001.018.002.003. | 65.0000 | Material | 0 | 0.0000
620131 | A.1802 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 5989 | Tape Roll | No. | 0.1643 | 1327.5000 | 168.001.001.002.007.001.018.002.003. | 1327.5000 | Material | 0 | 0.0000
620131 | A.1802 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 26445 | Tile Grout | Kgs | 0.1095 | 100.0000 | 168.001.001.002.007.001.018.002.003. | 100.0000 | Material | 0 | 0.0000
620133 | A.1803 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 19.6900 | 100.0000 | 168.001.001.002.007.001.018.003.001. | 100.0000 | Material | 0 | 0.0000
620133 | A.1803 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 89 | Cement 43 Grade | Bags | 0.3938 | 375.0000 | 168.001.001.002.007.001.018.003.001. | 375.0000 | Material | 0 | 0.0000
620133 | A.1803 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 161 | Crush Sand | Cu.Ft | 1.5752 | 33.0000 | 168.001.001.002.007.001.018.003.001. | 33.0000 | Material | 0 | 0.0000
620133 | A.1803 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 19.6900 | 100.0000 | 168.001.001.002.007.001.018.003.001. | 100.0000 | Material | 0 | 0.0000
620133 | A.1803 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 1361 | HCL Acid | Ltrs | 0.2954 | 6.0000 | 168.001.001.002.007.001.018.003.001. | 6.0000 | Material | 0 | 0.0000
620133 | A.1803 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 24440 | M Sand | Cu.Ft | 1.5752 | 65.0000 | 168.001.001.002.007.001.018.003.001. | 65.0000 | Material | 0 | 0.0000
620133 | A.1803 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 5989 | Tape Roll | No. | 0.2954 | 1327.5000 | 168.001.001.002.007.001.018.003.001. | 1327.5000 | Material | 0 | 0.0000
620133 | A.1803 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 26445 | Tile Grout | Kgs | 0.1969 | 100.0000 | 168.001.001.002.007.001.018.003.001. | 100.0000 | Material | 0 | 0.0000
620134 | A.1803 Internal Flat Flooring | Sq.Ft | 256.4300 | 256.4300 | 89 | Cement 43 Grade | Bags | 5.1286 | 375.0000 | 168.001.001.002.007.001.018.003.002. | 375.0000 | Material | 0 | 0.0000
620134 | A.1803 Internal Flat Flooring | Sq.Ft | 256.4300 | 256.4300 | 161 | Crush Sand | Cu.Ft | 20.5144 | 33.0000 | 168.001.001.002.007.001.018.003.002. | 33.0000 | Material | 0 | 0.0000
620134 | A.1803 Internal Flat Flooring | Sq.Ft | 256.4300 | 256.4300 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 256.4300 | 100.0000 | 168.001.001.002.007.001.018.003.002. | 100.0000 | Material | 0 | 0.0000
620134 | A.1803 Internal Flat Flooring | Sq.Ft | 256.4300 | 256.4300 | 1361 | HCL Acid | Ltrs | 3.8465 | 6.0000 | 168.001.001.002.007.001.018.003.002. | 6.0000 | Material | 0 | 0.0000
620134 | A.1803 Internal Flat Flooring | Sq.Ft | 256.4300 | 256.4300 | 24440 | M Sand | Cu.Ft | 20.5144 | 65.0000 | 168.001.001.002.007.001.018.003.002. | 65.0000 | Material | 0 | 0.0000
620134 | A.1803 Internal Flat Flooring | Sq.Ft | 256.4300 | 256.4300 | 5989 | Tape Roll | No. | 3.8465 | 1327.5000 | 168.001.001.002.007.001.018.003.002. | 1327.5000 | Material | 0 | 0.0000
620134 | A.1803 Internal Flat Flooring | Sq.Ft | 256.4300 | 256.4300 | 26445 | Tile Grout | Kgs | 2.5643 | 100.0000 | 168.001.001.002.007.001.018.003.002. | 100.0000 | Material | 0 | 0.0000
620134 | A.1803 Internal Flat Flooring | Sq.Ft | 256.4300 | 256.4300 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.36 | 100.0000 | 168.001.001.002.007.001.018.003.002. | 100.0000 | Material | 0 | 0.0000
620135 | A.1803 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.018.003.003. | 100.0000 | Material | 0 | 0.0000
620135 | A.1803 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 89 | Cement 43 Grade | Bags | 0.2190 | 375.0000 | 168.001.001.002.007.001.018.003.003. | 375.0000 | Material | 0 | 0.0000
620135 | A.1803 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.018.003.003. | 33.0000 | Material | 0 | 0.0000
620135 | A.1803 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.018.003.003. | 100.0000 | Material | 0 | 0.0000
620135 | A.1803 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 1361 | HCL Acid | Ltrs | 0.1643 | 6.0000 | 168.001.001.002.007.001.018.003.003. | 6.0000 | Material | 0 | 0.0000
620135 | A.1803 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 24440 | M Sand | Cu.Ft | 0.8760 | 65.0000 | 168.001.001.002.007.001.018.003.003. | 65.0000 | Material | 0 | 0.0000
620135 | A.1803 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 5989 | Tape Roll | No. | 0.1643 | 1327.5000 | 168.001.001.002.007.001.018.003.003. | 1327.5000 | Material | 0 | 0.0000
620135 | A.1803 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 26445 | Tile Grout | Kgs | 0.1095 | 100.0000 | 168.001.001.002.007.001.018.003.003. | 100.0000 | Material | 0 | 0.0000
620137 | A.1804 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8200 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 20.8200 | 100.0000 | 168.001.001.002.007.001.018.004.001. | 100.0000 | Material | 0 | 0.0000
620137 | A.1804 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8200 | 89 | Cement 43 Grade | Bags | 0.4164 | 375.0000 | 168.001.001.002.007.001.018.004.001. | 375.0000 | Material | 0 | 0.0000
620137 | A.1804 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8200 | 161 | Crush Sand | Cu.Ft | 1.6656 | 33.0000 | 168.001.001.002.007.001.018.004.001. | 33.0000 | Material | 0 | 0.0000
620137 | A.1804 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8200 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 20.8200 | 100.0000 | 168.001.001.002.007.001.018.004.001. | 100.0000 | Material | 0 | 0.0000
620137 | A.1804 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8200 | 1361 | HCL Acid | Ltrs | 0.3123 | 6.0000 | 168.001.001.002.007.001.018.004.001. | 6.0000 | Material | 0 | 0.0000
620137 | A.1804 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8200 | 24440 | M Sand | Cu.Ft | 1.6656 | 65.0000 | 168.001.001.002.007.001.018.004.001. | 65.0000 | Material | 0 | 0.0000
620137 | A.1804 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8200 | 5989 | Tape Roll | No. | 0.3123 | 1327.5000 | 168.001.001.002.007.001.018.004.001. | 1327.5000 | Material | 0 | 0.0000
620137 | A.1804 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8200 | 26445 | Tile Grout | Kgs | 0.2082 | 100.0000 | 168.001.001.002.007.001.018.004.001. | 100.0000 | Material | 0 | 0.0000
620138 | A.1804 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 89 | Cement 43 Grade | Bags | 5.1310 | 375.0000 | 168.001.001.002.007.001.018.004.002. | 375.0000 | Material | 0 | 0.0000
620138 | A.1804 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 161 | Crush Sand | Cu.Ft | 20.5240 | 33.0000 | 168.001.001.002.007.001.018.004.002. | 33.0000 | Material | 0 | 0.0000
620138 | A.1804 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 256.5500 | 100.0000 | 168.001.001.002.007.001.018.004.002. | 100.0000 | Material | 0 | 0.0000
620138 | A.1804 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 1361 | HCL Acid | Ltrs | 3.8483 | 6.0000 | 168.001.001.002.007.001.018.004.002. | 6.0000 | Material | 0 | 0.0000
620138 | A.1804 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 24440 | M Sand | Cu.Ft | 20.5240 | 65.0000 | 168.001.001.002.007.001.018.004.002. | 65.0000 | Material | 0 | 0.0000
620138 | A.1804 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 5989 | Tape Roll | No. | 3.8483 | 1327.5000 | 168.001.001.002.007.001.018.004.002. | 1327.5000 | Material | 0 | 0.0000
620138 | A.1804 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 26445 | Tile Grout | Kgs | 2.5655 | 100.0000 | 168.001.001.002.007.001.018.004.002. | 100.0000 | Material | 0 | 0.0000
620138 | A.1804 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.36 | 100.0000 | 168.001.001.002.007.001.018.004.002. | 100.0000 | Material | 0 | 0.0000
620139 | A.1804 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.018.004.003. | 100.0000 | Material | 0 | 0.0000
620139 | A.1804 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 89 | Cement 43 Grade | Bags | 0.2190 | 375.0000 | 168.001.001.002.007.001.018.004.003. | 375.0000 | Material | 0 | 0.0000
620139 | A.1804 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.018.004.003. | 33.0000 | Material | 0 | 0.0000
620139 | A.1804 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.018.004.003. | 100.0000 | Material | 0 | 0.0000
620139 | A.1804 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 1361 | HCL Acid | Ltrs | 0.1643 | 6.0000 | 168.001.001.002.007.001.018.004.003. | 6.0000 | Material | 0 | 0.0000
620139 | A.1804 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 24440 | M Sand | Cu.Ft | 0.8760 | 65.0000 | 168.001.001.002.007.001.018.004.003. | 65.0000 | Material | 0 | 0.0000
620139 | A.1804 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 5989 | Tape Roll | No. | 0.1643 | 1327.5000 | 168.001.001.002.007.001.018.004.003. | 1327.5000 | Material | 0 | 0.0000
620139 | A.1804 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 26445 | Tile Grout | Kgs | 0.1095 | 100.0000 | 168.001.001.002.007.001.018.004.003. | 100.0000 | Material | 0 | 0.0000
620141 | A.1805 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 20.8700 | 100.0000 | 168.001.001.002.007.001.018.005.001. | 100.0000 | Material | 0 | 0.0000
620141 | A.1805 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 89 | Cement 43 Grade | Bags | 0.4174 | 375.0000 | 168.001.001.002.007.001.018.005.001. | 375.0000 | Material | 0 | 0.0000
620141 | A.1805 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 161 | Crush Sand | Cu.Ft | 1.6696 | 33.0000 | 168.001.001.002.007.001.018.005.001. | 33.0000 | Material | 0 | 0.0000
620141 | A.1805 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 20.8700 | 100.0000 | 168.001.001.002.007.001.018.005.001. | 100.0000 | Material | 0 | 0.0000
620141 | A.1805 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 1361 | HCL Acid | Ltrs | 0.3131 | 6.0000 | 168.001.001.002.007.001.018.005.001. | 6.0000 | Material | 0 | 0.0000
620141 | A.1805 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 24440 | M Sand | Cu.Ft | 1.6696 | 65.0000 | 168.001.001.002.007.001.018.005.001. | 65.0000 | Material | 0 | 0.0000
620141 | A.1805 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 5989 | Tape Roll | No. | 0.3131 | 1327.5000 | 168.001.001.002.007.001.018.005.001. | 1327.5000 | Material | 0 | 0.0000
620141 | A.1805 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 26445 | Tile Grout | Kgs | 0.2087 | 100.0000 | 168.001.001.002.007.001.018.005.001. | 100.0000 | Material | 0 | 0.0000
620142 | A.1805 Internal Flat Flooring | Sq.Ft | 249.5700 | 249.5700 | 89 | Cement 43 Grade | Bags | 4.9914 | 375.0000 | 168.001.001.002.007.001.018.005.002. | 375.0000 | Material | 0 | 0.0000
620142 | A.1805 Internal Flat Flooring | Sq.Ft | 249.5700 | 249.5700 | 161 | Crush Sand | Cu.Ft | 19.9656 | 33.0000 | 168.001.001.002.007.001.018.005.002. | 33.0000 | Material | 0 | 0.0000
620142 | A.1805 Internal Flat Flooring | Sq.Ft | 249.5700 | 249.5700 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 249.5700 | 100.0000 | 168.001.001.002.007.001.018.005.002. | 100.0000 | Material | 0 | 0.0000
620142 | A.1805 Internal Flat Flooring | Sq.Ft | 249.5700 | 249.5700 | 1361 | HCL Acid | Ltrs | 3.7436 | 6.0000 | 168.001.001.002.007.001.018.005.002. | 6.0000 | Material | 0 | 0.0000
620142 | A.1805 Internal Flat Flooring | Sq.Ft | 249.5700 | 249.5700 | 24440 | M Sand | Cu.Ft | 19.9656 | 65.0000 | 168.001.001.002.007.001.018.005.002. | 65.0000 | Material | 0 | 0.0000
620142 | A.1805 Internal Flat Flooring | Sq.Ft | 249.5700 | 249.5700 | 5989 | Tape Roll | No. | 3.7436 | 1327.5000 | 168.001.001.002.007.001.018.005.002. | 1327.5000 | Material | 0 | 0.0000
620142 | A.1805 Internal Flat Flooring | Sq.Ft | 249.5700 | 249.5700 | 26445 | Tile Grout | Kgs | 2.4957 | 100.0000 | 168.001.001.002.007.001.018.005.002. | 100.0000 | Material | 0 | 0.0000
620142 | A.1805 Internal Flat Flooring | Sq.Ft | 249.5700 | 249.5700 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.36 | 100.0000 | 168.001.001.002.007.001.018.005.002. | 100.0000 | Material | 0 | 0.0000
620143 | A.1805 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.018.005.003. | 100.0000 | Material | 0 | 0.0000
620143 | A.1805 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 89 | Cement 43 Grade | Bags | 0.2190 | 375.0000 | 168.001.001.002.007.001.018.005.003. | 375.0000 | Material | 0 | 0.0000
620143 | A.1805 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.018.005.003. | 33.0000 | Material | 0 | 0.0000
620143 | A.1805 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.018.005.003. | 100.0000 | Material | 0 | 0.0000
620143 | A.1805 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 1361 | HCL Acid | Ltrs | 0.1643 | 6.0000 | 168.001.001.002.007.001.018.005.003. | 6.0000 | Material | 0 | 0.0000
620143 | A.1805 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 24440 | M Sand | Cu.Ft | 0.8760 | 65.0000 | 168.001.001.002.007.001.018.005.003. | 65.0000 | Material | 0 | 0.0000
620143 | A.1805 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 5989 | Tape Roll | No. | 0.1643 | 1327.5000 | 168.001.001.002.007.001.018.005.003. | 1327.5000 | Material | 0 | 0.0000
620143 | A.1805 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 26445 | Tile Grout | Kgs | 0.1095 | 100.0000 | 168.001.001.002.007.001.018.005.003. | 100.0000 | Material | 0 | 0.0000
620145 | A.1806 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 20.8700 | 100.0000 | 168.001.001.002.007.001.018.006.001. | 100.0000 | Material | 0 | 0.0000
620145 | A.1806 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 89 | Cement 43 Grade | Bags | 0.4174 | 375.0000 | 168.001.001.002.007.001.018.006.001. | 375.0000 | Material | 0 | 0.0000
620145 | A.1806 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 161 | Crush Sand | Cu.Ft | 1.6696 | 33.0000 | 168.001.001.002.007.001.018.006.001. | 33.0000 | Material | 0 | 0.0000
620145 | A.1806 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 20.8700 | 100.0000 | 168.001.001.002.007.001.018.006.001. | 100.0000 | Material | 0 | 0.0000
620145 | A.1806 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 1361 | HCL Acid | Ltrs | 0.3131 | 6.0000 | 168.001.001.002.007.001.018.006.001. | 6.0000 | Material | 0 | 0.0000
620145 | A.1806 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 24440 | M Sand | Cu.Ft | 1.6696 | 65.0000 | 168.001.001.002.007.001.018.006.001. | 65.0000 | Material | 0 | 0.0000
620145 | A.1806 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 5989 | Tape Roll | No. | 0.3131 | 1327.5000 | 168.001.001.002.007.001.018.006.001. | 1327.5000 | Material | 0 | 0.0000
620145 | A.1806 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 26445 | Tile Grout | Kgs | 0.2087 | 100.0000 | 168.001.001.002.007.001.018.006.001. | 100.0000 | Material | 0 | 0.0000
620146 | A.1806 Internal Flat Flooring | Sq.Ft | 250.4500 | 250.4500 | 89 | Cement 43 Grade | Bags | 5.0090 | 375.0000 | 168.001.001.002.007.001.018.006.002. | 375.0000 | Material | 0 | 0.0000
620146 | A.1806 Internal Flat Flooring | Sq.Ft | 250.4500 | 250.4500 | 161 | Crush Sand | Cu.Ft | 20.0360 | 33.0000 | 168.001.001.002.007.001.018.006.002. | 33.0000 | Material | 0 | 0.0000
620146 | A.1806 Internal Flat Flooring | Sq.Ft | 250.4500 | 250.4500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 250.4500 | 100.0000 | 168.001.001.002.007.001.018.006.002. | 100.0000 | Material | 0 | 0.0000
620146 | A.1806 Internal Flat Flooring | Sq.Ft | 250.4500 | 250.4500 | 1361 | HCL Acid | Ltrs | 3.7568 | 6.0000 | 168.001.001.002.007.001.018.006.002. | 6.0000 | Material | 0 | 0.0000
620146 | A.1806 Internal Flat Flooring | Sq.Ft | 250.4500 | 250.4500 | 24440 | M Sand | Cu.Ft | 20.0360 | 65.0000 | 168.001.001.002.007.001.018.006.002. | 65.0000 | Material | 0 | 0.0000
620146 | A.1806 Internal Flat Flooring | Sq.Ft | 250.4500 | 250.4500 | 5989 | Tape Roll | No. | 3.7568 | 1327.5000 | 168.001.001.002.007.001.018.006.002. | 1327.5000 | Material | 0 | 0.0000
620146 | A.1806 Internal Flat Flooring | Sq.Ft | 250.4500 | 250.4500 | 26445 | Tile Grout | Kgs | 2.5045 | 100.0000 | 168.001.001.002.007.001.018.006.002. | 100.0000 | Material | 0 | 0.0000
620146 | A.1806 Internal Flat Flooring | Sq.Ft | 250.4500 | 250.4500 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.36 | 100.0000 | 168.001.001.002.007.001.018.006.002. | 100.0000 | Material | 0 | 0.0000
620147 | A.1806 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.018.006.003. | 100.0000 | Material | 0 | 0.0000
620147 | A.1806 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 89 | Cement 43 Grade | Bags | 0.2190 | 375.0000 | 168.001.001.002.007.001.018.006.003. | 375.0000 | Material | 0 | 0.0000
620147 | A.1806 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.018.006.003. | 33.0000 | Material | 0 | 0.0000
620147 | A.1806 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.018.006.003. | 100.0000 | Material | 0 | 0.0000
620147 | A.1806 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 1361 | HCL Acid | Ltrs | 0.1643 | 6.0000 | 168.001.001.002.007.001.018.006.003. | 6.0000 | Material | 0 | 0.0000
620147 | A.1806 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 24440 | M Sand | Cu.Ft | 0.8760 | 65.0000 | 168.001.001.002.007.001.018.006.003. | 65.0000 | Material | 0 | 0.0000
620147 | A.1806 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 5989 | Tape Roll | No. | 0.1643 | 1327.5000 | 168.001.001.002.007.001.018.006.003. | 1327.5000 | Material | 0 | 0.0000
620147 | A.1806 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 26445 | Tile Grout | Kgs | 0.1095 | 100.0000 | 168.001.001.002.007.001.018.006.003. | 100.0000 | Material | 0 | 0.0000