## Sheet1
Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW
Selected Group :- Staircase 1 | Selected Group :- Staircase 1 | Selected Group :- Staircase 1 | Selected Group :- Staircase 1 | Selected Group :- Staircase 1 | Selected Group :- Staircase 1 | Selected Group :- Staircase 1 | Selected Group :- Staircase 1 | Selected Group :- Staircase 1 | Selected Group :- Staircase 1 | Selected Group :- Staircase 1 | Selected Group :- Staircase 1 | Selected Group :- Staircase 1 | Selected Group :- Staircase 1 | Selected Group :- Staircase 1 | Selected Group :- Staircase 1
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
667602 | A - Ground Floor Staircase 1 Flooring Work | Sq.Ft | 95.7990 | 95.7990 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 106.338 | 300.0000 | 168.001.001.005.005.002.003.001.001.001. | 300.0000 | Material | 0 | 0.0000
667602 | A - Ground Floor Staircase 1 Flooring Work | Sq.Ft | 95.7990 | 95.7990 | 89 | Cement 43 Grade | Bags | 1.9160 | 375.0000 | 168.001.001.005.005.002.003.001.001.001. | 375.0000 | Material | 0 | 0.0000
667602 | A - Ground Floor Staircase 1 Flooring Work | Sq.Ft | 95.7990 | 95.7990 | 161 | Crush Sand | Cu.Ft | 7.6639 | 33.0000 | 168.001.001.005.005.002.003.001.001.001. | 33.0000 | Material | 0 | 0.0000
667602 | A - Ground Floor Staircase 1 Flooring Work | Sq.Ft | 95.7990 | 95.7990 | 1361 | HCL Acid | Ltrs | 1.4370 | 6.0000 | 168.001.001.005.005.002.003.001.001.001. | 6.0000 | Material | 0 | 0.0000
667602 | A - Ground Floor Staircase 1 Flooring Work | Sq.Ft | 95.7990 | 95.7990 | 24440 | M Sand | Cu.Ft | 7.6639 | 65.0000 | 168.001.001.005.005.002.003.001.001.001. | 65.0000 | Material | 0 | 0.0000
667602 | A - Ground Floor Staircase 1 Flooring Work | Sq.Ft | 95.7990 | 95.7990 | 26445 | Tile Grout | Kgs | 0.9580 | 100.0000 | 168.001.001.005.005.002.003.001.001.001. | 100.0000 | Material | 0 | 0.0000
667603 | A - Ground Floor Staircase 1 Skirting Work | Sq.Ft | 34.8330 | 34.8330 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.774 | 300.0000 | 168.001.001.005.005.002.003.001.001.002. | 300.0000 | Material | 0 | 0.0000
667605 | A - 1st Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.002.001. | 300.0000 | Material | 0 | 0.0000
667605 | A - 1st Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.002.001. | 375.0000 | Material | 0 | 0.0000
667605 | A - 1st Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.002.001. | 33.0000 | Material | 0 | 0.0000
667605 | A - 1st Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.002.001. | 6.0000 | Material | 0 | 0.0000
667605 | A - 1st Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.002.001. | 65.0000 | Material | 0 | 0.0000
667605 | A - 1st Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.002.001. | 100.0000 | Material | 0 | 0.0000
667606 | A - 1st Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.002.002. | 300.0000 | Material | 0 | 0.0000
668050 | A - 2nd Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.003.001. | 300.0000 | Material | 0 | 0.0000
668050 | A - 2nd Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.003.001. | 375.0000 | Material | 0 | 0.0000
668050 | A - 2nd Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.003.001. | 33.0000 | Material | 0 | 0.0000
668050 | A - 2nd Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.003.001. | 6.0000 | Material | 0 | 0.0000
668050 | A - 2nd Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.003.001. | 65.0000 | Material | 0 | 0.0000
668050 | A - 2nd Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.003.001. | 100.0000 | Material | 0 | 0.0000
668051 | A - 2nd Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.003.002. | 300.0000 | Material | 0 | 0.0000
668053 | A - 3rd Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.004.001. | 300.0000 | Material | 0 | 0.0000
668053 | A - 3rd Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.004.001. | 375.0000 | Material | 0 | 0.0000
668053 | A - 3rd Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.004.001. | 33.0000 | Material | 0 | 0.0000
668053 | A - 3rd Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.004.001. | 6.0000 | Material | 0 | 0.0000
668053 | A - 3rd Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.004.001. | 65.0000 | Material | 0 | 0.0000
668053 | A - 3rd Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.004.001. | 100.0000 | Material | 0 | 0.0000
668054 | A - 3rd Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.004.002. | 300.0000 | Material | 0 | 0.0000
668056 | A - 4th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.005.001. | 300.0000 | Material | 0 | 0.0000
668056 | A - 4th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.005.001. | 375.0000 | Material | 0 | 0.0000
668056 | A - 4th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.005.001. | 33.0000 | Material | 0 | 0.0000
668056 | A - 4th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.005.001. | 6.0000 | Material | 0 | 0.0000
668056 | A - 4th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.005.001. | 65.0000 | Material | 0 | 0.0000
668056 | A - 4th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.005.001. | 100.0000 | Material | 0 | 0.0000
668057 | A - 4th Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.005.002. | 300.0000 | Material | 0 | 0.0000
668059 | A - 5th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.006.001. | 300.0000 | Material | 0 | 0.0000
668059 | A - 5th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.006.001. | 375.0000 | Material | 0 | 0.0000
668059 | A - 5th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.006.001. | 33.0000 | Material | 0 | 0.0000
668059 | A - 5th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.006.001. | 6.0000 | Material | 0 | 0.0000
668059 | A - 5th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.006.001. | 65.0000 | Material | 0 | 0.0000
668059 | A - 5th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.006.001. | 100.0000 | Material | 0 | 0.0000
668060 | A - 5th Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.006.002. | 300.0000 | Material | 0 | 0.0000
668062 | A - 6th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.007.001. | 300.0000 | Material | 0 | 0.0000
668062 | A - 6th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.007.001. | 375.0000 | Material | 0 | 0.0000
668062 | A - 6th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.007.001. | 33.0000 | Material | 0 | 0.0000
668062 | A - 6th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.007.001. | 6.0000 | Material | 0 | 0.0000
668062 | A - 6th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.007.001. | 65.0000 | Material | 0 | 0.0000
668062 | A - 6th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.007.001. | 100.0000 | Material | 0 | 0.0000
668063 | A - 6th Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.007.002. | 300.0000 | Material | 0 | 0.0000
668065 | A - 7th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.008.001. | 300.0000 | Material | 0 | 0.0000
668065 | A - 7th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.008.001. | 375.0000 | Material | 0 | 0.0000
668065 | A - 7th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.008.001. | 33.0000 | Material | 0 | 0.0000
668065 | A - 7th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.008.001. | 6.0000 | Material | 0 | 0.0000
668065 | A - 7th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.008.001. | 65.0000 | Material | 0 | 0.0000
668065 | A - 7th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.008.001. | 100.0000 | Material | 0 | 0.0000
668066 | A - 7th Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.008.002. | 300.0000 | Material | 0 | 0.0000
668068 | A - 8th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.009.001. | 300.0000 | Material | 0 | 0.0000
668068 | A - 8th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.009.001. | 375.0000 | Material | 0 | 0.0000
668068 | A - 8th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.009.001. | 33.0000 | Material | 0 | 0.0000
668068 | A - 8th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.009.001. | 6.0000 | Material | 0 | 0.0000
668068 | A - 8th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.009.001. | 65.0000 | Material | 0 | 0.0000
668068 | A - 8th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.009.001. | 100.0000 | Material | 0 | 0.0000
668069 | A - 8th Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.009.002. | 300.0000 | Material | 0 | 0.0000
668071 | A - 9th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.010.001. | 300.0000 | Material | 0 | 0.0000
668071 | A - 9th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.010.001. | 375.0000 | Material | 0 | 0.0000
668071 | A - 9th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.010.001. | 33.0000 | Material | 0 | 0.0000
668071 | A - 9th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.010.001. | 6.0000 | Material | 0 | 0.0000
668071 | A - 9th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.010.001. | 65.0000 | Material | 0 | 0.0000
668071 | A - 9th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.010.001. | 100.0000 | Material | 0 | 0.0000
668072 | A - 9th Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.010.002. | 300.0000 | Material | 0 | 0.0000
668074 | A - 10th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.011.001. | 300.0000 | Material | 0 | 0.0000
668074 | A - 10th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.011.001. | 375.0000 | Material | 0 | 0.0000
668074 | A - 10th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.011.001. | 33.0000 | Material | 0 | 0.0000
668074 | A - 10th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.011.001. | 6.0000 | Material | 0 | 0.0000
668074 | A - 10th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.011.001. | 65.0000 | Material | 0 | 0.0000
668074 | A - 10th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.011.001. | 100.0000 | Material | 0 | 0.0000
668075 | A - 10th Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.011.002. | 300.0000 | Material | 0 | 0.0000
668077 | A - 11th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.012.001. | 300.0000 | Material | 0 | 0.0000
668077 | A - 11th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.012.001. | 375.0000 | Material | 0 | 0.0000
668077 | A - 11th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.012.001. | 33.0000 | Material | 0 | 0.0000
668077 | A - 11th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.012.001. | 6.0000 | Material | 0 | 0.0000
668077 | A - 11th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.012.001. | 65.0000 | Material | 0 | 0.0000
668077 | A - 11th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.012.001. | 100.0000 | Material | 0 | 0.0000
668078 | A - 11th Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.012.002. | 300.0000 | Material | 0 | 0.0000
668080 | A - 12th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.013.001. | 300.0000 | Material | 0 | 0.0000
668080 | A - 12th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.013.001. | 375.0000 | Material | 0 | 0.0000
668080 | A - 12th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.013.001. | 33.0000 | Material | 0 | 0.0000
668080 | A - 12th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.013.001. | 6.0000 | Material | 0 | 0.0000
668080 | A - 12th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.013.001. | 65.0000 | Material | 0 | 0.0000
668080 | A - 12th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.013.001. | 100.0000 | Material | 0 | 0.0000
668081 | A - 12th Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.013.002. | 300.0000 | Material | 0 | 0.0000
668083 | A - 13th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.014.001. | 300.0000 | Material | 0 | 0.0000
668083 | A - 13th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.014.001. | 375.0000 | Material | 0 | 0.0000
668083 | A - 13th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.014.001. | 33.0000 | Material | 0 | 0.0000
668083 | A - 13th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.014.001. | 6.0000 | Material | 0 | 0.0000
668083 | A - 13th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.014.001. | 65.0000 | Material | 0 | 0.0000
668083 | A - 13th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.014.001. | 100.0000 | Material | 0 | 0.0000
668084 | A - 13th Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.014.002. | 300.0000 | Material | 0 | 0.0000
668086 | A - 14th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.015.001. | 300.0000 | Material | 0 | 0.0000
668086 | A - 14th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.015.001. | 375.0000 | Material | 0 | 0.0000
668086 | A - 14th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.015.001. | 33.0000 | Material | 0 | 0.0000
668086 | A - 14th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.015.001. | 6.0000 | Material | 0 | 0.0000
668086 | A - 14th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.015.001. | 65.0000 | Material | 0 | 0.0000
668086 | A - 14th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.015.001. | 100.0000 | Material | 0 | 0.0000
668087 | A - 14th Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.015.002. | 300.0000 | Material | 0 | 0.0000
668089 | A - 15thFloor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.016.001. | 300.0000 | Material | 0 | 0.0000
668089 | A - 15thFloor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.016.001. | 375.0000 | Material | 0 | 0.0000
668089 | A - 15thFloor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.016.001. | 33.0000 | Material | 0 | 0.0000
668089 | A - 15thFloor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.016.001. | 6.0000 | Material | 0 | 0.0000
668089 | A - 15thFloor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.016.001. | 65.0000 | Material | 0 | 0.0000
668089 | A - 15thFloor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.016.001. | 100.0000 | Material | 0 | 0.0000
668090 | A - 15th Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.016.002. | 300.0000 | Material | 0 | 0.0000
668092 | A - 16th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.017.001. | 300.0000 | Material | 0 | 0.0000
668092 | A - 16th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.017.001. | 375.0000 | Material | 0 | 0.0000
668092 | A - 16th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.017.001. | 33.0000 | Material | 0 | 0.0000
668092 | A - 16th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.017.001. | 6.0000 | Material | 0 | 0.0000
668092 | A - 16th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.017.001. | 65.0000 | Material | 0 | 0.0000
668092 | A - 16th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.017.001. | 100.0000 | Material | 0 | 0.0000
668093 | A - 16th Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.017.002. | 300.0000 | Material | 0 | 0.0000
668095 | A - 17th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.018.001. | 300.0000 | Material | 0 | 0.0000
668095 | A - 17th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.018.001. | 375.0000 | Material | 0 | 0.0000
668095 | A - 17th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.018.001. | 33.0000 | Material | 0 | 0.0000
668095 | A - 17th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.018.001. | 6.0000 | Material | 0 | 0.0000
668095 | A - 17th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.018.001. | 65.0000 | Material | 0 | 0.0000
668095 | A - 17th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.018.001. | 100.0000 | Material | 0 | 0.0000
668096 | A - 17th Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.018.002. | 300.0000 | Material | 0 | 0.0000
668098 | A - 18th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 107.652 | 300.0000 | 168.001.001.005.005.002.003.001.019.001. | 300.0000 | Material | 0 | 0.0000
668098 | A - 18th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 89 | Cement 43 Grade | Bags | 1.9397 | 375.0000 | 168.001.001.005.005.002.003.001.019.001. | 375.0000 | Material | 0 | 0.0000
668098 | A - 18th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 161 | Crush Sand | Cu.Ft | 7.7586 | 33.0000 | 168.001.001.005.005.002.003.001.019.001. | 33.0000 | Material | 0 | 0.0000
668098 | A - 18th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 1361 | HCL Acid | Ltrs | 1.4547 | 6.0000 | 168.001.001.005.005.002.003.001.019.001. | 6.0000 | Material | 0 | 0.0000
668098 | A - 18th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24440 | M Sand | Cu.Ft | 7.7586 | 65.0000 | 168.001.001.005.005.002.003.001.019.001. | 65.0000 | Material | 0 | 0.0000
668098 | A - 18th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 26445 | Tile Grout | Kgs | 0.9698 | 100.0000 | 168.001.001.005.005.002.003.001.019.001. | 100.0000 | Material | 0 | 0.0000
668099 | A - 18th Floor Staircase 1 Skirting Work | Sq.Ft | 34.6040 | 34.6040 | 24492 | Altus Beige Tile 600 X 600. | Sq.Ft | 11.697 | 300.0000 | 168.001.001.005.005.002.003.001.019.002. | 300.0000 | Material | 0 | 0.0000