## Sheet1
Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW | Project :- TANGEWALA COLONY SRA PROJECT NEW
Selected Group :- 3rd Floor | Selected Group :- 3rd Floor | Selected Group :- 3rd Floor | Selected Group :- 3rd Floor | Selected Group :- 3rd Floor | Selected Group :- 3rd Floor | Selected Group :- 3rd Floor | Selected Group :- 3rd Floor | Selected Group :- 3rd Floor | Selected Group :- 3rd Floor | Selected Group :- 3rd Floor | Selected Group :- 3rd Floor | Selected Group :- 3rd Floor | Selected Group :- 3rd Floor | Selected Group :- 3rd Floor | Selected Group :- 3rd Floor
Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty | Material/Labour Qty
Taskno | TASKNM | Unit_Name | VOLOFWORK | volofworklab | Material_No | ML_Name | ML_Unit | Qty_Required | Price_expected | Tree_Id | PriceExpected_Basic | Type | Tax_Scheme_Id | Tax_Amt | Tax_Scheme_Name
503510 | A-301 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8300 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 21.952 | 100.0000 | 168.001.001.002.007.001.003.001.001. | 100.0000 | Material | 0 | 0.0000
503510 | A-301 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8300 | 89 | Cement 43 Grade | Bags | 0.4164 | 375.0000 | 168.001.001.002.007.001.003.001.001. | 375.0000 | Material | 0 | 0.0000
503510 | A-301 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8300 | 161 | Crush Sand | Cu.Ft | 1.6656 | 33.0000 | 168.001.001.002.007.001.003.001.001. | 33.0000 | Material | 0 | 0.0000
503510 | A-301 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8300 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 20.8200 | 100.0000 | 168.001.001.002.007.001.003.001.001. | 100.0000 | Material | 0 | 0.0000
503510 | A-301 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8300 | 1361 | HCL Acid | Ltrs | 0.3123 | 6.0000 | 168.001.001.002.007.001.003.001.001. | 6.0000 | Material | 0 | 0.0000
503510 | A-301 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8300 | 24440 | M Sand | Cu.Ft | 1.6656 | 65.0000 | 168.001.001.002.007.001.003.001.001. | 65.0000 | Material | 0 | 0.0000
503510 | A-301 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8300 | 5989 | Tape Roll | No. | 0.3123 | 1327.5000 | 168.001.001.002.007.001.003.001.001. | 1327.5000 | Material | 0 | 0.0000
503510 | A-301 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8300 | 26445 | Tile Grout | Kgs | 0.2082 | 100.0000 | 168.001.001.002.007.001.003.001.001. | 100.0000 | Material | 0 | 0.0000
503511 | A-301 Internal Flat Flooring | Sq.Ft | 275.6900 | 275.6900 | 89 | Cement 43 Grade | Bags | 5.5138 | 375.0000 | 168.001.001.002.007.001.003.001.002. | 375.0000 | Material | 0 | 0.0000
503511 | A-301 Internal Flat Flooring | Sq.Ft | 275.6900 | 275.6900 | 161 | Crush Sand | Cu.Ft | 22.0552 | 33.0000 | 168.001.001.002.007.001.003.001.002. | 33.0000 | Material | 0 | 0.0000
503511 | A-301 Internal Flat Flooring | Sq.Ft | 275.6900 | 275.6900 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 275.6900 | 100.0000 | 168.001.001.002.007.001.003.001.002. | 100.0000 | Material | 0 | 0.0000
503511 | A-301 Internal Flat Flooring | Sq.Ft | 275.6900 | 275.6900 | 1361 | HCL Acid | Ltrs | 4.1354 | 6.0000 | 168.001.001.002.007.001.003.001.002. | 6.0000 | Material | 0 | 0.0000
503511 | A-301 Internal Flat Flooring | Sq.Ft | 275.6900 | 275.6900 | 24440 | M Sand | Cu.Ft | 22.0552 | 65.0000 | 168.001.001.002.007.001.003.001.002. | 65.0000 | Material | 0 | 0.0000
503511 | A-301 Internal Flat Flooring | Sq.Ft | 275.6900 | 275.6900 | 5989 | Tape Roll | No. | 4.1354 | 1327.5000 | 168.001.001.002.007.001.003.001.002. | 1327.5000 | Material | 0 | 0.0000
503511 | A-301 Internal Flat Flooring | Sq.Ft | 275.6900 | 275.6900 | 26445 | Tile Grout | Kgs | 2.7569 | 100.0000 | 168.001.001.002.007.001.003.001.002. | 100.0000 | Material | 0 | 0.0000
503511 | A-301 Internal Flat Flooring | Sq.Ft | 275.6900 | 275.6900 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.3600 | 100.0000 | 168.001.001.002.007.001.003.001.002. | 100.0000 | Material | 0 | 0.0000
503512 | A-301 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 12.59 | 100.0000 | 168.001.001.002.007.001.003.001.003. | 100.0000 | Material | 0 | 0.0000
503512 | A-301 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 89 | Cement 43 Grade | Bags | 0.2190 | 375.0000 | 168.001.001.002.007.001.003.001.003. | 375.0000 | Material | 0 | 0.0000
503512 | A-301 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.003.001.003. | 33.0000 | Material | 0 | 0.0000
503512 | A-301 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.003.001.003. | 100.0000 | Material | 0 | 0.0000
503512 | A-301 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 1361 | HCL Acid | Ltrs | 0.1643 | 6.0000 | 168.001.001.002.007.001.003.001.003. | 6.0000 | Material | 0 | 0.0000
503512 | A-301 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 24440 | M Sand | Cu.Ft | 0.8760 | 65.0000 | 168.001.001.002.007.001.003.001.003. | 65.0000 | Material | 0 | 0.0000
503512 | A-301 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 5989 | Tape Roll | No. | 0.1643 | 1327.5000 | 168.001.001.002.007.001.003.001.003. | 1327.5000 | Material | 0 | 0.0000
503512 | A-301 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 26445 | Tile Grout | Kgs | 0.1095 | 100.0000 | 168.001.001.002.007.001.003.001.003. | 100.0000 | Material | 0 | 0.0000
503514 | A-302 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 21.952 | 100.0000 | 168.001.001.002.007.001.003.002.001. | 100.0000 | Material | 0 | 0.0000
503514 | A-302 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 89 | Cement 43 Grade | Bags | 0.3938 | 375.0000 | 168.001.001.002.007.001.003.002.001. | 375.0000 | Material | 0 | 0.0000
503514 | A-302 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 161 | Crush Sand | Cu.Ft | 1.5752 | 33.0000 | 168.001.001.002.007.001.003.002.001. | 33.0000 | Material | 0 | 0.0000
503514 | A-302 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 19.6900 | 100.0000 | 168.001.001.002.007.001.003.002.001. | 100.0000 | Material | 0 | 0.0000
503514 | A-302 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 1361 | HCL Acid | Ltrs | 0.2954 | 6.0000 | 168.001.001.002.007.001.003.002.001. | 6.0000 | Material | 0 | 0.0000
503514 | A-302 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 24440 | M Sand | Cu.Ft | 1.5752 | 65.0000 | 168.001.001.002.007.001.003.002.001. | 65.0000 | Material | 0 | 0.0000
503514 | A-302 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 5989 | Tape Roll | No. | 0.2954 | 1327.5000 | 168.001.001.002.007.001.003.002.001. | 1327.5000 | Material | 0 | 0.0000
503514 | A-302 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 26445 | Tile Grout | Kgs | 0.1969 | 100.0000 | 168.001.001.002.007.001.003.002.001. | 100.0000 | Material | 0 | 0.0000
503515 | A-302 Internal Flat Flooring | Sq.Ft | 254.3700 | 254.3700 | 89 | Cement 43 Grade | Bags | 5.0874 | 375.0000 | 168.001.001.002.007.001.003.002.002. | 375.0000 | Material | 0 | 0.0000
503515 | A-302 Internal Flat Flooring | Sq.Ft | 254.3700 | 254.3700 | 161 | Crush Sand | Cu.Ft | 20.3496 | 33.0000 | 168.001.001.002.007.001.003.002.002. | 33.0000 | Material | 0 | 0.0000
503515 | A-302 Internal Flat Flooring | Sq.Ft | 254.3700 | 254.3700 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 254.3700 | 100.0000 | 168.001.001.002.007.001.003.002.002. | 100.0000 | Material | 0 | 0.0000
503515 | A-302 Internal Flat Flooring | Sq.Ft | 254.3700 | 254.3700 | 1361 | HCL Acid | Ltrs | 3.8156 | 6.0000 | 168.001.001.002.007.001.003.002.002. | 6.0000 | Material | 0 | 0.0000
503515 | A-302 Internal Flat Flooring | Sq.Ft | 254.3700 | 254.3700 | 24440 | M Sand | Cu.Ft | 20.3496 | 65.0000 | 168.001.001.002.007.001.003.002.002. | 65.0000 | Material | 0 | 0.0000
503515 | A-302 Internal Flat Flooring | Sq.Ft | 254.3700 | 254.3700 | 5989 | Tape Roll | No. | 3.8156 | 1327.5000 | 168.001.001.002.007.001.003.002.002. | 1327.5000 | Material | 0 | 0.0000
503515 | A-302 Internal Flat Flooring | Sq.Ft | 254.3700 | 254.3700 | 26445 | Tile Grout | Kgs | 2.5437 | 100.0000 | 168.001.001.002.007.001.003.002.002. | 100.0000 | Material | 0 | 0.0000
503515 | A-302 Internal Flat Flooring | Sq.Ft | 254.3700 | 254.3700 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.3600 | 100.0000 | 168.001.001.002.007.001.003.002.002. | 100.0000 | Material | 0 | 0.0000
503516 | A-302 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 12.59 | 100.0000 | 168.001.001.002.007.001.003.002.003. | 100.0000 | Material | 0 | 0.0000
503516 | A-302 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 89 | Cement 43 Grade | Bags | 0.2190 | 375.0000 | 168.001.001.002.007.001.003.002.003. | 375.0000 | Material | 0 | 0.0000
503516 | A-302 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.003.002.003. | 33.0000 | Material | 0 | 0.0000
503516 | A-302 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.003.002.003. | 100.0000 | Material | 0 | 0.0000
503516 | A-302 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 1361 | HCL Acid | Ltrs | 0.1643 | 6.0000 | 168.001.001.002.007.001.003.002.003. | 6.0000 | Material | 0 | 0.0000
503516 | A-302 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 24440 | M Sand | Cu.Ft | 0.8760 | 65.0000 | 168.001.001.002.007.001.003.002.003. | 65.0000 | Material | 0 | 0.0000
503516 | A-302 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 5989 | Tape Roll | No. | 0.1643 | 1327.5000 | 168.001.001.002.007.001.003.002.003. | 1327.5000 | Material | 0 | 0.0000
503516 | A-302 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 26445 | Tile Grout | Kgs | 0.1095 | 100.0000 | 168.001.001.002.007.001.003.002.003. | 100.0000 | Material | 0 | 0.0000
503518 | A-303 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 21.952 | 100.0000 | 168.001.001.002.007.001.003.003.001. | 100.0000 | Material | 0 | 0.0000
503518 | A-303 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 89 | Cement 43 Grade | Bags | 0.3938 | 375.0000 | 168.001.001.002.007.001.003.003.001. | 375.0000 | Material | 0 | 0.0000
503518 | A-303 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 161 | Crush Sand | Cu.Ft | 1.5752 | 33.0000 | 168.001.001.002.007.001.003.003.001. | 33.0000 | Material | 0 | 0.0000
503518 | A-303 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 19.6900 | 100.0000 | 168.001.001.002.007.001.003.003.001. | 100.0000 | Material | 0 | 0.0000
503518 | A-303 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 1361 | HCL Acid | Ltrs | 0.2954 | 6.0000 | 168.001.001.002.007.001.003.003.001. | 6.0000 | Material | 0 | 0.0000
503518 | A-303 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 24440 | M Sand | Cu.Ft | 1.5752 | 65.0000 | 168.001.001.002.007.001.003.003.001. | 65.0000 | Material | 0 | 0.0000
503518 | A-303 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 5989 | Tape Roll | No. | 0.2954 | 1327.5000 | 168.001.001.002.007.001.003.003.001. | 1327.5000 | Material | 0 | 0.0000
503518 | A-303 Bath Flooring Work | Sq.Ft | 19.6900 | 19.6900 | 26445 | Tile Grout | Kgs | 0.1969 | 100.0000 | 168.001.001.002.007.001.003.003.001. | 100.0000 | Material | 0 | 0.0000
503519 | A-303 Internal Flat Flooring | Sq.Ft | 256.4300 | 256.4300 | 89 | Cement 43 Grade | Bags | 5.1286 | 375.0000 | 168.001.001.002.007.001.003.003.002. | 375.0000 | Material | 0 | 0.0000
503519 | A-303 Internal Flat Flooring | Sq.Ft | 256.4300 | 256.4300 | 161 | Crush Sand | Cu.Ft | 20.5144 | 33.0000 | 168.001.001.002.007.001.003.003.002. | 33.0000 | Material | 0 | 0.0000
503519 | A-303 Internal Flat Flooring | Sq.Ft | 256.4300 | 256.4300 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 256.4300 | 100.0000 | 168.001.001.002.007.001.003.003.002. | 100.0000 | Material | 0 | 0.0000
503519 | A-303 Internal Flat Flooring | Sq.Ft | 256.4300 | 256.4300 | 1361 | HCL Acid | Ltrs | 3.8465 | 6.0000 | 168.001.001.002.007.001.003.003.002. | 6.0000 | Material | 0 | 0.0000
503519 | A-303 Internal Flat Flooring | Sq.Ft | 256.4300 | 256.4300 | 24440 | M Sand | Cu.Ft | 20.5144 | 65.0000 | 168.001.001.002.007.001.003.003.002. | 65.0000 | Material | 0 | 0.0000
503519 | A-303 Internal Flat Flooring | Sq.Ft | 256.4300 | 256.4300 | 5989 | Tape Roll | No. | 3.8465 | 1327.5000 | 168.001.001.002.007.001.003.003.002. | 1327.5000 | Material | 0 | 0.0000
503519 | A-303 Internal Flat Flooring | Sq.Ft | 256.4300 | 256.4300 | 26445 | Tile Grout | Kgs | 2.5643 | 100.0000 | 168.001.001.002.007.001.003.003.002. | 100.0000 | Material | 0 | 0.0000
503519 | A-303 Internal Flat Flooring | Sq.Ft | 256.4300 | 256.4300 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.3600 | 100.0000 | 168.001.001.002.007.001.003.003.002. | 100.0000 | Material | 0 | 0.0000
503520 | A-303 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 12.59 | 100.0000 | 168.001.001.002.007.001.003.003.003. | 100.0000 | Material | 0 | 0.0000
503520 | A-303 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 89 | Cement 43 Grade | Bags | 0.2190 | 375.0000 | 168.001.001.002.007.001.003.003.003. | 375.0000 | Material | 0 | 0.0000
503520 | A-303 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.003.003.003. | 33.0000 | Material | 0 | 0.0000
503520 | A-303 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.003.003.003. | 100.0000 | Material | 0 | 0.0000
503520 | A-303 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 1361 | HCL Acid | Ltrs | 0.1643 | 6.0000 | 168.001.001.002.007.001.003.003.003. | 6.0000 | Material | 0 | 0.0000
503520 | A-303 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 24440 | M Sand | Cu.Ft | 0.8760 | 65.0000 | 168.001.001.002.007.001.003.003.003. | 65.0000 | Material | 0 | 0.0000
503520 | A-303 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 5989 | Tape Roll | No. | 0.1643 | 1327.5000 | 168.001.001.002.007.001.003.003.003. | 1327.5000 | Material | 0 | 0.0000
503520 | A-303 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 26445 | Tile Grout | Kgs | 0.1095 | 100.0000 | 168.001.001.002.007.001.003.003.003. | 100.0000 | Material | 0 | 0.0000
503522 | A-304 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8200 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 21.952 | 100.0000 | 168.001.001.002.007.001.003.004.001. | 100.0000 | Material | 0 | 0.0000
503522 | A-304 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8200 | 89 | Cement 43 Grade | Bags | 0.4164 | 375.0000 | 168.001.001.002.007.001.003.004.001. | 375.0000 | Material | 0 | 0.0000
503522 | A-304 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8200 | 161 | Crush Sand | Cu.Ft | 1.6656 | 33.0000 | 168.001.001.002.007.001.003.004.001. | 33.0000 | Material | 0 | 0.0000
503522 | A-304 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8200 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 20.8200 | 100.0000 | 168.001.001.002.007.001.003.004.001. | 100.0000 | Material | 0 | 0.0000
503522 | A-304 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8200 | 1361 | HCL Acid | Ltrs | 0.3123 | 6.0000 | 168.001.001.002.007.001.003.004.001. | 6.0000 | Material | 0 | 0.0000
503522 | A-304 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8200 | 24440 | M Sand | Cu.Ft | 1.6656 | 65.0000 | 168.001.001.002.007.001.003.004.001. | 65.0000 | Material | 0 | 0.0000
503522 | A-304 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8200 | 5989 | Tape Roll | No. | 0.3123 | 1327.5000 | 168.001.001.002.007.001.003.004.001. | 1327.5000 | Material | 0 | 0.0000
503522 | A-304 Bath Flooring Work | Sq.Ft | 20.8200 | 20.8200 | 26445 | Tile Grout | Kgs | 0.2082 | 100.0000 | 168.001.001.002.007.001.003.004.001. | 100.0000 | Material | 0 | 0.0000
503523 | A-304 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 89 | Cement 43 Grade | Bags | 5.1310 | 375.0000 | 168.001.001.002.007.001.003.004.002. | 375.0000 | Material | 0 | 0.0000
503523 | A-304 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 161 | Crush Sand | Cu.Ft | 20.5240 | 33.0000 | 168.001.001.002.007.001.003.004.002. | 33.0000 | Material | 0 | 0.0000
503523 | A-304 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 256.5500 | 100.0000 | 168.001.001.002.007.001.003.004.002. | 100.0000 | Material | 0 | 0.0000
503523 | A-304 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 1361 | HCL Acid | Ltrs | 3.8483 | 6.0000 | 168.001.001.002.007.001.003.004.002. | 6.0000 | Material | 0 | 0.0000
503523 | A-304 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 24440 | M Sand | Cu.Ft | 20.5240 | 65.0000 | 168.001.001.002.007.001.003.004.002. | 65.0000 | Material | 0 | 0.0000
503523 | A-304 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 5989 | Tape Roll | No. | 3.8483 | 1327.5000 | 168.001.001.002.007.001.003.004.002. | 1327.5000 | Material | 0 | 0.0000
503523 | A-304 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 26445 | Tile Grout | Kgs | 2.5655 | 100.0000 | 168.001.001.002.007.001.003.004.002. | 100.0000 | Material | 0 | 0.0000
503523 | A-304 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.3600 | 100.0000 | 168.001.001.002.007.001.003.004.002. | 100.0000 | Material | 0 | 0.0000
503524 | A-304 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 12.59 | 100.0000 | 168.001.001.002.007.001.003.004.003. | 100.0000 | Material | 0 | 0.0000
503524 | A-304 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 89 | Cement 43 Grade | Bags | 0.2190 | 375.0000 | 168.001.001.002.007.001.003.004.003. | 375.0000 | Material | 0 | 0.0000
503524 | A-304 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.003.004.003. | 33.0000 | Material | 0 | 0.0000
503524 | A-304 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.003.004.003. | 100.0000 | Material | 0 | 0.0000
503524 | A-304 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 1361 | HCL Acid | Ltrs | 0.1643 | 6.0000 | 168.001.001.002.007.001.003.004.003. | 6.0000 | Material | 0 | 0.0000
503524 | A-304 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 24440 | M Sand | Cu.Ft | 0.8760 | 65.0000 | 168.001.001.002.007.001.003.004.003. | 65.0000 | Material | 0 | 0.0000
503524 | A-304 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 5989 | Tape Roll | No. | 0.1643 | 1327.5000 | 168.001.001.002.007.001.003.004.003. | 1327.5000 | Material | 0 | 0.0000
503524 | A-304 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 26445 | Tile Grout | Kgs | 0.1095 | 100.0000 | 168.001.001.002.007.001.003.004.003. | 100.0000 | Material | 0 | 0.0000
503526 | A-305 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 21.952 | 100.0000 | 168.001.001.002.007.001.003.005.001. | 100.0000 | Material | 0 | 0.0000
503526 | A-305 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 89 | Cement 43 Grade | Bags | 0.4174 | 375.0000 | 168.001.001.002.007.001.003.005.001. | 375.0000 | Material | 0 | 0.0000
503526 | A-305 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 161 | Crush Sand | Cu.Ft | 1.6696 | 33.0000 | 168.001.001.002.007.001.003.005.001. | 33.0000 | Material | 0 | 0.0000
503526 | A-305 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 20.8700 | 100.0000 | 168.001.001.002.007.001.003.005.001. | 100.0000 | Material | 0 | 0.0000
503526 | A-305 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 1361 | HCL Acid | Ltrs | 0.3131 | 6.0000 | 168.001.001.002.007.001.003.005.001. | 6.0000 | Material | 0 | 0.0000
503526 | A-305 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 24440 | M Sand | Cu.Ft | 1.6696 | 65.0000 | 168.001.001.002.007.001.003.005.001. | 65.0000 | Material | 0 | 0.0000
503526 | A-305 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 5989 | Tape Roll | No. | 0.3131 | 1327.5000 | 168.001.001.002.007.001.003.005.001. | 1327.5000 | Material | 0 | 0.0000
503526 | A-305 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 26445 | Tile Grout | Kgs | 0.2087 | 100.0000 | 168.001.001.002.007.001.003.005.001. | 100.0000 | Material | 0 | 0.0000
503527 | A-305 Internal Flat Flooring | Sq.Ft | 249.5700 | 249.5700 | 89 | Cement 43 Grade | Bags | 4.9914 | 375.0000 | 168.001.001.002.007.001.003.005.002. | 375.0000 | Material | 0 | 0.0000
503527 | A-305 Internal Flat Flooring | Sq.Ft | 249.5700 | 249.5700 | 161 | Crush Sand | Cu.Ft | 19.9656 | 33.0000 | 168.001.001.002.007.001.003.005.002. | 33.0000 | Material | 0 | 0.0000
503527 | A-305 Internal Flat Flooring | Sq.Ft | 249.5700 | 249.5700 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 249.5700 | 100.0000 | 168.001.001.002.007.001.003.005.002. | 100.0000 | Material | 0 | 0.0000
503527 | A-305 Internal Flat Flooring | Sq.Ft | 249.5700 | 249.5700 | 1361 | HCL Acid | Ltrs | 3.7436 | 6.0000 | 168.001.001.002.007.001.003.005.002. | 6.0000 | Material | 0 | 0.0000
503527 | A-305 Internal Flat Flooring | Sq.Ft | 249.5700 | 249.5700 | 24440 | M Sand | Cu.Ft | 19.9656 | 65.0000 | 168.001.001.002.007.001.003.005.002. | 65.0000 | Material | 0 | 0.0000
503527 | A-305 Internal Flat Flooring | Sq.Ft | 249.5700 | 249.5700 | 5989 | Tape Roll | No. | 3.7436 | 1327.5000 | 168.001.001.002.007.001.003.005.002. | 1327.5000 | Material | 0 | 0.0000
503527 | A-305 Internal Flat Flooring | Sq.Ft | 249.5700 | 249.5700 | 26445 | Tile Grout | Kgs | 2.4957 | 100.0000 | 168.001.001.002.007.001.003.005.002. | 100.0000 | Material | 0 | 0.0000
503527 | A-305 Internal Flat Flooring | Sq.Ft | 249.5700 | 249.5700 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.3600 | 100.0000 | 168.001.001.002.007.001.003.005.002. | 100.0000 | Material | 0 | 0.0000
503528 | A-305 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 12.59 | 100.0000 | 168.001.001.002.007.001.003.005.003. | 100.0000 | Material | 0 | 0.0000
503528 | A-305 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 89 | Cement 43 Grade | Bags | 0.2190 | 375.0000 | 168.001.001.002.007.001.003.005.003. | 375.0000 | Material | 0 | 0.0000
503528 | A-305 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.003.005.003. | 33.0000 | Material | 0 | 0.0000
503528 | A-305 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.003.005.003. | 100.0000 | Material | 0 | 0.0000
503528 | A-305 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 1361 | HCL Acid | Ltrs | 0.1643 | 6.0000 | 168.001.001.002.007.001.003.005.003. | 6.0000 | Material | 0 | 0.0000
503528 | A-305 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 24440 | M Sand | Cu.Ft | 0.8760 | 65.0000 | 168.001.001.002.007.001.003.005.003. | 65.0000 | Material | 0 | 0.0000
503528 | A-305 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 5989 | Tape Roll | No. | 0.1643 | 1327.5000 | 168.001.001.002.007.001.003.005.003. | 1327.5000 | Material | 0 | 0.0000
503528 | A-305 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 26445 | Tile Grout | Kgs | 0.1095 | 100.0000 | 168.001.001.002.007.001.003.005.003. | 100.0000 | Material | 0 | 0.0000
503530 | A-306 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 21.952 | 100.0000 | 168.001.001.002.007.001.003.006.001. | 100.0000 | Material | 0 | 0.0000
503530 | A-306 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 89 | Cement 43 Grade | Bags | 0.4174 | 375.0000 | 168.001.001.002.007.001.003.006.001. | 375.0000 | Material | 0 | 0.0000
503530 | A-306 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 161 | Crush Sand | Cu.Ft | 1.6696 | 33.0000 | 168.001.001.002.007.001.003.006.001. | 33.0000 | Material | 0 | 0.0000
503530 | A-306 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 20.8700 | 100.0000 | 168.001.001.002.007.001.003.006.001. | 100.0000 | Material | 0 | 0.0000
503530 | A-306 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 1361 | HCL Acid | Ltrs | 0.3131 | 6.0000 | 168.001.001.002.007.001.003.006.001. | 6.0000 | Material | 0 | 0.0000
503530 | A-306 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 24440 | M Sand | Cu.Ft | 1.6696 | 65.0000 | 168.001.001.002.007.001.003.006.001. | 65.0000 | Material | 0 | 0.0000
503530 | A-306 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 5989 | Tape Roll | No. | 0.3131 | 1327.5000 | 168.001.001.002.007.001.003.006.001. | 1327.5000 | Material | 0 | 0.0000
503530 | A-306 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 26445 | Tile Grout | Kgs | 0.2087 | 100.0000 | 168.001.001.002.007.001.003.006.001. | 100.0000 | Material | 0 | 0.0000
503531 | A-306 Internal Flat Flooring | Sq.Ft | 250.4500 | 250.4500 | 89 | Cement 43 Grade | Bags | 5.0090 | 375.0000 | 168.001.001.002.007.001.003.006.002. | 375.0000 | Material | 0 | 0.0000
503531 | A-306 Internal Flat Flooring | Sq.Ft | 250.4500 | 250.4500 | 161 | Crush Sand | Cu.Ft | 20.0360 | 33.0000 | 168.001.001.002.007.001.003.006.002. | 33.0000 | Material | 0 | 0.0000
503531 | A-306 Internal Flat Flooring | Sq.Ft | 250.4500 | 250.4500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 250.4500 | 100.0000 | 168.001.001.002.007.001.003.006.002. | 100.0000 | Material | 0 | 0.0000
503531 | A-306 Internal Flat Flooring | Sq.Ft | 250.4500 | 250.4500 | 1361 | HCL Acid | Ltrs | 3.7568 | 6.0000 | 168.001.001.002.007.001.003.006.002. | 6.0000 | Material | 0 | 0.0000
503531 | A-306 Internal Flat Flooring | Sq.Ft | 250.4500 | 250.4500 | 24440 | M Sand | Cu.Ft | 20.0360 | 65.0000 | 168.001.001.002.007.001.003.006.002. | 65.0000 | Material | 0 | 0.0000
503531 | A-306 Internal Flat Flooring | Sq.Ft | 250.4500 | 250.4500 | 5989 | Tape Roll | No. | 3.7568 | 1327.5000 | 168.001.001.002.007.001.003.006.002. | 1327.5000 | Material | 0 | 0.0000
503531 | A-306 Internal Flat Flooring | Sq.Ft | 250.4500 | 250.4500 | 26445 | Tile Grout | Kgs | 2.5045 | 100.0000 | 168.001.001.002.007.001.003.006.002. | 100.0000 | Material | 0 | 0.0000
503531 | A-306 Internal Flat Flooring | Sq.Ft | 250.4500 | 250.4500 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.3600 | 100.0000 | 168.001.001.002.007.001.003.006.002. | 100.0000 | Material | 0 | 0.0000
503532 | A-306 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 12.59 | 100.0000 | 168.001.001.002.007.001.003.006.003. | 100.0000 | Material | 0 | 0.0000
503532 | A-306 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 89 | Cement 43 Grade | Bags | 0.2190 | 375.0000 | 168.001.001.002.007.001.003.006.003. | 375.0000 | Material | 0 | 0.0000
503532 | A-306 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.003.006.003. | 33.0000 | Material | 0 | 0.0000
503532 | A-306 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.003.006.003. | 100.0000 | Material | 0 | 0.0000
503532 | A-306 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 1361 | HCL Acid | Ltrs | 0.1643 | 6.0000 | 168.001.001.002.007.001.003.006.003. | 6.0000 | Material | 0 | 0.0000
503532 | A-306 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 24440 | M Sand | Cu.Ft | 0.8760 | 65.0000 | 168.001.001.002.007.001.003.006.003. | 65.0000 | Material | 0 | 0.0000
503532 | A-306 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 5989 | Tape Roll | No. | 0.1643 | 1327.5000 | 168.001.001.002.007.001.003.006.003. | 1327.5000 | Material | 0 | 0.0000
503532 | A-306 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 26445 | Tile Grout | Kgs | 0.1095 | 100.0000 | 168.001.001.002.007.001.003.006.003. | 100.0000 | Material | 0 | 0.0000
503534 | A-307 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 21.952 | 100.0000 | 168.001.001.002.007.001.003.007.001. | 100.0000 | Material | 0 | 0.0000
503534 | A-307 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 89 | Cement 43 Grade | Bags | 0.4174 | 375.0000 | 168.001.001.002.007.001.003.007.001. | 375.0000 | Material | 0 | 0.0000
503534 | A-307 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 161 | Crush Sand | Cu.Ft | 1.6696 | 33.0000 | 168.001.001.002.007.001.003.007.001. | 33.0000 | Material | 0 | 0.0000
503534 | A-307 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 20.8700 | 100.0000 | 168.001.001.002.007.001.003.007.001. | 100.0000 | Material | 0 | 0.0000
503534 | A-307 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 1361 | HCL Acid | Ltrs | 0.3131 | 6.0000 | 168.001.001.002.007.001.003.007.001. | 6.0000 | Material | 0 | 0.0000
503534 | A-307 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 24440 | M Sand | Cu.Ft | 1.6696 | 65.0000 | 168.001.001.002.007.001.003.007.001. | 65.0000 | Material | 0 | 0.0000
503534 | A-307 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 5989 | Tape Roll | No. | 0.3131 | 1327.5000 | 168.001.001.002.007.001.003.007.001. | 1327.5000 | Material | 0 | 0.0000
503534 | A-307 Bath Flooring Work | Sq.Ft | 20.8700 | 20.8700 | 26445 | Tile Grout | Kgs | 0.2087 | 100.0000 | 168.001.001.002.007.001.003.007.001. | 100.0000 | Material | 0 | 0.0000
503535 | A-307 Internal Flat Flooring | Sq.Ft | 251.8700 | 251.8700 | 89 | Cement 43 Grade | Bags | 5.0374 | 375.0000 | 168.001.001.002.007.001.003.007.002. | 375.0000 | Material | 0 | 0.0000
503535 | A-307 Internal Flat Flooring | Sq.Ft | 251.8700 | 251.8700 | 161 | Crush Sand | Cu.Ft | 20.1496 | 33.0000 | 168.001.001.002.007.001.003.007.002. | 33.0000 | Material | 0 | 0.0000
503535 | A-307 Internal Flat Flooring | Sq.Ft | 251.8700 | 251.8700 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 251.8700 | 100.0000 | 168.001.001.002.007.001.003.007.002. | 100.0000 | Material | 0 | 0.0000
503535 | A-307 Internal Flat Flooring | Sq.Ft | 251.8700 | 251.8700 | 1361 | HCL Acid | Ltrs | 3.7781 | 6.0000 | 168.001.001.002.007.001.003.007.002. | 6.0000 | Material | 0 | 0.0000
503535 | A-307 Internal Flat Flooring | Sq.Ft | 251.8700 | 251.8700 | 24440 | M Sand | Cu.Ft | 20.1496 | 65.0000 | 168.001.001.002.007.001.003.007.002. | 65.0000 | Material | 0 | 0.0000
503535 | A-307 Internal Flat Flooring | Sq.Ft | 251.8700 | 251.8700 | 5989 | Tape Roll | No. | 3.7781 | 1327.5000 | 168.001.001.002.007.001.003.007.002. | 1327.5000 | Material | 0 | 0.0000
503535 | A-307 Internal Flat Flooring | Sq.Ft | 251.8700 | 251.8700 | 26445 | Tile Grout | Kgs | 2.5187 | 100.0000 | 168.001.001.002.007.001.003.007.002. | 100.0000 | Material | 0 | 0.0000
503535 | A-307 Internal Flat Flooring | Sq.Ft | 251.8700 | 251.8700 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.3600 | 100.0000 | 168.001.001.002.007.001.003.007.002. | 100.0000 | Material | 0 | 0.0000
503536 | A-307 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 12.59 | 100.0000 | 168.001.001.002.007.001.003.007.003. | 100.0000 | Material | 0 | 0.0000
503536 | A-307 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 89 | Cement 43 Grade | Bags | 0.2190 | 375.0000 | 168.001.001.002.007.001.003.007.003. | 375.0000 | Material | 0 | 0.0000
503536 | A-307 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.003.007.003. | 33.0000 | Material | 0 | 0.0000
503536 | A-307 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.003.007.003. | 100.0000 | Material | 0 | 0.0000
503536 | A-307 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 1361 | HCL Acid | Ltrs | 0.1643 | 6.0000 | 168.001.001.002.007.001.003.007.003. | 6.0000 | Material | 0 | 0.0000
503536 | A-307 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 24440 | M Sand | Cu.Ft | 0.8760 | 65.0000 | 168.001.001.002.007.001.003.007.003. | 65.0000 | Material | 0 | 0.0000
503536 | A-307 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 5989 | Tape Roll | No. | 0.1643 | 1327.5000 | 168.001.001.002.007.001.003.007.003. | 1327.5000 | Material | 0 | 0.0000
503536 | A-307 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 26445 | Tile Grout | Kgs | 0.1095 | 100.0000 | 168.001.001.002.007.001.003.007.003. | 100.0000 | Material | 0 | 0.0000
503538 | A-308 Bath Flooring Work | Sq.Ft | 21.7600 | 21.7600 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 21.952 | 100.0000 | 168.001.001.002.007.001.003.008.001. | 100.0000 | Material | 0 | 0.0000
503538 | A-308 Bath Flooring Work | Sq.Ft | 21.7600 | 21.7600 | 89 | Cement 43 Grade | Bags | 0.4352 | 375.0000 | 168.001.001.002.007.001.003.008.001. | 375.0000 | Material | 0 | 0.0000
503538 | A-308 Bath Flooring Work | Sq.Ft | 21.7600 | 21.7600 | 161 | Crush Sand | Cu.Ft | 1.7408 | 33.0000 | 168.001.001.002.007.001.003.008.001. | 33.0000 | Material | 0 | 0.0000
503538 | A-308 Bath Flooring Work | Sq.Ft | 21.7600 | 21.7600 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 21.7600 | 100.0000 | 168.001.001.002.007.001.003.008.001. | 100.0000 | Material | 0 | 0.0000
503538 | A-308 Bath Flooring Work | Sq.Ft | 21.7600 | 21.7600 | 1361 | HCL Acid | Ltrs | 0.3264 | 6.0000 | 168.001.001.002.007.001.003.008.001. | 6.0000 | Material | 0 | 0.0000
503538 | A-308 Bath Flooring Work | Sq.Ft | 21.7600 | 21.7600 | 24440 | M Sand | Cu.Ft | 1.7408 | 65.0000 | 168.001.001.002.007.001.003.008.001. | 65.0000 | Material | 0 | 0.0000
503538 | A-308 Bath Flooring Work | Sq.Ft | 21.7600 | 21.7600 | 5989 | Tape Roll | No. | 0.3264 | 1327.5000 | 168.001.001.002.007.001.003.008.001. | 1327.5000 | Material | 0 | 0.0000
503538 | A-308 Bath Flooring Work | Sq.Ft | 21.7600 | 21.7600 | 26445 | Tile Grout | Kgs | 0.2176 | 100.0000 | 168.001.001.002.007.001.003.008.001. | 100.0000 | Material | 0 | 0.0000
503539 | A-308 Internal Flat Flooring | Sq.Ft | 250.7700 | 250.7700 | 89 | Cement 43 Grade | Bags | 5.0154 | 375.0000 | 168.001.001.002.007.001.003.008.002. | 375.0000 | Material | 0 | 0.0000
503539 | A-308 Internal Flat Flooring | Sq.Ft | 250.7700 | 250.7700 | 161 | Crush Sand | Cu.Ft | 20.0616 | 33.0000 | 168.001.001.002.007.001.003.008.002. | 33.0000 | Material | 0 | 0.0000
503539 | A-308 Internal Flat Flooring | Sq.Ft | 250.7700 | 250.7700 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 250.7700 | 100.0000 | 168.001.001.002.007.001.003.008.002. | 100.0000 | Material | 0 | 0.0000
503539 | A-308 Internal Flat Flooring | Sq.Ft | 250.7700 | 250.7700 | 1361 | HCL Acid | Ltrs | 3.7616 | 6.0000 | 168.001.001.002.007.001.003.008.002. | 6.0000 | Material | 0 | 0.0000
503539 | A-308 Internal Flat Flooring | Sq.Ft | 250.7700 | 250.7700 | 24440 | M Sand | Cu.Ft | 20.0616 | 65.0000 | 168.001.001.002.007.001.003.008.002. | 65.0000 | Material | 0 | 0.0000
503539 | A-308 Internal Flat Flooring | Sq.Ft | 250.7700 | 250.7700 | 5989 | Tape Roll | No. | 3.7616 | 1327.5000 | 168.001.001.002.007.001.003.008.002. | 1327.5000 | Material | 0 | 0.0000
503539 | A-308 Internal Flat Flooring | Sq.Ft | 250.7700 | 250.7700 | 26445 | Tile Grout | Kgs | 2.5077 | 100.0000 | 168.001.001.002.007.001.003.008.002. | 100.0000 | Material | 0 | 0.0000
503539 | A-308 Internal Flat Flooring | Sq.Ft | 250.7700 | 250.7700 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.3600 | 100.0000 | 168.001.001.002.007.001.003.008.002. | 100.0000 | Material | 0 | 0.0000
503540 | A-308 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 12.59 | 100.0000 | 168.001.001.002.007.001.003.008.003. | 100.0000 | Material | 0 | 0.0000
503540 | A-308 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 89 | Cement 43 Grade | Bags | 0.2190 | 375.0000 | 168.001.001.002.007.001.003.008.003. | 375.0000 | Material | 0 | 0.0000
503540 | A-308 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.003.008.003. | 33.0000 | Material | 0 | 0.0000
503540 | A-308 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 10.9500 | 100.0000 | 168.001.001.002.007.001.003.008.003. | 100.0000 | Material | 0 | 0.0000
503540 | A-308 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 1361 | HCL Acid | Ltrs | 0.1643 | 6.0000 | 168.001.001.002.007.001.003.008.003. | 6.0000 | Material | 0 | 0.0000
503540 | A-308 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 24440 | M Sand | Cu.Ft | 0.8760 | 65.0000 | 168.001.001.002.007.001.003.008.003. | 65.0000 | Material | 0 | 0.0000
503540 | A-308 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 5989 | Tape Roll | No. | 0.1643 | 1327.5000 | 168.001.001.002.007.001.003.008.003. | 1327.5000 | Material | 0 | 0.0000
503540 | A-308 WC Flooring Work | Sq.Ft | 10.9500 | 10.9500 | 26445 | Tile Grout | Kgs | 0.1095 | 100.0000 | 168.001.001.002.007.001.003.008.003. | 100.0000 | Material | 0 | 0.0000
503542 | B-301 Bath Flooring Work | Sq.Ft | 23.0100 | 23.0100 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 23.0100 | 100.0000 | 168.001.001.002.007.001.003.009.001. | 100.0000 | Material | 0 | 0.0000
503542 | B-301 Bath Flooring Work | Sq.Ft | 23.0100 | 23.0100 | 89 | Cement 43 Grade | Bags | 0.7800 | 375.0000 | 168.001.001.002.007.001.003.009.001. | 375.0000 | Material | 0 | 0.0000
503542 | B-301 Bath Flooring Work | Sq.Ft | 23.0100 | 23.0100 | 161 | Crush Sand | Cu.Ft | 3.1290 | 33.0000 | 168.001.001.002.007.001.003.009.001. | 33.0000 | Material | 0 | 0.0000
503542 | B-301 Bath Flooring Work | Sq.Ft | 23.0100 | 23.0100 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 23.0100 | 100.0000 | 168.001.001.002.007.001.003.009.001. | 100.0000 | Material | 0 | 0.0000
503542 | B-301 Bath Flooring Work | Sq.Ft | 23.0100 | 23.0100 | 1361 | HCL Acid | Ltrs | 0.3452 | 6.0000 | 168.001.001.002.007.001.003.009.001. | 6.0000 | Material | 0 | 0.0000
503542 | B-301 Bath Flooring Work | Sq.Ft | 23.0100 | 23.0100 | 24440 | M Sand | Cu.Ft | 3.1290 | 65.0000 | 168.001.001.002.007.001.003.009.001. | 65.0000 | Material | 0 | 0.0000
503542 | B-301 Bath Flooring Work | Sq.Ft | 23.0100 | 23.0100 | 5989 | Tape Roll | No. | 0.3452 | 1327.5000 | 168.001.001.002.007.001.003.009.001. | 1327.5000 | Material | 0 | 0.0000
503542 | B-301 Bath Flooring Work | Sq.Ft | 23.0100 | 23.0100 | 26445 | Tile Grout | Kgs | 0.2301 | 100.0000 | 168.001.001.002.007.001.003.009.001. | 100.0000 | Material | 0 | 0.0000
503543 | B-301 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 89 | Cement 43 Grade | Bags | 5.1310 | 375.0000 | 168.001.001.002.007.001.003.009.002. | 375.0000 | Material | 0 | 0.0000
503543 | B-301 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 161 | Crush Sand | Cu.Ft | 20.5240 | 33.0000 | 168.001.001.002.007.001.003.009.002. | 33.0000 | Material | 0 | 0.0000
503543 | B-301 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 256.5500 | 100.0000 | 168.001.001.002.007.001.003.009.002. | 100.0000 | Material | 0 | 0.0000
503543 | B-301 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 1361 | HCL Acid | Ltrs | 3.8483 | 6.0000 | 168.001.001.002.007.001.003.009.002. | 6.0000 | Material | 0 | 0.0000
503543 | B-301 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 24440 | M Sand | Cu.Ft | 20.5240 | 65.0000 | 168.001.001.002.007.001.003.009.002. | 65.0000 | Material | 0 | 0.0000
503543 | B-301 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 5989 | Tape Roll | No. | 3.8483 | 1327.5000 | 168.001.001.002.007.001.003.009.002. | 1327.5000 | Material | 0 | 0.0000
503543 | B-301 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 26445 | Tile Grout | Kgs | 2.5655 | 100.0000 | 168.001.001.002.007.001.003.009.002. | 100.0000 | Material | 0 | 0.0000
503543 | B-301 Internal Flat Flooring | Sq.Ft | 256.5500 | 256.5500 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.3600 | 100.0000 | 168.001.001.002.007.001.003.009.002. | 100.0000 | Material | 0 | 0.0000
503544 | B-301 WC Flooring Work | Sq.Ft | 13.7990 | 13.7990 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 13.7990 | 100.0000 | 168.001.001.002.007.001.003.009.003. | 100.0000 | Material | 0 | 0.0000
503544 | B-301 WC Flooring Work | Sq.Ft | 13.7990 | 13.7990 | 89 | Cement 43 Grade | Bags | 0.2760 | 375.0000 | 168.001.001.002.007.001.003.009.003. | 375.0000 | Material | 0 | 0.0000
503544 | B-301 WC Flooring Work | Sq.Ft | 13.7990 | 13.7990 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.003.009.003. | 33.0000 | Material | 0 | 0.0000
503544 | B-301 WC Flooring Work | Sq.Ft | 13.7990 | 13.7990 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 13.7990 | 100.0000 | 168.001.001.002.007.001.003.009.003. | 100.0000 | Material | 0 | 0.0000
503544 | B-301 WC Flooring Work | Sq.Ft | 13.7990 | 13.7990 | 1361 | HCL Acid | Ltrs | 0.2070 | 6.0000 | 168.001.001.002.007.001.003.009.003. | 6.0000 | Material | 0 | 0.0000
503544 | B-301 WC Flooring Work | Sq.Ft | 13.7990 | 13.7990 | 24440 | M Sand | Cu.Ft | 1.1039 | 65.0000 | 168.001.001.002.007.001.003.009.003. | 65.0000 | Material | 0 | 0.0000
503544 | B-301 WC Flooring Work | Sq.Ft | 13.7990 | 13.7990 | 5989 | Tape Roll | No. | 0.2070 | 1327.5000 | 168.001.001.002.007.001.003.009.003. | 1327.5000 | Material | 0 | 0.0000
503544 | B-301 WC Flooring Work | Sq.Ft | 13.7990 | 13.7990 | 26445 | Tile Grout | Kgs | 0.1380 | 100.0000 | 168.001.001.002.007.001.003.009.003. | 100.0000 | Material | 0 | 0.0000
503546 | B-302 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 23.0000 | 100.0000 | 168.001.001.002.007.001.003.010.001. | 100.0000 | Material | 0 | 0.0000
503546 | B-302 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 89 | Cement 43 Grade | Bags | 0.7800 | 375.0000 | 168.001.001.002.007.001.003.010.001. | 375.0000 | Material | 0 | 0.0000
503546 | B-302 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 161 | Crush Sand | Cu.Ft | 3.1290 | 33.0000 | 168.001.001.002.007.001.003.010.001. | 33.0000 | Material | 0 | 0.0000
503546 | B-302 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 23.0000 | 100.0000 | 168.001.001.002.007.001.003.010.001. | 100.0000 | Material | 0 | 0.0000
503546 | B-302 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 1361 | HCL Acid | Ltrs | 0.3450 | 6.0000 | 168.001.001.002.007.001.003.010.001. | 6.0000 | Material | 0 | 0.0000
503546 | B-302 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 24440 | M Sand | Cu.Ft | 3.1290 | 65.0000 | 168.001.001.002.007.001.003.010.001. | 65.0000 | Material | 0 | 0.0000
503546 | B-302 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 5989 | Tape Roll | No. | 0.3450 | 1327.5000 | 168.001.001.002.007.001.003.010.001. | 1327.5000 | Material | 0 | 0.0000
503546 | B-302 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 26445 | Tile Grout | Kgs | 0.2300 | 100.0000 | 168.001.001.002.007.001.003.010.001. | 100.0000 | Material | 0 | 0.0000
503547 | B-302 Internal Flat Flooring | Sq.Ft | 275.5200 | 275.5200 | 89 | Cement 43 Grade | Bags | 5.5104 | 375.0000 | 168.001.001.002.007.001.003.010.002. | 375.0000 | Material | 0 | 0.0000
503547 | B-302 Internal Flat Flooring | Sq.Ft | 275.5200 | 275.5200 | 161 | Crush Sand | Cu.Ft | 22.0416 | 33.0000 | 168.001.001.002.007.001.003.010.002. | 33.0000 | Material | 0 | 0.0000
503547 | B-302 Internal Flat Flooring | Sq.Ft | 275.5200 | 275.5200 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 275.5200 | 100.0000 | 168.001.001.002.007.001.003.010.002. | 100.0000 | Material | 0 | 0.0000
503547 | B-302 Internal Flat Flooring | Sq.Ft | 275.5200 | 275.5200 | 1361 | HCL Acid | Ltrs | 4.1328 | 6.0000 | 168.001.001.002.007.001.003.010.002. | 6.0000 | Material | 0 | 0.0000
503547 | B-302 Internal Flat Flooring | Sq.Ft | 275.5200 | 275.5200 | 24440 | M Sand | Cu.Ft | 22.0416 | 65.0000 | 168.001.001.002.007.001.003.010.002. | 65.0000 | Material | 0 | 0.0000
503547 | B-302 Internal Flat Flooring | Sq.Ft | 275.5200 | 275.5200 | 5989 | Tape Roll | No. | 4.1328 | 1327.5000 | 168.001.001.002.007.001.003.010.002. | 1327.5000 | Material | 0 | 0.0000
503547 | B-302 Internal Flat Flooring | Sq.Ft | 275.5200 | 275.5200 | 26445 | Tile Grout | Kgs | 2.7552 | 100.0000 | 168.001.001.002.007.001.003.010.002. | 100.0000 | Material | 0 | 0.0000
503547 | B-302 Internal Flat Flooring | Sq.Ft | 275.5200 | 275.5200 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.3600 | 100.0000 | 168.001.001.002.007.001.003.010.002. | 100.0000 | Material | 0 | 0.0000
503548 | B-302 WC Flooring Work | Sq.Ft | 13.8100 | 13.8100 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 13.8100 | 100.0000 | 168.001.001.002.007.001.003.010.003. | 100.0000 | Material | 0 | 0.0000
503548 | B-302 WC Flooring Work | Sq.Ft | 13.8100 | 13.8100 | 89 | Cement 43 Grade | Bags | 0.2762 | 375.0000 | 168.001.001.002.007.001.003.010.003. | 375.0000 | Material | 0 | 0.0000
503548 | B-302 WC Flooring Work | Sq.Ft | 13.8100 | 13.8100 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.003.010.003. | 33.0000 | Material | 0 | 0.0000
503548 | B-302 WC Flooring Work | Sq.Ft | 13.8100 | 13.8100 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 13.8100 | 100.0000 | 168.001.001.002.007.001.003.010.003. | 100.0000 | Material | 0 | 0.0000
503548 | B-302 WC Flooring Work | Sq.Ft | 13.8100 | 13.8100 | 1361 | HCL Acid | Ltrs | 0.2072 | 6.0000 | 168.001.001.002.007.001.003.010.003. | 6.0000 | Material | 0 | 0.0000
503548 | B-302 WC Flooring Work | Sq.Ft | 13.8100 | 13.8100 | 24440 | M Sand | Cu.Ft | 1.1048 | 65.0000 | 168.001.001.002.007.001.003.010.003. | 65.0000 | Material | 0 | 0.0000
503548 | B-302 WC Flooring Work | Sq.Ft | 13.8100 | 13.8100 | 5989 | Tape Roll | No. | 0.2072 | 1327.5000 | 168.001.001.002.007.001.003.010.003. | 1327.5000 | Material | 0 | 0.0000
503548 | B-302 WC Flooring Work | Sq.Ft | 13.8100 | 13.8100 | 26445 | Tile Grout | Kgs | 0.1381 | 100.0000 | 168.001.001.002.007.001.003.010.003. | 100.0000 | Material | 0 | 0.0000
503550 | B-303 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 23.0000 | 100.0000 | 168.001.001.002.007.001.003.011.001. | 100.0000 | Material | 0 | 0.0000
503550 | B-303 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 89 | Cement 43 Grade | Bags | 0.7800 | 375.0000 | 168.001.001.002.007.001.003.011.001. | 375.0000 | Material | 0 | 0.0000
503550 | B-303 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 161 | Crush Sand | Cu.Ft | 3.1290 | 33.0000 | 168.001.001.002.007.001.003.011.001. | 33.0000 | Material | 0 | 0.0000
503550 | B-303 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 23.0000 | 100.0000 | 168.001.001.002.007.001.003.011.001. | 100.0000 | Material | 0 | 0.0000
503550 | B-303 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 1361 | HCL Acid | Ltrs | 0.3450 | 6.0000 | 168.001.001.002.007.001.003.011.001. | 6.0000 | Material | 0 | 0.0000
503550 | B-303 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 24440 | M Sand | Cu.Ft | 3.1290 | 65.0000 | 168.001.001.002.007.001.003.011.001. | 65.0000 | Material | 0 | 0.0000
503550 | B-303 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 5989 | Tape Roll | No. | 0.3450 | 1327.5000 | 168.001.001.002.007.001.003.011.001. | 1327.5000 | Material | 0 | 0.0000
503550 | B-303 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 26445 | Tile Grout | Kgs | 0.2300 | 100.0000 | 168.001.001.002.007.001.003.011.001. | 100.0000 | Material | 0 | 0.0000
503551 | B-303 Internal Flat Flooring | Sq.Ft | 257.5200 | 257.5200 | 89 | Cement 43 Grade | Bags | 5.1504 | 375.0000 | 168.001.001.002.007.001.003.011.002. | 375.0000 | Material | 0 | 0.0000
503551 | B-303 Internal Flat Flooring | Sq.Ft | 257.5200 | 257.5200 | 161 | Crush Sand | Cu.Ft | 20.6016 | 33.0000 | 168.001.001.002.007.001.003.011.002. | 33.0000 | Material | 0 | 0.0000
503551 | B-303 Internal Flat Flooring | Sq.Ft | 257.5200 | 257.5200 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 257.5200 | 100.0000 | 168.001.001.002.007.001.003.011.002. | 100.0000 | Material | 0 | 0.0000
503551 | B-303 Internal Flat Flooring | Sq.Ft | 257.5200 | 257.5200 | 1361 | HCL Acid | Ltrs | 3.8628 | 6.0000 | 168.001.001.002.007.001.003.011.002. | 6.0000 | Material | 0 | 0.0000
503551 | B-303 Internal Flat Flooring | Sq.Ft | 257.5200 | 257.5200 | 24440 | M Sand | Cu.Ft | 20.6016 | 65.0000 | 168.001.001.002.007.001.003.011.002. | 65.0000 | Material | 0 | 0.0000
503551 | B-303 Internal Flat Flooring | Sq.Ft | 257.5200 | 257.5200 | 5989 | Tape Roll | No. | 3.8628 | 1327.5000 | 168.001.001.002.007.001.003.011.002. | 1327.5000 | Material | 0 | 0.0000
503551 | B-303 Internal Flat Flooring | Sq.Ft | 257.5200 | 257.5200 | 26445 | Tile Grout | Kgs | 2.5752 | 100.0000 | 168.001.001.002.007.001.003.011.002. | 100.0000 | Material | 0 | 0.0000
503551 | B-303 Internal Flat Flooring | Sq.Ft | 257.5200 | 257.5200 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.3600 | 100.0000 | 168.001.001.002.007.001.003.011.002. | 100.0000 | Material | 0 | 0.0000
503552 | B-303 WC Flooring Work | Sq.Ft | 13.7900 | 13.7900 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 13.7900 | 100.0000 | 168.001.001.002.007.001.003.011.003. | 100.0000 | Material | 0 | 0.0000
503552 | B-303 WC Flooring Work | Sq.Ft | 13.7900 | 13.7900 | 89 | Cement 43 Grade | Bags | 0.2758 | 375.0000 | 168.001.001.002.007.001.003.011.003. | 375.0000 | Material | 0 | 0.0000
503552 | B-303 WC Flooring Work | Sq.Ft | 13.7900 | 13.7900 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.003.011.003. | 33.0000 | Material | 0 | 0.0000
503552 | B-303 WC Flooring Work | Sq.Ft | 13.7900 | 13.7900 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 13.7900 | 100.0000 | 168.001.001.002.007.001.003.011.003. | 100.0000 | Material | 0 | 0.0000
503552 | B-303 WC Flooring Work | Sq.Ft | 13.7900 | 13.7900 | 1361 | HCL Acid | Ltrs | 0.2069 | 6.0000 | 168.001.001.002.007.001.003.011.003. | 6.0000 | Material | 0 | 0.0000
503552 | B-303 WC Flooring Work | Sq.Ft | 13.7900 | 13.7900 | 24440 | M Sand | Cu.Ft | 1.1032 | 65.0000 | 168.001.001.002.007.001.003.011.003. | 65.0000 | Material | 0 | 0.0000
503552 | B-303 WC Flooring Work | Sq.Ft | 13.7900 | 13.7900 | 5989 | Tape Roll | No. | 0.2069 | 1327.5000 | 168.001.001.002.007.001.003.011.003. | 1327.5000 | Material | 0 | 0.0000
503552 | B-303 WC Flooring Work | Sq.Ft | 13.7900 | 13.7900 | 26445 | Tile Grout | Kgs | 0.1379 | 100.0000 | 168.001.001.002.007.001.003.011.003. | 100.0000 | Material | 0 | 0.0000
503554 | B-304 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 23.0000 | 100.0000 | 168.001.001.002.007.001.003.012.001. | 100.0000 | Material | 0 | 0.0000
503554 | B-304 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 89 | Cement 43 Grade | Bags | 0.7800 | 375.0000 | 168.001.001.002.007.001.003.012.001. | 375.0000 | Material | 0 | 0.0000
503554 | B-304 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 161 | Crush Sand | Cu.Ft | 3.1290 | 33.0000 | 168.001.001.002.007.001.003.012.001. | 33.0000 | Material | 0 | 0.0000
503554 | B-304 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 23.0000 | 100.0000 | 168.001.001.002.007.001.003.012.001. | 100.0000 | Material | 0 | 0.0000
503554 | B-304 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 1361 | HCL Acid | Ltrs | 0.3450 | 6.0000 | 168.001.001.002.007.001.003.012.001. | 6.0000 | Material | 0 | 0.0000
503554 | B-304 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 24440 | M Sand | Cu.Ft | 3.1290 | 65.0000 | 168.001.001.002.007.001.003.012.001. | 65.0000 | Material | 0 | 0.0000
503554 | B-304 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 5989 | Tape Roll | No. | 0.3450 | 1327.5000 | 168.001.001.002.007.001.003.012.001. | 1327.5000 | Material | 0 | 0.0000
503554 | B-304 Bath Flooring Work | Sq.Ft | 23.0000 | 23.0000 | 26445 | Tile Grout | Kgs | 0.2300 | 100.0000 | 168.001.001.002.007.001.003.012.001. | 100.0000 | Material | 0 | 0.0000
503555 | B-304 Internal Flat Flooring | Sq.Ft | 253.9000 | 253.9000 | 89 | Cement 43 Grade | Bags | 5.0780 | 375.0000 | 168.001.001.002.007.001.003.012.002. | 375.0000 | Material | 0 | 0.0000
503555 | B-304 Internal Flat Flooring | Sq.Ft | 253.9000 | 253.9000 | 161 | Crush Sand | Cu.Ft | 20.3120 | 33.0000 | 168.001.001.002.007.001.003.012.002. | 33.0000 | Material | 0 | 0.0000
503555 | B-304 Internal Flat Flooring | Sq.Ft | 253.9000 | 253.9000 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 253.9000 | 100.0000 | 168.001.001.002.007.001.003.012.002. | 100.0000 | Material | 0 | 0.0000
503555 | B-304 Internal Flat Flooring | Sq.Ft | 253.9000 | 253.9000 | 1361 | HCL Acid | Ltrs | 3.8085 | 6.0000 | 168.001.001.002.007.001.003.012.002. | 6.0000 | Material | 0 | 0.0000
503555 | B-304 Internal Flat Flooring | Sq.Ft | 253.9000 | 253.9000 | 24440 | M Sand | Cu.Ft | 20.3120 | 65.0000 | 168.001.001.002.007.001.003.012.002. | 65.0000 | Material | 0 | 0.0000
503555 | B-304 Internal Flat Flooring | Sq.Ft | 253.9000 | 253.9000 | 5989 | Tape Roll | No. | 3.8085 | 1327.5000 | 168.001.001.002.007.001.003.012.002. | 1327.5000 | Material | 0 | 0.0000
503555 | B-304 Internal Flat Flooring | Sq.Ft | 253.9000 | 253.9000 | 26445 | Tile Grout | Kgs | 2.5390 | 100.0000 | 168.001.001.002.007.001.003.012.002. | 100.0000 | Material | 0 | 0.0000
503555 | B-304 Internal Flat Flooring | Sq.Ft | 253.9000 | 253.9000 | 27368 | Vitrified Flooring Tile 600 X 600 DC Tropicana flooring | Sq.Ft | 295.3600 | 100.0000 | 168.001.001.002.007.001.003.012.002. | 100.0000 | Material | 0 | 0.0000
503556 | B-304 WC Flooring Work | Sq.Ft | 13.8100 | 13.8100 | 27369 | Anti-skid Tile 300 X 300 (Grey color). ASMI FLA1 | Sq.Ft | 13.8100 | 100.0000 | 168.001.001.002.007.001.003.012.003. | 100.0000 | Material | 0 | 0.0000
503556 | B-304 WC Flooring Work | Sq.Ft | 13.8100 | 13.8100 | 89 | Cement 43 Grade | Bags | 0.2762 | 375.0000 | 168.001.001.002.007.001.003.012.003. | 375.0000 | Material | 0 | 0.0000
503556 | B-304 WC Flooring Work | Sq.Ft | 13.8100 | 13.8100 | 161 | Crush Sand | Cu.Ft | 11.9990 | 33.0000 | 168.001.001.002.007.001.003.012.003. | 33.0000 | Material | 0 | 0.0000
503556 | B-304 WC Flooring Work | Sq.Ft | 13.8100 | 13.8100 | 6314 | Floor Guard Sheet (4ft x 6ft) | Sq.Ft | 13.8100 | 100.0000 | 168.001.001.002.007.001.003.012.003. | 100.0000 | Material | 0 | 0.0000
503556 | B-304 WC Flooring Work | Sq.Ft | 13.8100 | 13.8100 | 1361 | HCL Acid | Ltrs | 0.2072 | 6.0000 | 168.001.001.002.007.001.003.012.003. | 6.0000 | Material | 0 | 0.0000
503556 | B-304 WC Flooring Work | Sq.Ft | 13.8100 | 13.8100 | 24440 | M Sand | Cu.Ft | 1.1048 | 65.0000 | 168.001.001.002.007.001.003.012.003. | 65.0000 | Material | 0 | 0.0000
503556 | B-304 WC Flooring Work | Sq.Ft | 13.8100 | 13.8100 | 5989 | Tape Roll | No. | 0.2072 | 1327.5000 | 168.001.001.002.007.001.003.012.003. | 1327.5000 | Material | 0 | 0.0000
503556 | B-304 WC Flooring Work | Sq.Ft | 13.8100 | 13.8100 | 26445 | Tile Grout | Kgs | 0.1381 | 100.0000 | 168.001.001.002.007.001.003.012.003. | 100.0000 | Material | 0 | 0.0000