## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- G- Waterproofing (M) | Selected Group :- G- Waterproofing (M) | Selected Group :- G- Waterproofing (M) | Selected Group :- G- Waterproofing (M) | Selected Group :- G- Waterproofing (M) | Selected Group :- G- Waterproofing (M) | Selected Group :- G- Waterproofing (M) | Selected Group :- G- Waterproofing (M) | Selected Group :- G- Waterproofing (M) | Selected Group :- G- Waterproofing (M) | Selected Group :- G- Waterproofing (M) | Selected Group :- G- Waterproofing (M) | Selected Group :- G- Waterproofing (M) | Selected Group :- G- Waterproofing (M) | Selected Group :- G- Waterproofing (M) | Selected Group :- G- Waterproofing (M) | Selected Group :- G- Waterproofing (M)
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 555866 | G- Waterproofing (M) | NA | 0.0000 | 0.0000 | 0 | 548302 | 31 | 0 | [6 empty] | 0.0000
2 | 555867 | G- 1st Floor | NA | 0.0000 | 0.0000 | 1 | 555866 | 31 | 0 | [6 empty] | 0.0000
3 | 555868 | G- Flat No 101 | NA | 0.0000 | 0.0000 | 2 | 555867 | 31 | 0 | [6 empty] | 0.0000
4 | 555869 | G- 101 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 3 | 555868 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
5 | 555870 | G- 101 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 3 | 555868 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
6 | 555871 | G- 101 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 3 | 555868 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
7 | 555872 | G- Flat No 102 | NA | 0.0000 | 0.0000 | 2 | 555867 | 31 | 0 | [6 empty] | 0.0000
8 | 555873 | G. 102 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 7 | 555872 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
9 | 555874 | G. 102 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 7 | 555872 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
10 | 555875 | G. 102 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 7 | 555872 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
11 | 555876 | G- Flat No 103 | NA | 0.0000 | 0.0000 | 2 | 555867 | 31 | 0 | [6 empty] | 0.0000
12 | 555877 | G. 103 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 11 | 555876 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
13 | 555878 | G. 103 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 11 | 555876 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
14 | 555879 | G. 103 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 11 | 555876 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
15 | 555880 | G- Flat No 104 | NA | 0.0000 | 0.0000 | 2 | 555867 | 31 | 0 | [6 empty] | 0.0000
16 | 555881 | G. 104 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 15 | 555880 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
17 | 555882 | G. 104 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 15 | 555880 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
18 | 555883 | G. 104 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 15 | 555880 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
19 | 555884 | G- Flat No 105 | NA | 0.0000 | 0.0000 | 2 | 555867 | 31 | 0 | [6 empty] | 0.0000
20 | 555885 | G. 105 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 19 | 555884 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
21 | 555886 | G. 105 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 19 | 555884 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
22 | 555887 | G. 105 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 19 | 555884 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
23 | 555888 | G- Flat No 106 | NA | 0.0000 | 0.0000 | 2 | 555867 | 31 | 0 | [6 empty] | 0.0000
24 | 555889 | G. 106 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 23 | 555888 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
25 | 555890 | G. 106 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 23 | 555888 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
26 | 555891 | G. 106 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 23 | 555888 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
27 | 555892 | G- Flat No 107 | NA | 0.0000 | 0.0000 | 2 | 555867 | 31 | 0 | [6 empty] | 0.0000
28 | 555893 | G. 107 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 27 | 555892 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
29 | 555894 | G. 107 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 27 | 555892 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
30 | 555895 | G. 107 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 27 | 555892 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
31 | 555896 | G- Flat No 108 | NA | 0.0000 | 0.0000 | 2 | 555867 | 31 | 0 | [6 empty] | 0.0000
32 | 555897 | G. 108 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 31 | 555896 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
33 | 555898 | G. 108 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 31 | 555896 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
34 | 555899 | G. 108 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 31 | 555896 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
35 | 555900 | G- Flat No 109 | NA | 0.0000 | 0.0000 | 2 | 555867 | 31 | 0 | [6 empty] | 0.0000
36 | 555901 | G. 109 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 35 | 555900 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
37 | 555902 | G. 109 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 35 | 555900 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
38 | 555903 | G. 109 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 35 | 555900 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
39 | 555904 | G- Flat No 110 | NA | 0.0000 | 0.0000 | 2 | 555867 | 31 | 0 | [6 empty] | 0.0000
40 | 555905 | G. 110 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 39 | 555904 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
41 | 555906 | G. 110 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 39 | 555904 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
42 | 555907 | G. 110 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 39 | 555904 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
43 | 555908 | G- Flat No 111 | NA | 0.0000 | 0.0000 | 2 | 555867 | 31 | 0 | [6 empty] | 0.0000
44 | 555909 | G. 111 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 43 | 555908 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
45 | 555910 | G. 111 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 43 | 555908 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
46 | 555911 | G. 111 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 43 | 555908 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
47 | 555912 | G- Flat No 112 | NA | 0.0000 | 0.0000 | 2 | 555867 | 31 | 0 | [6 empty] | 0.0000
48 | 555913 | G. 112 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 47 | 555912 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
49 | 555914 | G. 112 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 47 | 555912 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
50 | 555915 | G. 112 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 47 | 555912 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
51 | 555916 | G- Flat No 113 | NA | 0.0000 | 0.0000 | 2 | 555867 | 31 | 0 | [6 empty] | 0.0000
52 | 555917 | G. 113 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 51 | 555916 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
53 | 555918 | G. 113 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 51 | 555916 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
54 | 555919 | G. 113 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 51 | 555916 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
55 | 555920 | G- Flat No 114 | NA | 0.0000 | 0.0000 | 2 | 555867 | 31 | 0 | [6 empty] | 0.0000
56 | 555921 | G. 114 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 55 | 555920 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
57 | 555922 | G. 114 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 55 | 555920 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
58 | 555923 | G. 114 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 55 | 555920 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
59 | 555927 | G- 2nd Floor | NA | 0.0000 | 0.0000 | 1 | 555866 | 31 | 0 | [6 empty] | 0.0000
60 | 555928 | G- Flat No 201 | NA | 0.0000 | 0.0000 | 59 | 555927 | 31 | 0 | [6 empty] | 0.0000
61 | 555929 | G. 201 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 60 | 555928 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
62 | 555930 | G. 201 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 60 | 555928 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
63 | 555931 | G. 201 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 60 | 555928 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
64 | 555932 | G- Flat No 202 | NA | 0.0000 | 0.0000 | 59 | 555927 | 31 | 0 | [6 empty] | 0.0000
65 | 555933 | G. 202 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 64 | 555932 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
66 | 555934 | G. 202 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 64 | 555932 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
67 | 555935 | G. 202 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 64 | 555932 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
68 | 555936 | G- Flat No 203 | NA | 0.0000 | 0.0000 | 59 | 555927 | 31 | 0 | [6 empty] | 0.0000
69 | 555937 | G. 203 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 68 | 555936 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
70 | 555938 | G. 203 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 68 | 555936 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
71 | 555939 | G. 203 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 68 | 555936 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
72 | 555940 | G- Flat No 204 | NA | 0.0000 | 0.0000 | 59 | 555927 | 31 | 0 | [6 empty] | 0.0000
73 | 555941 | G. 204 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 72 | 555940 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
74 | 555942 | G. 204 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 72 | 555940 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
75 | 555943 | G. 204 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 72 | 555940 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
76 | 555944 | G- Flat No 205 | NA | 0.0000 | 0.0000 | 59 | 555927 | 31 | 0 | [6 empty] | 0.0000
77 | 555945 | G. 205 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 76 | 555944 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
78 | 555946 | G. 205 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 76 | 555944 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
79 | 555947 | G. 205 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 76 | 555944 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
80 | 555948 | G- Flat No 206 | NA | 0.0000 | 0.0000 | 59 | 555927 | 31 | 0 | [6 empty] | 0.0000
81 | 555949 | G. 206 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 80 | 555948 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
82 | 555950 | G. 206 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 80 | 555948 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
83 | 555951 | G. 206 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 80 | 555948 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
84 | 555952 | G- Flat No 207 | NA | 0.0000 | 0.0000 | 59 | 555927 | 31 | 0 | [6 empty] | 0.0000
85 | 555953 | G. 207 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 84 | 555952 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
86 | 555954 | G. 207 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 84 | 555952 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
87 | 555955 | G. 207 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 84 | 555952 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
88 | 555956 | G- Flat No 208 | NA | 0.0000 | 0.0000 | 59 | 555927 | 31 | 0 | [6 empty] | 0.0000
89 | 555957 | G. 208 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 88 | 555956 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
90 | 555958 | G. 208 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 88 | 555956 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
91 | 555959 | G. 208 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 88 | 555956 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
92 | 555960 | G- Flat No 209 | NA | 0.0000 | 0.0000 | 59 | 555927 | 31 | 0 | [6 empty] | 0.0000
93 | 555961 | G. 209 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 92 | 555960 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
94 | 555962 | G. 209 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 92 | 555960 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
95 | 555963 | G. 209 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 92 | 555960 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
96 | 555964 | G- Flat No 210 | NA | 0.0000 | 0.0000 | 59 | 555927 | 31 | 0 | [6 empty] | 0.0000
97 | 555965 | G. 210 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 96 | 555964 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
98 | 555966 | G. 210 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 96 | 555964 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
99 | 555967 | G. 210 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 96 | 555964 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
100 | 555968 | G- Flat No 211 | NA | 0.0000 | 0.0000 | 59 | 555927 | 31 | 0 | [6 empty] | 0.0000
101 | 555969 | G. 211 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 100 | 555968 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
102 | 555970 | G. 211 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 100 | 555968 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
103 | 555971 | G. 211 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 100 | 555968 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
104 | 555972 | G- Flat No 212 | NA | 0.0000 | 0.0000 | 59 | 555927 | 31 | 0 | [6 empty] | 0.0000
105 | 555973 | G. 212 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 104 | 555972 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
106 | 555974 | G. 212 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 104 | 555972 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
107 | 555975 | G. 212 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 104 | 555972 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
108 | 555976 | G- Flat No 213 | NA | 0.0000 | 0.0000 | 59 | 555927 | 31 | 0 | [6 empty] | 0.0000
109 | 555977 | G. 213 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 555976 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
110 | 555978 | G. 213 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 555976 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
111 | 555979 | G. 213 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 555976 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
112 | 555980 | G- Flat No 214 | NA | 0.0000 | 0.0000 | 59 | 555927 | 31 | 0 | [6 empty] | 0.0000
113 | 555981 | G. 214 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 112 | 555980 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
114 | 555982 | G. 214 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 112 | 555980 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
115 | 555983 | G. 214 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 112 | 555980 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
116 | 555984 | G- 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 555866 | 31 | 0 | [6 empty] | 0.0000
117 | 555985 | G- Flat No 301 | NA | 0.0000 | 0.0000 | 116 | 555984 | 31 | 0 | [6 empty] | 0.0000
118 | 555986 | G. 301 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 117 | 555985 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
119 | 555987 | G. 301 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 117 | 555985 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
120 | 555988 | G. 301 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 117 | 555985 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
121 | 555989 | G- Flat No 302 | NA | 0.0000 | 0.0000 | 116 | 555984 | 31 | 0 | [6 empty] | 0.0000
122 | 555990 | G. 302 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 121 | 555989 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
123 | 555991 | G. 302 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 121 | 555989 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
124 | 555992 | G. 302 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 121 | 555989 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
125 | 555993 | G- Flat No 303 | NA | 0.0000 | 0.0000 | 116 | 555984 | 31 | 0 | [6 empty] | 0.0000
126 | 555994 | G. 303 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 125 | 555993 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
127 | 555995 | G. 303 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 125 | 555993 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
128 | 555996 | G. 303 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 125 | 555993 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
129 | 555997 | G- Flat No 304 | NA | 0.0000 | 0.0000 | 116 | 555984 | 31 | 0 | [6 empty] | 0.0000
130 | 555998 | G. 304 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 129 | 555997 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
131 | 555999 | G. 304 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 129 | 555997 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
132 | 556000 | G. 304 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 129 | 555997 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
133 | 556001 | G- Flat No 305 | NA | 0.0000 | 0.0000 | 116 | 555984 | 31 | 0 | [6 empty] | 0.0000
134 | 556002 | G. 305 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 133 | 556001 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
135 | 556003 | G. 305 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 133 | 556001 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
136 | 556004 | G. 305 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 133 | 556001 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
137 | 556005 | G- Flat No 306 | NA | 0.0000 | 0.0000 | 116 | 555984 | 31 | 0 | [6 empty] | 0.0000
138 | 556006 | G. 306 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 137 | 556005 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
139 | 556007 | G. 306 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 137 | 556005 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
140 | 556008 | G. 306 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 137 | 556005 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
141 | 556009 | G- Flat No 307 | NA | 0.0000 | 0.0000 | 116 | 555984 | 31 | 0 | [6 empty] | 0.0000
142 | 556010 | G. 307 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 141 | 556009 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
143 | 556011 | G. 307 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 141 | 556009 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
144 | 556012 | G. 307 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 141 | 556009 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
145 | 556013 | G- Flat No 308 | NA | 0.0000 | 0.0000 | 116 | 555984 | 31 | 0 | [6 empty] | 0.0000
146 | 556014 | G. 308 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 145 | 556013 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
147 | 556015 | G. 308 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 145 | 556013 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
148 | 556016 | G. 308 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 145 | 556013 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
149 | 556017 | G- Flat No 309 | NA | 0.0000 | 0.0000 | 116 | 555984 | 31 | 0 | [6 empty] | 0.0000
150 | 556018 | G. 309 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 149 | 556017 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
151 | 556019 | G. 309 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 149 | 556017 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
152 | 556020 | G. 309 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 149 | 556017 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
153 | 556021 | G- Flat No 310 | NA | 0.0000 | 0.0000 | 116 | 555984 | 31 | 0 | [6 empty] | 0.0000
154 | 556022 | G. 310 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 153 | 556021 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
155 | 556023 | G. 310 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 153 | 556021 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
156 | 556024 | G. 310 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 153 | 556021 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
157 | 556025 | G- Flat No 311 | NA | 0.0000 | 0.0000 | 116 | 555984 | 31 | 0 | [6 empty] | 0.0000
158 | 556026 | G. 311 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 157 | 556025 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
159 | 556027 | G. 311 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 157 | 556025 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
160 | 556028 | G. 311 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 157 | 556025 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
161 | 556029 | G- Flat No 312 | NA | 0.0000 | 0.0000 | 116 | 555984 | 31 | 0 | [6 empty] | 0.0000
162 | 556030 | G. 312 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 161 | 556029 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
163 | 556031 | G. 312 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 161 | 556029 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
164 | 556032 | G. 312 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 161 | 556029 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
165 | 556033 | G- Flat No 313 | NA | 0.0000 | 0.0000 | 116 | 555984 | 31 | 0 | [6 empty] | 0.0000
166 | 556034 | G. 313 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 165 | 556033 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
167 | 556035 | G. 313 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 165 | 556033 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
168 | 556036 | G. 313 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 165 | 556033 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
169 | 556037 | G- Flat No 314 | NA | 0.0000 | 0.0000 | 116 | 555984 | 31 | 0 | [6 empty] | 0.0000
170 | 556038 | G. 314 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 169 | 556037 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
171 | 556039 | G. 314 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 169 | 556037 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
172 | 556040 | G. 314 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 169 | 556037 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
173 | 556041 | G- 4th Floor | NA | 0.0000 | 0.0000 | 1 | 555866 | 31 | 0 | [6 empty] | 0.0000
174 | 556042 | G- Flat No 401 | NA | 0.0000 | 0.0000 | 173 | 556041 | 31 | 0 | [6 empty] | 0.0000
175 | 556043 | G. 401 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 174 | 556042 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
176 | 556044 | G. 401 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 174 | 556042 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
177 | 556045 | G. 401 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 174 | 556042 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
178 | 556046 | G- Flat No 402 | NA | 0.0000 | 0.0000 | 173 | 556041 | 31 | 0 | [6 empty] | 0.0000
179 | 556047 | G. 402 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 178 | 556046 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
180 | 556048 | G. 402 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 178 | 556046 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
181 | 556049 | G. 402 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 178 | 556046 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
182 | 556050 | G- Flat No 403 | NA | 0.0000 | 0.0000 | 173 | 556041 | 31 | 0 | [6 empty] | 0.0000
183 | 556051 | G. 403 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 182 | 556050 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
184 | 556052 | G. 403 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 182 | 556050 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
185 | 556053 | G. 403 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 182 | 556050 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
186 | 556054 | G- Flat No 404 | NA | 0.0000 | 0.0000 | 173 | 556041 | 31 | 0 | [6 empty] | 0.0000
187 | 556055 | G. 404 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 186 | 556054 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
188 | 556056 | G. 404 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 186 | 556054 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
189 | 556057 | G. 404 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 186 | 556054 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
190 | 556058 | G- Flat No 405 | NA | 0.0000 | 0.0000 | 173 | 556041 | 31 | 0 | [6 empty] | 0.0000
191 | 556059 | G. 405 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 190 | 556058 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
192 | 556060 | G. 405 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 190 | 556058 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
193 | 556061 | G. 405 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 190 | 556058 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
194 | 556062 | G- Flat No 406 | NA | 0.0000 | 0.0000 | 173 | 556041 | 31 | 0 | [6 empty] | 0.0000
195 | 556063 | G. 406 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 194 | 556062 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
196 | 556064 | G. 406 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 194 | 556062 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
197 | 556065 | G. 406 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 194 | 556062 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
198 | 556066 | G- Flat No 407 | NA | 0.0000 | 0.0000 | 173 | 556041 | 31 | 0 | [6 empty] | 0.0000
199 | 556067 | G. 407 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 198 | 556066 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
200 | 556068 | G. 407 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 198 | 556066 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
201 | 556069 | G. 407 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 198 | 556066 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
202 | 556070 | G- Flat No 408 | NA | 0.0000 | 0.0000 | 173 | 556041 | 31 | 0 | [6 empty] | 0.0000
203 | 556071 | G. 408 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 202 | 556070 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
204 | 556072 | G. 408 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 202 | 556070 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
205 | 556073 | G. 408 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 202 | 556070 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
206 | 556074 | G- Flat No 409 | NA | 0.0000 | 0.0000 | 173 | 556041 | 31 | 0 | [6 empty] | 0.0000
207 | 556075 | G. 409 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 206 | 556074 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
208 | 556076 | G. 409 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 206 | 556074 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
209 | 556077 | G. 409 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 206 | 556074 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
210 | 556078 | G- Flat No 410 | NA | 0.0000 | 0.0000 | 173 | 556041 | 31 | 0 | [6 empty] | 0.0000
211 | 556079 | G. 410 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 210 | 556078 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
212 | 556080 | G. 410 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 210 | 556078 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
213 | 556081 | G. 410 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 210 | 556078 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
214 | 556082 | G- Flat No 411 | NA | 0.0000 | 0.0000 | 173 | 556041 | 31 | 0 | [6 empty] | 0.0000
215 | 556083 | G. 411 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 214 | 556082 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
216 | 556084 | G. 411 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 214 | 556082 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
217 | 556085 | G. 411 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 214 | 556082 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
218 | 556086 | G- Flat No 412 | NA | 0.0000 | 0.0000 | 173 | 556041 | 31 | 0 | [6 empty] | 0.0000
219 | 556087 | G. 412 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 218 | 556086 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
220 | 556088 | G. 412 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 218 | 556086 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
221 | 556089 | G. 412 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 218 | 556086 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
222 | 556090 | G- Flat No 413 | NA | 0.0000 | 0.0000 | 173 | 556041 | 31 | 0 | [6 empty] | 0.0000
223 | 556091 | G. 413 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 222 | 556090 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
224 | 556092 | G. 413 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 222 | 556090 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
225 | 556093 | G. 413 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 222 | 556090 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
226 | 556094 | G- Flat No 414 | NA | 0.0000 | 0.0000 | 173 | 556041 | 31 | 0 | [6 empty] | 0.0000
227 | 556095 | G. 414 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 226 | 556094 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
228 | 556096 | G. 414 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 226 | 556094 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
229 | 556097 | G. 414 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 226 | 556094 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
230 | 558794 | G- 5th Floor | NA | 0.0000 | 0.0000 | 1 | 555866 | 31 | 0 | [6 empty] | 0.0000
231 | 558795 | G- Flat No 501 | NA | 0.0000 | 0.0000 | 230 | 558794 | 31 | 0 | [6 empty] | 0.0000
232 | 558796 | G. 501 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 231 | 558795 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
233 | 558797 | G. 501 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 231 | 558795 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
234 | 558798 | G. 501 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 231 | 558795 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
235 | 558799 | G- Flat No 502 | NA | 0.0000 | 0.0000 | 230 | 558794 | 31 | 0 | [6 empty] | 0.0000
236 | 558800 | G. 502 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 235 | 558799 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
237 | 558801 | G. 502 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 235 | 558799 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
238 | 558802 | G. 502 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 235 | 558799 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
239 | 558803 | G- Flat No 503 | NA | 0.0000 | 0.0000 | 230 | 558794 | 31 | 0 | [6 empty] | 0.0000
240 | 558804 | G. 503 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 239 | 558803 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
241 | 558805 | G. 503 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 239 | 558803 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
242 | 558806 | G. 503 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 239 | 558803 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
243 | 558807 | G- Flat No 504 | NA | 0.0000 | 0.0000 | 230 | 558794 | 31 | 0 | [6 empty] | 0.0000
244 | 558808 | G. 504 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 243 | 558807 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
245 | 558809 | G. 504 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 243 | 558807 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
246 | 558810 | G. 504 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 243 | 558807 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
247 | 558811 | G- Flat No 505 | NA | 0.0000 | 0.0000 | 230 | 558794 | 31 | 0 | [6 empty] | 0.0000
248 | 558812 | G. 505 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 247 | 558811 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
249 | 558813 | G. 505 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 247 | 558811 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
250 | 558814 | G. 505 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 247 | 558811 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
251 | 558815 | G- Flat No 506 | NA | 0.0000 | 0.0000 | 230 | 558794 | 31 | 0 | [6 empty] | 0.0000
252 | 558816 | G. 506 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 251 | 558815 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
253 | 558817 | G. 506 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 251 | 558815 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
254 | 558818 | G. 506 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 251 | 558815 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
255 | 558819 | G- Flat No 507 | NA | 0.0000 | 0.0000 | 230 | 558794 | 31 | 0 | [6 empty] | 0.0000
256 | 558820 | G. 507 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 255 | 558819 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
257 | 558821 | G. 507 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 255 | 558819 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
258 | 558822 | G. 507 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 255 | 558819 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
259 | 558823 | G- Flat No 508 | NA | 0.0000 | 0.0000 | 230 | 558794 | 31 | 0 | [6 empty] | 0.0000
260 | 558824 | G. 508 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 259 | 558823 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
261 | 558825 | G. 508 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 259 | 558823 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
262 | 558826 | G. 508 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 259 | 558823 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
263 | 558827 | G- Flat No 509 | NA | 0.0000 | 0.0000 | 230 | 558794 | 31 | 0 | [6 empty] | 0.0000
264 | 558828 | G. 509 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 263 | 558827 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
265 | 558829 | G. 509 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 263 | 558827 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
266 | 558830 | G. 509 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 263 | 558827 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
267 | 558831 | G- Flat No 510 | NA | 0.0000 | 0.0000 | 230 | 558794 | 31 | 0 | [6 empty] | 0.0000
268 | 558832 | G. 510 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 267 | 558831 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
269 | 558833 | G. 510 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 267 | 558831 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
270 | 558834 | G. 510 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 267 | 558831 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
271 | 558835 | G- Flat No 511 | NA | 0.0000 | 0.0000 | 230 | 558794 | 31 | 0 | [6 empty] | 0.0000
272 | 558836 | G. 511 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 271 | 558835 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
273 | 558837 | G. 511 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 271 | 558835 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
274 | 558838 | G. 511 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 271 | 558835 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
275 | 558839 | G- Flat No 512 | NA | 0.0000 | 0.0000 | 230 | 558794 | 31 | 0 | [6 empty] | 0.0000
276 | 558840 | G. 512 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 275 | 558839 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
277 | 558841 | G. 512 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 275 | 558839 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
278 | 558842 | G. 512 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 275 | 558839 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
279 | 558843 | G- Flat No 513 | NA | 0.0000 | 0.0000 | 230 | 558794 | 31 | 0 | [6 empty] | 0.0000
280 | 558844 | G. 513 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 279 | 558843 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
281 | 558845 | G. 513 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 279 | 558843 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
282 | 558846 | G. 513 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 279 | 558843 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
283 | 558847 | G- Flat No 514 | NA | 0.0000 | 0.0000 | 230 | 558794 | 31 | 0 | [6 empty] | 0.0000
284 | 558848 | G. 514 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 283 | 558847 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
285 | 558849 | G. 514 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 283 | 558847 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
286 | 558850 | G. 514 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 283 | 558847 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
287 | 558851 | G- 6th Floor | NA | 0.0000 | 0.0000 | 1 | 555866 | 31 | 0 | [6 empty] | 0.0000
288 | 558852 | G- Flat No 601 | NA | 0.0000 | 0.0000 | 287 | 558851 | 31 | 0 | [6 empty] | 0.0000
289 | 558853 | G. 601 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 288 | 558852 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
290 | 558854 | G. 601 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 288 | 558852 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
291 | 558855 | G. 601 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 288 | 558852 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
292 | 558856 | G- Flat No 602 | NA | 0.0000 | 0.0000 | 287 | 558851 | 31 | 0 | [6 empty] | 0.0000
293 | 558857 | G. 602 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 292 | 558856 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
294 | 558858 | G. 602 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 292 | 558856 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
295 | 558859 | G. 602 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 292 | 558856 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
296 | 558860 | G- Flat No 603 | NA | 0.0000 | 0.0000 | 287 | 558851 | 31 | 0 | [6 empty] | 0.0000
297 | 558861 | G. 603 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 296 | 558860 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
298 | 558862 | G. 603 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 296 | 558860 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
299 | 558863 | G. 603 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 296 | 558860 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
300 | 558864 | G- Flat No 604 | NA | 0.0000 | 0.0000 | 287 | 558851 | 31 | 0 | [6 empty] | 0.0000
301 | 558865 | G. 604 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 300 | 558864 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
302 | 558866 | G. 604 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 300 | 558864 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
303 | 558867 | G. 604 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 300 | 558864 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
304 | 558868 | G- Flat No 605 | NA | 0.0000 | 0.0000 | 287 | 558851 | 31 | 0 | [6 empty] | 0.0000
305 | 558869 | G. 605 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 304 | 558868 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
306 | 558870 | G. 605 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 304 | 558868 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
307 | 558871 | G. 605 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 304 | 558868 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
308 | 558872 | G- Flat No 606 | NA | 0.0000 | 0.0000 | 287 | 558851 | 31 | 0 | [6 empty] | 0.0000
309 | 558873 | G. 606 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 308 | 558872 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
310 | 558874 | G. 606 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 308 | 558872 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
311 | 558875 | G. 606 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 308 | 558872 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
312 | 558876 | G- Flat No 607 | NA | 0.0000 | 0.0000 | 287 | 558851 | 31 | 0 | [6 empty] | 0.0000
313 | 558877 | G. 607 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 312 | 558876 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
314 | 558878 | G. 607 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 312 | 558876 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
315 | 558879 | G. 607 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 312 | 558876 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
316 | 558880 | G- Flat No 608 | NA | 0.0000 | 0.0000 | 287 | 558851 | 31 | 0 | [6 empty] | 0.0000
317 | 558881 | G. 608 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 316 | 558880 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
318 | 558882 | G. 608 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 316 | 558880 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
319 | 558883 | G. 608 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 316 | 558880 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
320 | 558884 | G- Flat No 609 | NA | 0.0000 | 0.0000 | 287 | 558851 | 31 | 0 | [6 empty] | 0.0000
321 | 558885 | G. 609 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 320 | 558884 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
322 | 558886 | G. 609 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 320 | 558884 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
323 | 558887 | G. 609 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 320 | 558884 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
324 | 558888 | G- Flat No 610 | NA | 0.0000 | 0.0000 | 287 | 558851 | 31 | 0 | [6 empty] | 0.0000
325 | 558889 | G. 610 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 324 | 558888 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
326 | 558890 | G. 610 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 324 | 558888 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
327 | 558891 | G. 610 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 324 | 558888 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
328 | 558892 | G- Flat No 611 | NA | 0.0000 | 0.0000 | 287 | 558851 | 31 | 0 | [6 empty] | 0.0000
329 | 558893 | G. 611 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 328 | 558892 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
330 | 558894 | G. 611 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 328 | 558892 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
331 | 558895 | G. 611 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 328 | 558892 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
332 | 558896 | G- Flat No 612 | NA | 0.0000 | 0.0000 | 287 | 558851 | 31 | 0 | [6 empty] | 0.0000
333 | 558897 | G. 612 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 332 | 558896 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
334 | 558898 | G. 612 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 332 | 558896 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
335 | 558899 | G. 612 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 332 | 558896 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
336 | 558900 | G- Flat No 613 | NA | 0.0000 | 0.0000 | 287 | 558851 | 31 | 0 | [6 empty] | 0.0000
337 | 558901 | G. 613 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 336 | 558900 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
338 | 558902 | G. 613 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 336 | 558900 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
339 | 558903 | G. 613 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 336 | 558900 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
340 | 558904 | G- Flat No 614 | NA | 0.0000 | 0.0000 | 287 | 558851 | 31 | 0 | [6 empty] | 0.0000
341 | 558905 | G. 614 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 340 | 558904 | 4 | 33516 | G- 101 Balcony Waterproofing Work |  |  |  |  | Started | 0.0000
342 | 558906 | G. 614 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 340 | 558904 | 4 | 33517 | G- 101 Bath & WC W/P Work |  |  |  |  | Started | 0.0000
343 | 558907 | G. 614 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 340 | 558904 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work |  |  |  |  | Started | 0.0000
344 | 576670 | G- 7th Floor | NA | 0.0000 | 0.0000 | 1 | 555866 | 31 | 0 | [6 empty] | 0.0000
345 | 576671 | G- Flat No 701 | NA | 0.0000 | 0.0000 | 344 | 576670 | 31 | 0 | [6 empty] | 0.0000
346 | 576672 | G. 701 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 345 | 576671 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
347 | 576673 | G. 701 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 345 | 576671 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
348 | 576674 | G. 701 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 345 | 576671 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
349 | 576675 | G- Flat No 702 | NA | 0.0000 | 0.0000 | 344 | 576670 | 31 | 0 | [6 empty] | 0.0000
350 | 576676 | G. 702 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 349 | 576675 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
351 | 576677 | G. 702 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 349 | 576675 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
352 | 576678 | G. 702 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 349 | 576675 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
353 | 576679 | G- Flat No 703 | NA | 0.0000 | 0.0000 | 344 | 576670 | 31 | 0 | [6 empty] | 0.0000
354 | 576680 | G. 703 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 353 | 576679 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
355 | 576681 | G. 703 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 353 | 576679 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
356 | 576682 | G. 703 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 353 | 576679 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
357 | 576683 | G- Flat No 704 | NA | 0.0000 | 0.0000 | 344 | 576670 | 31 | 0 | [6 empty] | 0.0000
358 | 576684 | G. 704 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 357 | 576683 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
359 | 576685 | G. 704 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 357 | 576683 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
360 | 576686 | G. 704 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 357 | 576683 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
361 | 576687 | G- Flat No 705 | NA | 0.0000 | 0.0000 | 344 | 576670 | 31 | 0 | [6 empty] | 0.0000
362 | 576688 | G. 705 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 361 | 576687 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
363 | 576689 | G. 705 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 361 | 576687 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
364 | 576690 | G. 705 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 361 | 576687 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
365 | 576691 | G- Flat No 706 | NA | 0.0000 | 0.0000 | 344 | 576670 | 31 | 0 | [6 empty] | 0.0000
366 | 576692 | G. 706 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 365 | 576691 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
367 | 576693 | G. 706 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 365 | 576691 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
368 | 576694 | G. 706 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 365 | 576691 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
369 | 576695 | G- Flat No 707 | NA | 0.0000 | 0.0000 | 344 | 576670 | 31 | 0 | [6 empty] | 0.0000
370 | 576696 | G. 707 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 369 | 576695 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
371 | 576697 | G. 707 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 369 | 576695 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
372 | 576698 | G. 707 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 369 | 576695 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
373 | 576699 | G- Flat No 708 | NA | 0.0000 | 0.0000 | 344 | 576670 | 31 | 0 | [6 empty] | 0.0000
374 | 576700 | G. 708 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 373 | 576699 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
375 | 576701 | G. 708 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 373 | 576699 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
376 | 576702 | G. 708 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 373 | 576699 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
377 | 576703 | G- Flat No 709 | NA | 0.0000 | 0.0000 | 344 | 576670 | 31 | 0 | [6 empty] | 0.0000
378 | 576704 | G. 709 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 377 | 576703 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
379 | 576705 | G. 709 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 377 | 576703 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
380 | 576706 | G. 709 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 377 | 576703 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
381 | 576707 | G- Flat No 710 | NA | 0.0000 | 0.0000 | 344 | 576670 | 31 | 0 | [6 empty] | 0.0000
382 | 576708 | G. 710 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 381 | 576707 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
383 | 576709 | G. 710 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 381 | 576707 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
384 | 576710 | G. 710 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 381 | 576707 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
385 | 576711 | G- Flat No 711 | NA | 0.0000 | 0.0000 | 344 | 576670 | 31 | 0 | [6 empty] | 0.0000
386 | 576712 | G. 711 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 385 | 576711 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
387 | 576713 | G. 711 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 385 | 576711 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
388 | 576714 | G. 711 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 385 | 576711 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
389 | 576715 | G- Flat No 712 | NA | 0.0000 | 0.0000 | 344 | 576670 | 31 | 0 | [6 empty] | 0.0000
390 | 576716 | G. 712 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 389 | 576715 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
391 | 576717 | G. 712 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 389 | 576715 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
392 | 576718 | G. 712 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 389 | 576715 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
393 | 576719 | G- Flat No 713 | NA | 0.0000 | 0.0000 | 344 | 576670 | 31 | 0 | [6 empty] | 0.0000
394 | 576720 | G. 713 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 393 | 576719 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
395 | 576721 | G. 713 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 393 | 576719 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
396 | 576722 | G. 713 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 393 | 576719 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
397 | 576723 | G- Flat No 714 | NA | 0.0000 | 0.0000 | 344 | 576670 | 31 | 0 | [6 empty] | 0.0000
398 | 576724 | G. 714 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 397 | 576723 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
399 | 576725 | G. 714 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 397 | 576723 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
400 | 576726 | G. 714 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 397 | 576723 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
401 | 576785 | G- 8th Floor | NA | 0.0000 | 0.0000 | 1 | 555866 | 31 | 0 | [6 empty] | 0.0000
402 | 576786 | G- Flat No 801 | NA | 0.0000 | 0.0000 | 401 | 576785 | 31 | 0 | [6 empty] | 0.0000
403 | 576787 | G. 801 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 402 | 576786 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
404 | 576788 | G. 801 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 402 | 576786 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
405 | 576789 | G. 801 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 402 | 576786 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
406 | 576790 | G- Flat No 802 | NA | 0.0000 | 0.0000 | 401 | 576785 | 31 | 0 | [6 empty] | 0.0000
407 | 576791 | G. 802 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 406 | 576790 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
408 | 576792 | G. 802 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 406 | 576790 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
409 | 576793 | G. 802 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 406 | 576790 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
410 | 576794 | G- Flat No 803 | NA | 0.0000 | 0.0000 | 401 | 576785 | 31 | 0 | [6 empty] | 0.0000
411 | 576795 | G. 803 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 410 | 576794 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
412 | 576796 | G. 803 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 410 | 576794 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
413 | 576797 | G. 803 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 410 | 576794 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
414 | 576798 | G- Flat No 804 | NA | 0.0000 | 0.0000 | 401 | 576785 | 31 | 0 | [6 empty] | 0.0000
415 | 576799 | G. 804 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 414 | 576798 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
416 | 576800 | G. 804 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 414 | 576798 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
417 | 576801 | G. 804 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 414 | 576798 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
418 | 576802 | G- Flat No 805 | NA | 0.0000 | 0.0000 | 401 | 576785 | 31 | 0 | [6 empty] | 0.0000
419 | 576803 | G. 805 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 418 | 576802 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
420 | 576804 | G. 805 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 418 | 576802 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
421 | 576805 | G. 805 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 418 | 576802 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
422 | 576806 | G- Flat No 806 | NA | 0.0000 | 0.0000 | 401 | 576785 | 31 | 0 | [6 empty] | 0.0000
423 | 576807 | G. 806 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 422 | 576806 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
424 | 576808 | G. 806 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 422 | 576806 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
425 | 576809 | G. 806 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 422 | 576806 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
426 | 576810 | G- Flat No 807 | NA | 0.0000 | 0.0000 | 401 | 576785 | 31 | 0 | [6 empty] | 0.0000
427 | 576811 | G. 807 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 426 | 576810 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
428 | 576812 | G. 807 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 426 | 576810 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
429 | 576813 | G. 807 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 426 | 576810 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
430 | 576814 | G- Flat No 808 | NA | 0.0000 | 0.0000 | 401 | 576785 | 31 | 0 | [6 empty] | 0.0000
431 | 576815 | G. 808 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 430 | 576814 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
432 | 576816 | G. 808 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 430 | 576814 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
433 | 576817 | G. 808 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 430 | 576814 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
434 | 576818 | G- Flat No 809 | NA | 0.0000 | 0.0000 | 401 | 576785 | 31 | 0 | [6 empty] | 0.0000
435 | 576819 | G. 809 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 434 | 576818 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
436 | 576820 | G. 809 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 434 | 576818 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
437 | 576821 | G. 809 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 434 | 576818 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
438 | 576822 | G- Flat No 810 | NA | 0.0000 | 0.0000 | 401 | 576785 | 31 | 0 | [6 empty] | 0.0000
439 | 576823 | G. 810 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 438 | 576822 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
440 | 576824 | G. 810 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 438 | 576822 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
441 | 576825 | G. 810 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 438 | 576822 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
442 | 576826 | G- Flat No 811 | NA | 0.0000 | 0.0000 | 401 | 576785 | 31 | 0 | [6 empty] | 0.0000
443 | 576827 | G. 811 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 442 | 576826 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
444 | 576828 | G. 811 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 442 | 576826 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
445 | 576829 | G. 811 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 442 | 576826 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
446 | 576830 | G- Flat No 812 | NA | 0.0000 | 0.0000 | 401 | 576785 | 31 | 0 | [6 empty] | 0.0000
447 | 576831 | G. 812 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 446 | 576830 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
448 | 576832 | G. 812 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 446 | 576830 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
449 | 576833 | G. 812 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 446 | 576830 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
450 | 576834 | G- Flat No 813 | NA | 0.0000 | 0.0000 | 401 | 576785 | 31 | 0 | [6 empty] | 0.0000
451 | 576835 | G. 813 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 450 | 576834 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
452 | 576836 | G. 813 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 450 | 576834 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
453 | 576837 | G. 813 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 450 | 576834 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
454 | 576838 | G- Flat No 814 | NA | 0.0000 | 0.0000 | 401 | 576785 | 31 | 0 | [6 empty] | 0.0000
455 | 576839 | G. 814 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 454 | 576838 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
456 | 576840 | G. 814 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 454 | 576838 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
457 | 576841 | G. 814 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 454 | 576838 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
458 | 576871 | G- 9th Floor | NA | 0.0000 | 0.0000 | 1 | 555866 | 31 | 0 | [6 empty] | 0.0000
459 | 576872 | G- Flat No 901 | NA | 0.0000 | 0.0000 | 458 | 576871 | 31 | 0 | [6 empty] | 0.0000
460 | 576873 | G. 901 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 459 | 576872 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
461 | 576874 | G. 901 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 459 | 576872 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
462 | 576875 | G. 901 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 459 | 576872 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
463 | 576876 | G- Flat No 902 | NA | 0.0000 | 0.0000 | 458 | 576871 | 31 | 0 | [6 empty] | 0.0000
464 | 576877 | G. 902 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 463 | 576876 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
465 | 576878 | G. 902 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 463 | 576876 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
466 | 576879 | G. 902 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 463 | 576876 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
467 | 576880 | G- Flat No 903 | NA | 0.0000 | 0.0000 | 458 | 576871 | 31 | 0 | [6 empty] | 0.0000
468 | 576881 | G. 903 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 467 | 576880 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
469 | 576882 | G. 903 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 467 | 576880 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
470 | 576883 | G. 903 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 467 | 576880 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
471 | 576884 | G- Flat No 904 | NA | 0.0000 | 0.0000 | 458 | 576871 | 31 | 0 | [6 empty] | 0.0000
472 | 576885 | G. 904 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 471 | 576884 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
473 | 576886 | G. 904 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 471 | 576884 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
474 | 576887 | G. 904 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 471 | 576884 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
475 | 576888 | G- Flat No 905 | NA | 0.0000 | 0.0000 | 458 | 576871 | 31 | 0 | [6 empty] | 0.0000
476 | 576889 | G. 905 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 475 | 576888 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
477 | 576890 | G. 905 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 475 | 576888 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
478 | 576891 | G. 905 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 475 | 576888 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
479 | 576892 | G- Flat No 906 | NA | 0.0000 | 0.0000 | 458 | 576871 | 31 | 0 | [6 empty] | 0.0000
480 | 576893 | G. 906 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 479 | 576892 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
481 | 576894 | G. 906 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 479 | 576892 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
482 | 576895 | G. 906 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 479 | 576892 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
483 | 576896 | G- Flat No 907 | NA | 0.0000 | 0.0000 | 458 | 576871 | 31 | 0 | [6 empty] | 0.0000
484 | 576897 | G. 907 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 483 | 576896 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
485 | 576898 | G. 907 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 483 | 576896 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
486 | 576899 | G. 907 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 483 | 576896 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
487 | 576900 | G- Flat No 908 | NA | 0.0000 | 0.0000 | 458 | 576871 | 31 | 0 | [6 empty] | 0.0000
488 | 576901 | G. 908 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 487 | 576900 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
489 | 576902 | G. 908 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 487 | 576900 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
490 | 576903 | G. 908 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 487 | 576900 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
491 | 576904 | G- Flat No 909 | NA | 0.0000 | 0.0000 | 458 | 576871 | 31 | 0 | [6 empty] | 0.0000
492 | 576905 | G. 909 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 491 | 576904 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
493 | 576906 | G. 909 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 491 | 576904 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
494 | 576907 | G. 909 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 491 | 576904 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
495 | 576908 | G- Flat No 910 | NA | 0.0000 | 0.0000 | 458 | 576871 | 31 | 0 | [6 empty] | 0.0000
496 | 576909 | G. 910 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 495 | 576908 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
497 | 576910 | G. 910 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 495 | 576908 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
498 | 576911 | G. 910 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 495 | 576908 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
499 | 576912 | G- Flat No 911 | NA | 0.0000 | 0.0000 | 458 | 576871 | 31 | 0 | [6 empty] | 0.0000
500 | 576913 | G. 911 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 499 | 576912 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
501 | 576914 | G. 911 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 499 | 576912 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
502 | 576915 | G. 911 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 499 | 576912 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
503 | 576916 | G- Flat No 912 | NA | 0.0000 | 0.0000 | 458 | 576871 | 31 | 0 | [6 empty] | 0.0000
504 | 576917 | G. 912 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 503 | 576916 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
505 | 576918 | G. 912 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 503 | 576916 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
506 | 576919 | G. 912 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 503 | 576916 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
507 | 576920 | G- Flat No 913 | NA | 0.0000 | 0.0000 | 458 | 576871 | 31 | 0 | [6 empty] | 0.0000
508 | 576921 | G. 913 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 507 | 576920 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
509 | 576922 | G. 913 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 507 | 576920 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
510 | 576923 | G. 913 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 507 | 576920 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
511 | 576924 | G- Flat No 914 | NA | 0.0000 | 0.0000 | 458 | 576871 | 31 | 0 | [6 empty] | 0.0000
512 | 576925 | G. 914 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 511 | 576924 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
513 | 576926 | G. 914 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 511 | 576924 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
514 | 576927 | G. 914 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 511 | 576924 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
515 | 576957 | G- 10th Floor | NA | 0.0000 | 0.0000 | 1 | 555866 | 31 | 0 | [6 empty] | 0.0000
516 | 576958 | G- Flat No 1001 | NA | 0.0000 | 0.0000 | 515 | 576957 | 31 | 0 | [6 empty] | 0.0000
517 | 576959 | G. 1001 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 516 | 576958 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
518 | 576960 | G. 1001 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 516 | 576958 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
519 | 576961 | G. 1001 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 516 | 576958 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
520 | 576962 | G- Flat No 1002 | NA | 0.0000 | 0.0000 | 515 | 576957 | 31 | 0 | [6 empty] | 0.0000
521 | 576963 | G. 1002 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 520 | 576962 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
522 | 576964 | G. 1002 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 520 | 576962 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
523 | 576965 | G. 1002 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 520 | 576962 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
524 | 576966 | G- Flat No 1003 | NA | 0.0000 | 0.0000 | 515 | 576957 | 31 | 0 | [6 empty] | 0.0000
525 | 576967 | G. 1003 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 524 | 576966 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
526 | 576968 | G. 1003 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 524 | 576966 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
527 | 576969 | G. 1003 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 524 | 576966 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
528 | 576970 | G- Flat No 1004 | NA | 0.0000 | 0.0000 | 515 | 576957 | 31 | 0 | [6 empty] | 0.0000
529 | 576971 | G. 1004 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 528 | 576970 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
530 | 576972 | G. 1004 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 528 | 576970 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
531 | 576973 | G. 1004 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 528 | 576970 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
532 | 576974 | G- Flat No 1005 | NA | 0.0000 | 0.0000 | 515 | 576957 | 31 | 0 | [6 empty] | 0.0000
533 | 576975 | G. 1005 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 532 | 576974 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
534 | 576976 | G. 1005 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 532 | 576974 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
535 | 576977 | G. 1005 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 532 | 576974 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
536 | 576978 | G- Flat No 1006 | NA | 0.0000 | 0.0000 | 515 | 576957 | 31 | 0 | [6 empty] | 0.0000
537 | 576979 | G. 1006 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 536 | 576978 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
538 | 576980 | G. 1006 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 536 | 576978 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
539 | 576981 | G. 1006 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 536 | 576978 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
540 | 576982 | G- Flat No 1007 | NA | 0.0000 | 0.0000 | 515 | 576957 | 31 | 0 | [6 empty] | 0.0000
541 | 576983 | G. 1007 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 540 | 576982 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
542 | 576984 | G. 1007 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 540 | 576982 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
543 | 576985 | G. 1007 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 540 | 576982 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
544 | 576986 | G- Flat No 1008 | NA | 0.0000 | 0.0000 | 515 | 576957 | 31 | 0 | [6 empty] | 0.0000
545 | 576987 | G. 1008 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 544 | 576986 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
546 | 576988 | G. 1008 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 544 | 576986 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
547 | 576989 | G. 1008 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 544 | 576986 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
548 | 576990 | G- Flat No 1009 | NA | 0.0000 | 0.0000 | 515 | 576957 | 31 | 0 | [6 empty] | 0.0000
549 | 576991 | G. 1009 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 548 | 576990 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
550 | 576992 | G. 1009 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 548 | 576990 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
551 | 576993 | G. 1009 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 548 | 576990 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
552 | 576994 | G- Flat No 1010 | NA | 0.0000 | 0.0000 | 515 | 576957 | 31 | 0 | [6 empty] | 0.0000
553 | 576995 | G. 1010 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 552 | 576994 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
554 | 576996 | G. 1010 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 552 | 576994 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
555 | 576997 | G. 1010 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 552 | 576994 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
556 | 576998 | G- Flat No 1011 | NA | 0.0000 | 0.0000 | 515 | 576957 | 31 | 0 | [6 empty] | 0.0000
557 | 576999 | G. 1011 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 556 | 576998 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
558 | 577000 | G. 1011 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 556 | 576998 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
559 | 577001 | G. 1011 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 556 | 576998 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
560 | 577002 | G- Flat No 1012 | NA | 0.0000 | 0.0000 | 515 | 576957 | 31 | 0 | [6 empty] | 0.0000
561 | 577003 | G. 1012 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 560 | 577002 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
562 | 577004 | G. 1012 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 560 | 577002 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
563 | 577005 | G. 1012 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 560 | 577002 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
564 | 577006 | G- Flat No 1013 | NA | 0.0000 | 0.0000 | 515 | 576957 | 31 | 0 | [6 empty] | 0.0000
565 | 577007 | G. 1013 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 564 | 577006 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
566 | 577008 | G. 1013 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 564 | 577006 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
567 | 577009 | G. 1013 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 564 | 577006 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
568 | 577010 | G- Flat No 1014 | NA | 0.0000 | 0.0000 | 515 | 576957 | 31 | 0 | [6 empty] | 0.0000
569 | 577011 | G. 1014 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 568 | 577010 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
570 | 577012 | G. 1014 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 568 | 577010 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
571 | 577013 | G. 1014 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 568 | 577010 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
572 | 577014 | G- 11th Floor | NA | 0.0000 | 0.0000 | 1 | 555866 | 31 | 0 | [6 empty] | 0.0000
573 | 577015 | G- Flat No 1101 | NA | 0.0000 | 0.0000 | 572 | 577014 | 31 | 0 | [6 empty] | 0.0000
574 | 577016 | G. 1101 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 573 | 577015 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
575 | 577017 | G. 1101 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 573 | 577015 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
576 | 577018 | G. 1101 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 573 | 577015 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
577 | 577019 | G- Flat No 1102 | NA | 0.0000 | 0.0000 | 572 | 577014 | 31 | 0 | [6 empty] | 0.0000
578 | 577020 | G. 1102 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 577 | 577019 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
579 | 577021 | G. 1102 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 577 | 577019 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
580 | 577022 | G. 1102 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 577 | 577019 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
581 | 577023 | G- Flat No 1103 | NA | 0.0000 | 0.0000 | 572 | 577014 | 31 | 0 | [6 empty] | 0.0000
582 | 577024 | G. 1103 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 581 | 577023 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
583 | 577025 | G. 1103 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 581 | 577023 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
584 | 577026 | G. 1103 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 581 | 577023 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
585 | 577027 | G- Flat No 1104 | NA | 0.0000 | 0.0000 | 572 | 577014 | 31 | 0 | [6 empty] | 0.0000
586 | 577028 | G. 1104 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 585 | 577027 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
587 | 577029 | G. 1104 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 585 | 577027 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
588 | 577030 | G. 1104 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 585 | 577027 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
589 | 577031 | G- Flat No 1105 | NA | 0.0000 | 0.0000 | 572 | 577014 | 31 | 0 | [6 empty] | 0.0000
590 | 577032 | G. 1105 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 589 | 577031 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
591 | 577033 | G. 1105 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 589 | 577031 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
592 | 577034 | G. 1105 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 589 | 577031 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
593 | 577035 | G- Flat No 1106 | NA | 0.0000 | 0.0000 | 572 | 577014 | 31 | 0 | [6 empty] | 0.0000
594 | 577036 | G. 1106 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 593 | 577035 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
595 | 577037 | G. 1106 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 593 | 577035 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
596 | 577038 | G. 1106 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 593 | 577035 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
597 | 577039 | G- Flat No 1107 | NA | 0.0000 | 0.0000 | 572 | 577014 | 31 | 0 | [6 empty] | 0.0000
598 | 577040 | G. 1107 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 597 | 577039 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
599 | 577041 | G. 1107 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 597 | 577039 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
600 | 577042 | G. 1107 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 597 | 577039 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
601 | 577043 | G- Flat No 1108 | NA | 0.0000 | 0.0000 | 572 | 577014 | 31 | 0 | [6 empty] | 0.0000
602 | 577044 | G. 1108 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 601 | 577043 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
603 | 577045 | G. 1108 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 601 | 577043 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
604 | 577046 | G. 1108 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 601 | 577043 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
605 | 577047 | G- Flat No 1109 | NA | 0.0000 | 0.0000 | 572 | 577014 | 31 | 0 | [6 empty] | 0.0000
606 | 577048 | G. 1109 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 605 | 577047 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
607 | 577049 | G. 1109 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 605 | 577047 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
608 | 577050 | G. 1109 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 605 | 577047 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
609 | 577051 | G- Flat No 1110 | NA | 0.0000 | 0.0000 | 572 | 577014 | 31 | 0 | [6 empty] | 0.0000
610 | 577052 | G. 1110 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 609 | 577051 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
611 | 577053 | G. 1110 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 609 | 577051 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
612 | 577054 | G. 1110 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 609 | 577051 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
613 | 577055 | G- Flat No 1111 | NA | 0.0000 | 0.0000 | 572 | 577014 | 31 | 0 | [6 empty] | 0.0000
614 | 577056 | G. 1111 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 613 | 577055 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
615 | 577057 | G. 1111 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 613 | 577055 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
616 | 577058 | G. 1111 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 613 | 577055 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
617 | 577059 | G- Flat No 1112 | NA | 0.0000 | 0.0000 | 572 | 577014 | 31 | 0 | [6 empty] | 0.0000
618 | 577060 | G. 1112 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 617 | 577059 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
619 | 577061 | G. 1112 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 617 | 577059 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
620 | 577062 | G. 1112 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 617 | 577059 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
621 | 577063 | G- Flat No 1113 | NA | 0.0000 | 0.0000 | 572 | 577014 | 31 | 0 | [6 empty] | 0.0000
622 | 577064 | G. 1113 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 621 | 577063 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
623 | 577065 | G. 1113 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 621 | 577063 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
624 | 577066 | G. 1113 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 621 | 577063 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
625 | 577067 | G- Flat No 1114 | NA | 0.0000 | 0.0000 | 572 | 577014 | 31 | 0 | [6 empty] | 0.0000
626 | 577068 | G. 1114 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 625 | 577067 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
627 | 577069 | G. 1114 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 625 | 577067 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
628 | 577070 | G. 1114 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 625 | 577067 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
629 | 577071 | G- 12th Floor | NA | 0.0000 | 0.0000 | 1 | 555866 | 31 | 0 | [6 empty] | 0.0000
630 | 577072 | G- Flat No 1201 | NA | 0.0000 | 0.0000 | 629 | 577071 | 31 | 0 | [6 empty] | 0.0000
631 | 577073 | G. 1201 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 630 | 577072 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
632 | 577074 | G. 1201 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 630 | 577072 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
633 | 577075 | G. 1201 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 630 | 577072 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
634 | 577076 | G- Flat No 1202 | NA | 0.0000 | 0.0000 | 629 | 577071 | 31 | 0 | [6 empty] | 0.0000
635 | 577077 | G. 1202 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 634 | 577076 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
636 | 577078 | G. 1202 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 634 | 577076 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
637 | 577079 | G. 1202 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 634 | 577076 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
638 | 577080 | G- Flat No 1203 | NA | 0.0000 | 0.0000 | 629 | 577071 | 31 | 0 | [6 empty] | 0.0000
639 | 577081 | G. 1203 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 638 | 577080 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
640 | 577082 | G. 1203 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 638 | 577080 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
641 | 577083 | G. 1203 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 638 | 577080 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
642 | 577084 | G- Flat No 1204 | NA | 0.0000 | 0.0000 | 629 | 577071 | 31 | 0 | [6 empty] | 0.0000
643 | 577085 | G. 1204 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 642 | 577084 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
644 | 577086 | G. 1204 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 642 | 577084 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
645 | 577087 | G. 1204 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 642 | 577084 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
646 | 577088 | G- Flat No 1205 | NA | 0.0000 | 0.0000 | 629 | 577071 | 31 | 0 | [6 empty] | 0.0000
647 | 577089 | G. 1205 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 646 | 577088 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
648 | 577090 | G. 1205 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 646 | 577088 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
649 | 577091 | G. 1205 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 646 | 577088 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
650 | 577092 | G- Flat No 1206 | NA | 0.0000 | 0.0000 | 629 | 577071 | 31 | 0 | [6 empty] | 0.0000
651 | 577093 | G. 1206 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 650 | 577092 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
652 | 577094 | G. 1206 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 650 | 577092 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
653 | 577095 | G. 1206 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 650 | 577092 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
654 | 577096 | G- Flat No 1207 | NA | 0.0000 | 0.0000 | 629 | 577071 | 31 | 0 | [6 empty] | 0.0000
655 | 577097 | G. 1207 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 654 | 577096 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
656 | 577098 | G. 1207 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 654 | 577096 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
657 | 577099 | G. 1207 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 654 | 577096 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
658 | 577100 | G- Flat No 1208 | NA | 0.0000 | 0.0000 | 629 | 577071 | 31 | 0 | [6 empty] | 0.0000
659 | 577101 | G. 1208 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 658 | 577100 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
660 | 577102 | G. 1208 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 658 | 577100 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
661 | 577103 | G. 1208 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 658 | 577100 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
662 | 577104 | G- Flat No 1209 | NA | 0.0000 | 0.0000 | 629 | 577071 | 31 | 0 | [6 empty] | 0.0000
663 | 577105 | G. 1209 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 662 | 577104 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
664 | 577106 | G. 1209 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 662 | 577104 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
665 | 577107 | G. 1209 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 662 | 577104 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
666 | 577108 | G- Flat No 1210 | NA | 0.0000 | 0.0000 | 629 | 577071 | 31 | 0 | [6 empty] | 0.0000
667 | 577109 | G. 1210 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 666 | 577108 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
668 | 577110 | G. 1210 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 666 | 577108 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
669 | 577111 | G. 1210 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 666 | 577108 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
670 | 577112 | G- Flat No 1211 | NA | 0.0000 | 0.0000 | 629 | 577071 | 31 | 0 | [6 empty] | 0.0000
671 | 577113 | G. 1211 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 670 | 577112 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
672 | 577114 | G. 1211 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 670 | 577112 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
673 | 577115 | G. 1211 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 670 | 577112 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
674 | 577116 | G- Flat No 1212 | NA | 0.0000 | 0.0000 | 629 | 577071 | 31 | 0 | [6 empty] | 0.0000
675 | 577117 | G. 1212 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 674 | 577116 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
676 | 577118 | G. 1212 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 674 | 577116 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
677 | 577119 | G. 1212 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 674 | 577116 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
678 | 577120 | G- Flat No 1213 | NA | 0.0000 | 0.0000 | 629 | 577071 | 31 | 0 | [6 empty] | 0.0000
679 | 577121 | G. 1213 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 678 | 577120 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
680 | 577122 | G. 1213 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 678 | 577120 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
681 | 577123 | G. 1213 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 678 | 577120 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
682 | 577124 | G- Flat No 1214 | NA | 0.0000 | 0.0000 | 629 | 577071 | 31 | 0 | [6 empty] | 0.0000
683 | 577125 | G. 1214 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 682 | 577124 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
684 | 577126 | G. 1214 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 682 | 577124 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
685 | 577127 | G. 1214 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 682 | 577124 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
686 | 577128 | G- 13th Floor | NA | 0.0000 | 0.0000 | 1 | 555866 | 31 | 0 | [6 empty] | 0.0000
687 | 577129 | G- Flat No 1301 | NA | 0.0000 | 0.0000 | 686 | 577128 | 31 | 0 | [6 empty] | 0.0000
688 | 577130 | G. 1301 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 687 | 577129 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
689 | 577131 | G. 1301 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 687 | 577129 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
690 | 577132 | G. 1301 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 687 | 577129 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
691 | 577133 | G- Flat No 1302 | NA | 0.0000 | 0.0000 | 686 | 577128 | 31 | 0 | [6 empty] | 0.0000
692 | 577134 | G. 1302 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 691 | 577133 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
693 | 577135 | G. 1302 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 691 | 577133 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
694 | 577136 | G. 1302 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 691 | 577133 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
695 | 577137 | G- Flat No 1303 | NA | 0.0000 | 0.0000 | 686 | 577128 | 31 | 0 | [6 empty] | 0.0000
696 | 577138 | G. 1303 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 695 | 577137 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
697 | 577139 | G. 1303 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 695 | 577137 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
698 | 577140 | G. 1303 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 695 | 577137 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
699 | 577141 | G- Flat No 1304 | NA | 0.0000 | 0.0000 | 686 | 577128 | 31 | 0 | [6 empty] | 0.0000
700 | 577142 | G. 1304 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 699 | 577141 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
701 | 577143 | G. 1304 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 699 | 577141 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
702 | 577144 | G. 1304 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 699 | 577141 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
703 | 577145 | G- Flat No 1305 | NA | 0.0000 | 0.0000 | 686 | 577128 | 31 | 0 | [6 empty] | 0.0000
704 | 577146 | G. 1305 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 703 | 577145 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
705 | 577147 | G. 1305 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 703 | 577145 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
706 | 577148 | G. 1305 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 703 | 577145 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
707 | 577149 | G- Flat No 1306 | NA | 0.0000 | 0.0000 | 686 | 577128 | 31 | 0 | [6 empty] | 0.0000
708 | 577150 | G. 1306 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 707 | 577149 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
709 | 577151 | G. 1306 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 707 | 577149 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
710 | 577152 | G. 1306 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 707 | 577149 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
711 | 577153 | G- Flat No 1307 | NA | 0.0000 | 0.0000 | 686 | 577128 | 31 | 0 | [6 empty] | 0.0000
712 | 577154 | G. 1307 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 711 | 577153 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
713 | 577155 | G. 1307 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 711 | 577153 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
714 | 577156 | G. 1307 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 711 | 577153 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
715 | 577157 | G- Flat No 1308 | NA | 0.0000 | 0.0000 | 686 | 577128 | 31 | 0 | [6 empty] | 0.0000
716 | 577158 | G. 1308 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 715 | 577157 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
717 | 577159 | G. 1308 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 715 | 577157 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
718 | 577160 | G. 1308 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 715 | 577157 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
719 | 577161 | G- Flat No 1309 | NA | 0.0000 | 0.0000 | 686 | 577128 | 31 | 0 | [6 empty] | 0.0000
720 | 577162 | G. 1309 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 719 | 577161 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
721 | 577163 | G. 1309 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 719 | 577161 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
722 | 577164 | G. 1309 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 719 | 577161 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
723 | 577165 | G- Flat No 1310 | NA | 0.0000 | 0.0000 | 686 | 577128 | 31 | 0 | [6 empty] | 0.0000
724 | 577166 | G. 1310 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 723 | 577165 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
725 | 577167 | G. 1310 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 723 | 577165 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
726 | 577168 | G. 1310 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 723 | 577165 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
727 | 577169 | G- Flat No 1311 | NA | 0.0000 | 0.0000 | 686 | 577128 | 31 | 0 | [6 empty] | 0.0000
728 | 577170 | G. 1311 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 727 | 577169 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
729 | 577171 | G. 1311 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 727 | 577169 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
730 | 577172 | G. 1311 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 727 | 577169 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
731 | 577173 | G- Flat No 1312 | NA | 0.0000 | 0.0000 | 686 | 577128 | 31 | 0 | [6 empty] | 0.0000
732 | 577174 | G. 1312 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 731 | 577173 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
733 | 577175 | G. 1312 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 731 | 577173 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
734 | 577176 | G. 1312 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 731 | 577173 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
735 | 577177 | G- Flat No 1313 | NA | 0.0000 | 0.0000 | 686 | 577128 | 31 | 0 | [6 empty] | 0.0000
736 | 577178 | G. 1313 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 735 | 577177 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
737 | 577179 | G. 1313 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 735 | 577177 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
738 | 577180 | G. 1313 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 735 | 577177 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000
739 | 577181 | G- Flat No 1314 | NA | 0.0000 | 0.0000 | 686 | 577128 | 31 | 0 | [6 empty] | 0.0000
740 | 577182 | G. 1314 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 739 | 577181 | 4 | 33516 | G- 101 Balcony Waterproofing Work | [5 empty] | 0.0000
741 | 577183 | G. 1314 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 739 | 577181 | 4 | 33517 | G- 101 Bath & WC W/P Work | [5 empty] | 0.0000
742 | 577184 | G. 1314 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 739 | 577181 | 4 | 33518 | G- 101 Internal Flat Floor Grouting Work | [5 empty] | 0.0000