## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- D - 4th Floor | Selected Group :- D - 4th Floor | Selected Group :- D - 4th Floor | Selected Group :- D - 4th Floor | Selected Group :- D - 4th Floor | Selected Group :- D - 4th Floor | Selected Group :- D - 4th Floor | Selected Group :- D - 4th Floor | Selected Group :- D - 4th Floor | Selected Group :- D - 4th Floor | Selected Group :- D - 4th Floor | Selected Group :- D - 4th Floor | Selected Group :- D - 4th Floor | Selected Group :- D - 4th Floor | Selected Group :- D - 4th Floor | Selected Group :- D - 4th Floor | Selected Group :- D - 4th Floor
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 588726 | D - 4th Floor | NA | 0.0000 | 0.0000 | 0 | 588626 | 31 | 0 | [6 empty] | 0.0000
2 | 588727 | D - Flat No. 401 | NA | 0.0000 | 0.0000 | 1 | 588726 | 31 | 0 | [6 empty] | 0.0000
3 | 588728 | D - Flat No. 401 Internal Flat Chemical Grouting Work | Sq.Ft | 241.9700 | 241.9700 | 2 | 588727 | 4 | 34080 | D - Flat No. 301 Internal Flat Chemical | [5 empty] | 0.0000
4 | 588729 | D - Flat No. 401 WC,Bath,Balcony Brickbat W/P Work | Sq.Ft | 53.8200 | 53.8200 | 2 | 588727 | 4 | 34081 | D - Flat No. 301 WC,Bath,Balcony Brickba | [5 empty] | 0.0000
5 | 588730 | D - Flat No. 401 WC,Bath,Balcony Chemical W/P Work | Sq.Ft | 53.8200 | 53.8200 | 2 | 588727 | 4 | 34082 | D - Flat No. 301 WC,Bath,Balcony Chemica | [5 empty] | 0.0000
6 | 588731 | D - Flat No. 401 WC,Bath,Balcony IPS W/P Work | Sq.Ft | 53.8200 | 53.8200 | 2 | 588727 | 4 | 34083 | D - Flat No. 301 WC,Bath,Balcony IPS W/P | [5 empty] | 0.0000
7 | 588732 | D- Flat No. 401 WC,Bath,Balcony Door IPS Seal Pack | Flat | 1.0000 | 1.0000 | 2 | 588727 | 4 | 34084 | D- Flat No. 301 WC,Bath,Balcony Door IP | [5 empty] | 0.0000
8 | 588733 | D - Flat No. 401 Bore Packing + Perma Eazee Coat- Flat | No. | 1.0000 | 1.0000 | 2 | 588727 | 4 | 34085 | D - Flat No. 301 Bore Packing + Perma Ea | [5 empty] | 0.0000
9 | 588734 | D - Flat No. 402 | NA | 0.0000 | 0.0000 | 1 | 588726 | 31 | 0 | [6 empty] | 0.0000
10 | 588735 | D - Flat No. 402 Internal Flat Chemical Grouting Work | Sq.Ft | 243.9100 | 243.9100 | 9 | 588734 | 4 | 34080 | D - Flat No. 301 Internal Flat Chemical | [5 empty] | 0.0000
11 | 588736 | D - Flat No. 402 WC,Bath,Balcony Brickbat W/P Work | Sq.Ft | 52.1000 | 52.1000 | 9 | 588734 | 4 | 34081 | D - Flat No. 301 WC,Bath,Balcony Brickba | [5 empty] | 0.0000
12 | 588737 | D - Flat No. 402 WC,Bath,Balcony Chemical W/P Work | Sq.Ft | 52.1000 | 52.1000 | 9 | 588734 | 4 | 34082 | D - Flat No. 301 WC,Bath,Balcony Chemica | [5 empty] | 0.0000
13 | 588738 | D - Flat No. 402 WC,Bath,Balcony IPS W/P Work | Sq.Ft | 52.1000 | 52.1000 | 9 | 588734 | 4 | 34083 | D - Flat No. 301 WC,Bath,Balcony IPS W/P | [5 empty] | 0.0000
14 | 588739 | D- Flat No. 402 WC,Bath,Balcony Door IPS Seal Pack | Flat | 1.0000 | 1.0000 | 9 | 588734 | 4 | 34084 | D- Flat No. 301 WC,Bath,Balcony Door IP | [5 empty] | 0.0000
15 | 588740 | D - Flat No. 402 Bore Packing + Perma Eazee Coat- Flat | No. | 1.0000 | 1.0000 | 9 | 588734 | 4 | 34085 | D - Flat No. 301 Bore Packing + Perma Ea | [5 empty] | 0.0000
16 | 588741 | D - Flat No. 403 | NA | 0.0000 | 0.0000 | 1 | 588726 | 31 | 0 | [6 empty] | 0.0000
17 | 588742 | D - Flat No. 403 Internal Flat Chemical Grouting Work | Sq.Ft | 244.0200 | 244.0200 | 16 | 588741 | 4 | 34080 | D - Flat No. 301 Internal Flat Chemical | [5 empty] | 0.0000
18 | 588743 | D - Flat No. 403 WC,Bath,Balcony Brickbat W/P Work | Sq.Ft | 52.1000 | 52.1000 | 16 | 588741 | 4 | 34081 | D - Flat No. 301 WC,Bath,Balcony Brickba | [5 empty] | 0.0000
19 | 588744 | D - Flat No. 403 WC,Bath,Balcony Chemical W/P Work | Sq.Ft | 52.1000 | 52.1000 | 16 | 588741 | 4 | 34082 | D - Flat No. 301 WC,Bath,Balcony Chemica | [5 empty] | 0.0000
20 | 588745 | D - Flat No. 403 WC,Bath,Balcony IPS W/P Work | Sq.Ft | 52.1000 | 52.1000 | 16 | 588741 | 4 | 34083 | D - Flat No. 301 WC,Bath,Balcony IPS W/P | [5 empty] | 0.0000
21 | 588746 | D- Flat No. 403 WC,Bath,Balcony Door IPS Seal Pack | Flat | 1.0000 | 1.0000 | 16 | 588741 | 4 | 34084 | D- Flat No. 301 WC,Bath,Balcony Door IP | [5 empty] | 0.0000
22 | 588747 | D - Flat No. 403 Bore Packing + Perma Eazee Coat- Flat | No. | 1.0000 | 1.0000 | 16 | 588741 | 4 | 34085 | D - Flat No. 301 Bore Packing + Perma Ea | [5 empty] | 0.0000
23 | 588748 | D - Flat No. 404 | NA | 0.0000 | 0.0000 | 1 | 588726 | 31 | 0 | [6 empty] | 0.0000
24 | 588749 | D - Flat No. 404 Internal Flat Chemical Grouting Work | Sq.Ft | 244.4500 | 244.4500 | 23 | 588748 | 4 | 34080 | D - Flat No. 301 Internal Flat Chemical | [5 empty] | 0.0000
25 | 588750 | D - Flat No. 404 WC,Bath,Balcony Brickbat W/P Work | Sq.Ft | 51.5600 | 51.5600 | 23 | 588748 | 4 | 34081 | D - Flat No. 301 WC,Bath,Balcony Brickba | [5 empty] | 0.0000
26 | 588751 | D - Flat No. 404 WC,Bath,Balcony Chemical W/P Work | Sq.Ft | 51.5600 | 51.5600 | 23 | 588748 | 4 | 34082 | D - Flat No. 301 WC,Bath,Balcony Chemica | [5 empty] | 0.0000
27 | 588752 | D - Flat No. 404 WC,Bath,Balcony IPS W/P Work | Sq.Ft | 51.5600 | 51.5600 | 23 | 588748 | 4 | 34083 | D - Flat No. 301 WC,Bath,Balcony IPS W/P | [5 empty] | 0.0000
28 | 588753 | D- Flat No. 404 WC,Bath,Balcony Door IPS Seal Pack | Flat | 1.0000 | 1.0000 | 23 | 588748 | 4 | 34084 | D- Flat No. 301 WC,Bath,Balcony Door IP | [5 empty] | 0.0000
29 | 588754 | D - Flat No. 404 Bore Packing + Perma Eazee Coat- Flat | No. | 1.0000 | 1.0000 | 23 | 588748 | 4 | 34085 | D - Flat No. 301 Bore Packing + Perma Ea | [5 empty] | 0.0000
30 | 588755 | D - Flat No. 405 | NA | 0.0000 | 0.0000 | 1 | 588726 | 31 | 0 | [6 empty] | 0.0000
31 | 588756 | D - Flat No. 405 Internal Flat Chemical Grouting Work | Sq.Ft | 243.9100 | 243.9100 | 30 | 588755 | 4 | 34080 | D - Flat No. 301 Internal Flat Chemical | [5 empty] | 0.0000
32 | 588757 | D - Flat No. 405 WC,Bath,Balcony Brickbat W/P Work | Sq.Ft | 51.9900 | 51.9900 | 30 | 588755 | 4 | 34081 | D - Flat No. 301 WC,Bath,Balcony Brickba | [5 empty] | 0.0000
33 | 588758 | D - Flat No. 405 WC,Bath,Balcony Chemical W/P Work | Sq.Ft | 51.9900 | 51.9900 | 30 | 588755 | 4 | 34082 | D - Flat No. 301 WC,Bath,Balcony Chemica | [5 empty] | 0.0000
34 | 588759 | D - Flat No. 405 WC,Bath,Balcony IPS W/P Work | Sq.Ft | 51.9900 | 51.9900 | 30 | 588755 | 4 | 34083 | D - Flat No. 301 WC,Bath,Balcony IPS W/P | [5 empty] | 0.0000
35 | 588760 | D- Flat No. 405 WC,Bath,Balcony Door IPS Seal Pack | Flat | 1.0000 | 1.0000 | 30 | 588755 | 4 | 34084 | D- Flat No. 301 WC,Bath,Balcony Door IP | [5 empty] | 0.0000
36 | 588761 | D - Flat No. 405 Bore Packing + Perma Eazee Coat- Flat | No. | 1.0000 | 1.0000 | 30 | 588755 | 4 | 34085 | D - Flat No. 301 Bore Packing + Perma Ea | [5 empty] | 0.0000
37 | 588762 | D - Flat No. 406 | NA | 0.0000 | 0.0000 | 1 | 588726 | 31 | 0 | [6 empty] | 0.0000
38 | 588763 | D - Flat No. 406 Internal Flat Chemical Grouting Work | Sq.Ft | 243.3700 | 243.3700 | 37 | 588762 | 4 | 34080 | D - Flat No. 301 Internal Flat Chemical | [5 empty] | 0.0000
39 | 588764 | D - Flat No. 406 WC,Bath,Balcony Brickbat W/P Work | Sq.Ft | 52.42 | 52.42 | 37 | 588762 | 4 | 34081 | D - Flat No. 301 WC,Bath,Balcony Brickba | [5 empty] | 0.0000
40 | 588765 | D - Flat No. 406 WC,Bath,Balcony Chemical W/P Work | Sq.Ft | 52.42 | 52.42 | 37 | 588762 | 4 | 34082 | D - Flat No. 301 WC,Bath,Balcony Chemica | [5 empty] | 0.0000
41 | 588766 | D - Flat No. 406 WC,Bath,Balcony IPS W/P Work | Sq.Ft | 52.42 | 52.42 | 37 | 588762 | 4 | 34083 | D - Flat No. 301 WC,Bath,Balcony IPS W/P | [5 empty] | 0.0000
42 | 588767 | D- Flat No. 406 WC,Bath,Balcony Door IPS Seal Pack | Flat | 1.0000 | 1.0000 | 37 | 588762 | 4 | 34084 | D- Flat No. 301 WC,Bath,Balcony Door IP | [5 empty] | 0.0000
43 | 588768 | D - Flat No. 406 Bore Packing + Perma Eazee Coat- Flat | No. | 1.0000 | 1.0000 | 37 | 588762 | 4 | 34085 | D - Flat No. 301 Bore Packing + Perma Ea | [5 empty] | 0.0000
44 | 588769 | D - Flat No. 407 | NA | 0.0000 | 0.0000 | 1 | 588726 | 31 | 0 | [6 empty] | 0.0000
45 | 588770 | D - Flat No. 407 Internal Flat Chemical Grouting Work | Sq.Ft | 240.7900 | 240.7900 | 44 | 588769 | 4 | 34080 | D - Flat No. 301 Internal Flat Chemical | [5 empty] | 0.0000
46 | 588771 | D - Flat No. 407 WC,Bath,Balcony Brickbat W/P Work | Sq.Ft | 50.8100 | 50.8100 | 44 | 588769 | 4 | 34081 | D - Flat No. 301 WC,Bath,Balcony Brickba | [5 empty] | 0.0000
47 | 588772 | D - Flat No. 407 WC,Bath,Balcony Chemical W/P Work | Sq.Ft | 50.8100 | 50.8100 | 44 | 588769 | 4 | 34082 | D - Flat No. 301 WC,Bath,Balcony Chemica | [5 empty] | 0.0000
48 | 588773 | D - Flat No. 407 WC,Bath,Balcony IPS W/P Work | Sq.Ft | 50.8100 | 50.8100 | 44 | 588769 | 4 | 34083 | D - Flat No. 301 WC,Bath,Balcony IPS W/P | [5 empty] | 0.0000
49 | 588774 | D- Flat No. 407 WC,Bath,Balcony Door IPS Seal Pack | Flat | 1.0000 | 1.0000 | 44 | 588769 | 4 | 34084 | D- Flat No. 301 WC,Bath,Balcony Door IP | [5 empty] | 0.0000
50 | 588775 | D - Flat No. 407 Bore Packing + Perma Eazee Coat- Flat | No. | 1.0000 | 1.0000 | 44 | 588769 | 4 | 34085 | D - Flat No. 301 Bore Packing + Perma Ea | [5 empty] | 0.0000
51 | 588776 | D - Flat No. 408 | NA | 0.0000 | 0.0000 | 1 | 588726 | 31 | 0 | [6 empty] | 0.0000
52 | 588777 | D - Flat No. 408 Internal Flat Chemical Grouting Work | Sq.Ft | 240.1400 | 240.1400 | 51 | 588776 | 4 | 34080 | D - Flat No. 301 Internal Flat Chemical | [5 empty] | 0.0000
53 | 588778 | D - Flat No. 408 WC,Bath,Balcony Brickbat W/P Work | Sq.Ft | 51.4500 | 51.4500 | 51 | 588776 | 4 | 34081 | D - Flat No. 301 WC,Bath,Balcony Brickba | [5 empty] | 0.0000
54 | 588779 | D - Flat No. 408 WC,Bath,Balcony Chemical W/P Work | Sq.Ft | 51.4500 | 51.4500 | 51 | 588776 | 4 | 34082 | D - Flat No. 301 WC,Bath,Balcony Chemica | [5 empty] | 0.0000
55 | 588780 | D - Flat No. 408 WC,Bath,Balcony IPS W/P Work | Sq.Ft | 51.4500 | 51.4500 | 51 | 588776 | 4 | 34083 | D - Flat No. 301 WC,Bath,Balcony IPS W/P | [5 empty] | 0.0000
56 | 588781 | D- Flat No. 408 WC,Bath,Balcony Door IPS Seal Pack | Flat | 1.0000 | 1.0000 | 51 | 588776 | 4 | 34084 | D- Flat No. 301 WC,Bath,Balcony Door IP | [5 empty] | 0.0000
57 | 588782 | D - Flat No. 408 Bore Packing + Perma Eazee Coat- Flat | No. | 1.0000 | 1.0000 | 51 | 588776 | 4 | 34085 | D - Flat No. 301 Bore Packing + Perma Ea | [5 empty] | 0.0000
58 | 588783 | D - Flat No. 409 | NA | 0.0000 | 0.0000 | 1 | 588726 | 31 | 0 | [6 empty] | 0.0000
59 | 588784 | D - Flat No. 409 Internal Flat Chemical Grouting Work | Sq.Ft | 243.27 | 243.27 | 58 | 588783 | 4 | 34080 | D - Flat No. 301 Internal Flat Chemical | [5 empty] | 0.0000
60 | 588785 | D - Flat No. 409 WC,Bath,Balcony Brickbat W/P Work | Sq.Ft | 52.5300 | 52.5300 | 58 | 588783 | 4 | 34081 | D - Flat No. 301 WC,Bath,Balcony Brickba | [5 empty] | 0.0000
61 | 588786 | D - Flat No. 409 WC,Bath,Balcony Chemical W/P Work | Sq.Ft | 52.5300 | 52.5300 | 58 | 588783 | 4 | 34082 | D - Flat No. 301 WC,Bath,Balcony Chemica | [5 empty] | 0.0000
62 | 588787 | D - Flat No. 409 WC,Bath,Balcony IPS W/P Work | Sq.Ft | 52.5300 | 52.5300 | 58 | 588783 | 4 | 34083 | D - Flat No. 301 WC,Bath,Balcony IPS W/P | [5 empty] | 0.0000
63 | 588788 | D- Flat No. 409 WC,Bath,Balcony Door IPS Seal Pack | Flat | 1.0000 | 1.0000 | 58 | 588783 | 4 | 34084 | D- Flat No. 301 WC,Bath,Balcony Door IP | [5 empty] | 0.0000
64 | 588789 | D - Flat No. 409 Bore Packing + Perma Eazee Coat- Flat | No. | 1.0000 | 1.0000 | 58 | 588783 | 4 | 34085 | D - Flat No. 301 Bore Packing + Perma Ea | [5 empty] | 0.0000
65 | 588790 | D - Flat No. 410 | NA | 0.0000 | 0.0000 | 1 | 588726 | 31 | 0 | [6 empty] | 0.0000
66 | 588791 | D - Flat No. 410 Internal Flat Chemical Grouting Work | Sq.Ft | 244.9900 | 244.9900 | 65 | 588790 | 4 | 34080 | D - Flat No. 301 Internal Flat Chemical | [5 empty] | 0.0000
67 | 588792 | D - Flat No. 410 WC,Bath,Balcony Brickbat W/P Work | Sq.Ft | 53.82 | 53.82 | 65 | 588790 | 4 | 34081 | D - Flat No. 301 WC,Bath,Balcony Brickba | [5 empty] | 0.0000
68 | 588793 | D - Flat No. 410 WC,Bath,Balcony Chemical W/P Work | Sq.Ft | 53.82 | 53.82 | 65 | 588790 | 4 | 34082 | D - Flat No. 301 WC,Bath,Balcony Chemica | [5 empty] | 0.0000
69 | 588794 | D - Flat No. 410 WC,Bath,Balcony IPS W/P Work | Sq.Ft | 53.82 | 53.82 | 65 | 588790 | 4 | 34083 | D - Flat No. 301 WC,Bath,Balcony IPS W/P | [5 empty] | 0.0000
70 | 588795 | D- Flat No. 410 WC,Bath,Balcony Door IPS Seal Pack | Flat | 1.0000 | 1.0000 | 65 | 588790 | 4 | 34084 | D- Flat No. 301 WC,Bath,Balcony Door IP | [5 empty] | 0.0000
71 | 588796 | D - Flat No. 410 Bore Packing + Perma Eazee Coat- Flat | No. | 1.0000 | 1.0000 | 65 | 588790 | 4 | 34085 | D - Flat No. 301 Bore Packing + Perma Ea | [5 empty] | 0.0000
72 | 588797 | D - Flat No. 411 | NA | 0.0000 | 0.0000 | 1 | 588726 | 31 | 0 | [6 empty] | 0.0000
73 | 588798 | D - Flat No. 411 Internal Flat Chemical Grouting Work | Sq.Ft | 245.42 | 245.42 | 72 | 588797 | 4 | 34080 | D - Flat No. 301 Internal Flat Chemical | [5 empty] | 0.0000
74 | 588799 | D - Flat No. 411 WC,Bath,Balcony Brickbat W/P Work | Sq.Ft | 53.07 | 53.07 | 72 | 588797 | 4 | 34081 | D - Flat No. 301 WC,Bath,Balcony Brickba | [5 empty] | 0.0000
75 | 588800 | D - Flat No. 411 WC,Bath,Balcony Chemical W/P Work | Sq.Ft | 53.07 | 53.07 | 72 | 588797 | 4 | 34082 | D - Flat No. 301 WC,Bath,Balcony Chemica | [5 empty] | 0.0000
76 | 588801 | D - Flat No. 411 WC,Bath,Balcony IPS W/P Work | Sq.Ft | 53.07 | 53.07 | 72 | 588797 | 4 | 34083 | D - Flat No. 301 WC,Bath,Balcony IPS W/P | [5 empty] | 0.0000
77 | 588802 | D- Flat No. 411 WC,Bath,Balcony Door IPS Seal Pack | Flat | 1.0000 | 1.0000 | 72 | 588797 | 4 | 34084 | D- Flat No. 301 WC,Bath,Balcony Door IP | [5 empty] | 0.0000
78 | 588803 | D - Flat No. 411 Bore Packing + Perma Eazee Coat- Flat | No. | 1.0000 | 1.0000 | 72 | 588797 | 4 | 34085 | D - Flat No. 301 Bore Packing + Perma Ea | [5 empty] | 0.0000
79 | 588804 | D - Flat No. 412 | NA | 0.0000 | 0.0000 | 1 | 588726 | 31 | 0 | [6 empty] | 0.0000
80 | 588805 | D - Flat No. 412 Internal Flat Chemical Grouting Work | Sq.Ft | 245.53 | 245.53 | 79 | 588804 | 4 | 34080 | D - Flat No. 301 Internal Flat Chemical | [5 empty] | 0.0000
81 | 588806 | D - Flat No. 412 WC,Bath,Balcony Brickbat W/P Work | Sq.Ft | 53.17 | 53.17 | 79 | 588804 | 4 | 34081 | D - Flat No. 301 WC,Bath,Balcony Brickba | [5 empty] | 0.0000
82 | 588807 | D - Flat No. 412 WC,Bath,Balcony Chemical W/P Work | Sq.Ft | 53.17 | 53.17 | 79 | 588804 | 4 | 34082 | D - Flat No. 301 WC,Bath,Balcony Chemica | [5 empty] | 0.0000
83 | 588808 | D - Flat No. 412 WC,Bath,Balcony IPS W/P Work | Sq.Ft | 53.17 | 53.17 | 79 | 588804 | 4 | 34083 | D - Flat No. 301 WC,Bath,Balcony IPS W/P | [5 empty] | 0.0000
84 | 588809 | D- Flat No. 412 WC,Bath,Balcony Door IPS Seal Pack | Flat | 1.0000 | 1.0000 | 79 | 588804 | 4 | 34084 | D- Flat No. 301 WC,Bath,Balcony Door IP | [5 empty] | 0.0000
85 | 588810 | D - Flat No. 412 Bore Packing + Perma Eazee Coat- Flat | No. | 1.0000 | 1.0000 | 79 | 588804 | 4 | 34085 | D - Flat No. 301 Bore Packing + Perma Ea | [5 empty] | 0.0000
86 | 588811 | D - Flat No. 413 | NA | 0.0000 | 0.0000 | 1 | 588726 | 31 | 0 | [6 empty] | 0.0000
87 | 588812 | D - Flat No. 413 Internal Flat Chemical Grouting Work | Sq.Ft | 241.97 | 241.97 | 86 | 588811 | 4 | 34080 | D - Flat No. 301 Internal Flat Chemical | [5 empty] | 0.0000
88 | 588813 | D - Flat No. 413 WC,Bath,Balcony Brickbat W/P Work | Sq.Ft | 51.77 | 51.77 | 86 | 588811 | 4 | 34081 | D - Flat No. 301 WC,Bath,Balcony Brickba | [5 empty] | 0.0000
89 | 588814 | D - Flat No. 413 WC,Bath,Balcony Chemical W/P Work | Sq.Ft | 51.77 | 51.77 | 86 | 588811 | 4 | 34082 | D - Flat No. 301 WC,Bath,Balcony Chemica | [5 empty] | 0.0000
90 | 588815 | D - Flat No. 413 WC,Bath,Balcony IPS W/P Work | Sq.Ft | 51.77 | 51.77 | 86 | 588811 | 4 | 34083 | D - Flat No. 301 WC,Bath,Balcony IPS W/P | [5 empty] | 0.0000
91 | 588816 | D- Flat No. 413 WC,Bath,Balcony Door IPS Seal Pack | Flat | 1.0000 | 1.0000 | 86 | 588811 | 4 | 34084 | D- Flat No. 301 WC,Bath,Balcony Door IP | [5 empty] | 0.0000
92 | 588817 | D - Flat No. 413 Bore Packing + Perma Eazee Coat- Flat | No. | 1.0000 | 1.0000 | 86 | 588811 | 4 | 34085 | D - Flat No. 301 Bore Packing + Perma Ea | [5 empty] | 0.0000
93 | 588818 | D - Flat No. 414 | NA | 0.0000 | 0.0000 | 1 | 588726 | 31 | 0 | [6 empty] | 0.0000
94 | 588819 | D - Flat No. 414 Internal Flat Chemical Grouting Work | Sq.Ft | 242.62 | 242.62 | 93 | 588818 | 4 | 34080 | D - Flat No. 301 Internal Flat Chemical | [5 empty] | 0.0000
95 | 588820 | D - Flat No. 414 WC,Bath,Balcony Brickbat W/P Work | Sq.Ft | 53.39 | 53.39 | 93 | 588818 | 4 | 34081 | D - Flat No. 301 WC,Bath,Balcony Brickba | [5 empty] | 0.0000
96 | 588821 | D - Flat No. 414 WC,Bath,Balcony Chemical W/P Work | Sq.Ft | 53.39 | 53.39 | 93 | 588818 | 4 | 34082 | D - Flat No. 301 WC,Bath,Balcony Chemica | [5 empty] | 0.0000
97 | 588822 | D - Flat No. 414 WC,Bath,Balcony IPS W/P Work | Sq.Ft | 53.39 | 53.39 | 93 | 588818 | 4 | 34083 | D - Flat No. 301 WC,Bath,Balcony IPS W/P | [5 empty] | 0.0000
98 | 588823 | D- Flat No. 414 WC,Bath,Balcony Door IPS Seal Pack | Flat | 1.0000 | 1.0000 | 93 | 588818 | 4 | 34084 | D- Flat No. 301 WC,Bath,Balcony Door IP | [5 empty] | 0.0000
99 | 588824 | D - Flat No. 414 Bore Packing + Perma Eazee Coat- Flat | No. | 1.0000 | 1.0000 | 93 | 588818 | 4 | 34085 | D - Flat No. 301 Bore Packing + Perma Ea | [5 empty] | 0.0000