## Sheet1
Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT
Selected Group :- A Super Structure | Selected Group :- A Super Structure | Selected Group :- A Super Structure | Selected Group :- A Super Structure | Selected Group :- A Super Structure | Selected Group :- A Super Structure | Selected Group :- A Super Structure | Selected Group :- A Super Structure | Selected Group :- A Super Structure | Selected Group :- A Super Structure | Selected Group :- A Super Structure | Selected Group :- A Super Structure | Selected Group :- A Super Structure | Selected Group :- A Super Structure | Selected Group :- A Super Structure | Selected Group :- A Super Structure | Selected Group :- A Super Structure
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 623123 | A Super Structure | NA | 0.0000 | 0.0000 | 0 | 556879 | 31 | 0 | [6 empty] | 0.0000
2 | 623124 | A - Super structure RCC Work (L) | NA | 0.0000 | 0.0000 | 1 | 623123 | 31 | 0 | [6 empty] | 0.0000
3 | 623125 | A - 1st Slab RCC Work (L) | Sq.Ft | 8310.48 | 8310.48 | 2 | 623124 | 4 | 34336 | A - 1st Slab RCC Work (L) | [5 empty] | 0.0000
4 | 623126 | A - 2nd Slab RCC Work (L) | Sq.Ft | 8174.73 | 8174.73 | 2 | 623124 | 4 | 34336 | A - 1st Slab RCC Work (L) | [5 empty] | 0.0000
5 | 623127 | A - 3rd Slab RCC Work (L) | Sq.Ft | 8174.73 | 8174.73 | 2 | 623124 | 4 | 34336 | A - 1st Slab RCC Work (L) | [5 empty] | 0.0000
6 | 623128 | A - 4th Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34378 | A - 4th Slab RCC Work (L) | [5 empty] | 0.0000
7 | 623129 | A - 5th Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
8 | 623130 | A - 6th Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
9 | 623131 | A - 7th Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
10 | 623132 | A - 8th Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
11 | 623133 | A - 9th Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
12 | 623134 | A - 10th Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
13 | 623135 | A - 11th Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
14 | 623136 | A - 12th Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
15 | 623137 | A - 13th Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
16 | 623138 | A - 14th Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
17 | 623139 | A - 15th Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
18 | 623140 | A - 16th Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
19 | 623141 | A - 17th Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
20 | 623142 | A - 18th Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
21 | 623143 | A - 19th Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
22 | 623144 | A - 20th Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
23 | 623145 | A - 21st Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
24 | 623146 | A - 22nd Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
25 | 623147 | A - 23rd Slab RCC Work (L) | Sq.Ft | 5312.87 | 5312.87 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
26 | 623148 | A - 24th Slab RCC Work (L) | Sq.Ft | 5148.4029 | 5148.4029 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
27 | 623149 | A - LMR & OHWT RCC Work (L) | Sq.Ft | 2330.4000 | 2330.4000 | 2 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
28 | 623150 | A - Super Structure Aluform Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 623124 | 4 | 34381 | A - Super Structure Aluform | [5 empty] | 0.0000