## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 0 | C - Plumbing Duct Painting | NA | 0.0000 | 0.0000 | 0 | 0 | 31 | 0 | [6 empty] | 0.0000
2 | 0 | C -Duct 6 External painting Work | NA | 0.0000 | 0.0000 | 1 | 0 | 31 | 0 | [6 empty] | 0.0000
3 | 0 | C -1st Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 0 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
4 | 0 | C -2nd Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 0 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
5 | 0 | C -3rd Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 0 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
6 | 0 | C -4th External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 0 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
7 | 0 | C -5th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 0 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
8 | 0 | C -6th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 0 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
9 | 0 | C -7th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 0 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
10 | 0 | C -8th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 0 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
11 | 0 | C -9th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 0 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
12 | 0 | C -10th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 0 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
13 | 0 | C -11th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 0 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
14 | 0 | C -12th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 0 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
15 | 0 | C -13th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 0 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
16 | 0 | C -14th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 0 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
17 | 0 | C - Terrace Floor External Duct Painting Work | Sq.Ft | 2004.1710 | 2004.1710 | 2 | 0 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000