## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- D - Internal Flat Wall Painting Work | Selected Group :- D - Internal Flat Wall Painting Work | Selected Group :- D - Internal Flat Wall Painting Work | Selected Group :- D - Internal Flat Wall Painting Work | Selected Group :- D - Internal Flat Wall Painting Work | Selected Group :- D - Internal Flat Wall Painting Work | Selected Group :- D - Internal Flat Wall Painting Work | Selected Group :- D - Internal Flat Wall Painting Work | Selected Group :- D - Internal Flat Wall Painting Work | Selected Group :- D - Internal Flat Wall Painting Work | Selected Group :- D - Internal Flat Wall Painting Work | Selected Group :- D - Internal Flat Wall Painting Work | Selected Group :- D - Internal Flat Wall Painting Work | Selected Group :- D - Internal Flat Wall Painting Work | Selected Group :- D - Internal Flat Wall Painting Work | Selected Group :- D - Internal Flat Wall Painting Work | Selected Group :- D - Internal Flat Wall Painting Work
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 646680 | D - Internal Flat Wall Painting Work | NA | 0.0000 | 0.0000 | 0 | 646679 | 31 | 0 | [6 empty] | 0.0000
2 | 646682 | D - 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 646680 | 31 | 0 | [6 empty] | 0.0000
3 | 646683 | D - Flat No. 301 Wall OBD Painting Work | Sq.Ft | 804.9300 | 804.9300 | 2 | 646682 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
4 | 646684 | D - Flat No. 302 Wall OBD Painting Work | Sq.Ft | 804.9300 | 804.9300 | 2 | 646682 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
5 | 646685 | D - Flat No. 303 Wall OBD Painting Work | Sq.Ft | 804.9300 | 804.9300 | 2 | 646682 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
6 | 646686 | D - Flat No. 304 Wall OBD Painting Work | Sq.Ft | 804.9300 | 804.9300 | 2 | 646682 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
7 | 646687 | D - Flat No. 305 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 2 | 646682 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
8 | 646688 | D - Flat No. 306 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 2 | 646682 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
9 | 646689 | D - Flat No. 307 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 2 | 646682 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
10 | 646690 | D - Flat No. 308 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 2 | 646682 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
11 | 646691 | D - Flat No. 309 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 2 | 646682 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
12 | 646692 | D - Flat No. 310 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 2 | 646682 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
13 | 646693 | D - Flat No. 311 Wall OBD Painting Work | Sq.Ft | 804.9300 | 804.9300 | 2 | 646682 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
14 | 646694 | D - Flat No. 312 Wall OBD Painting Work | Sq.Ft | 804.9300 | 804.9300 | 2 | 646682 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
15 | 646695 | D - Flat No. 313 Wall OBD Painting Work | Sq.Ft | 804.9300 | 804.9300 | 2 | 646682 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
16 | 646696 | D - Flat No. 314 Wall OBD Painting Work | Sq.Ft | 804.9300 | 804.9300 | 2 | 646682 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
17 | 646697 | D - 4th Floor | NA | 0.0000 | 0.0000 | 1 | 646680 | 31 | 0 | [6 empty] | 0.0000
18 | 646698 | D - Flat No. 401 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 17 | 646697 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
19 | 646699 | D - Flat No. 402 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 17 | 646697 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
20 | 646700 | D - Flat No. 403 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 17 | 646697 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
21 | 646701 | D - Flat No. 404 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 17 | 646697 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
22 | 646702 | D - Flat No. 405 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 17 | 646697 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
23 | 646703 | D - Flat No. 406 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 17 | 646697 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
24 | 646704 | D - Flat No. 407 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 17 | 646697 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
25 | 646705 | D - Flat No. 408 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 17 | 646697 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
26 | 646706 | D - Flat No. 409 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 17 | 646697 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
27 | 646707 | D - Flat No. 410 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 17 | 646697 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
28 | 646708 | D - Flat No. 411 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 17 | 646697 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
29 | 646709 | D - Flat No. 412 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 17 | 646697 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
30 | 646710 | D - Flat No. 413 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 17 | 646697 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
31 | 646711 | D - Flat No. 414 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 17 | 646697 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
32 | 646712 | D - 5th Floor | NA | 0.0000 | 0.0000 | 1 | 646680 | 31 | 0 | [6 empty] | 0.0000
33 | 646713 | D - Flat No. 501 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 32 | 646712 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
34 | 646714 | D - Flat No. 502 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 32 | 646712 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
35 | 646715 | D - Flat No. 503 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 32 | 646712 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
36 | 646716 | D - Flat No. 504 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 32 | 646712 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
37 | 646717 | D - Flat No. 505 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 32 | 646712 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
38 | 646718 | D - Flat No. 506 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 32 | 646712 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
39 | 646719 | D - Flat No. 507 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 32 | 646712 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
40 | 646720 | D - Flat No. 508 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 32 | 646712 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
41 | 646721 | D - Flat No. 509 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 32 | 646712 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
42 | 646722 | D - Flat No. 510 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 32 | 646712 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
43 | 646723 | D - Flat No. 511 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 32 | 646712 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
44 | 646724 | D - Flat No. 512 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 32 | 646712 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
45 | 646725 | D - Flat No. 513 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 32 | 646712 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
46 | 646726 | D - Flat No. 514 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 32 | 646712 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
47 | 646727 | D - 6th Floor | NA | 0.0000 | 0.0000 | 1 | 646680 | 31 | 0 | [6 empty] | 0.0000
48 | 646728 | D - Flat No. 601 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 47 | 646727 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
49 | 646729 | D - Flat No. 602 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 47 | 646727 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
50 | 646730 | D - Flat No. 603 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 47 | 646727 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
51 | 646731 | D - Flat No. 604 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 47 | 646727 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
52 | 646732 | D - Flat No. 605 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 47 | 646727 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
53 | 646733 | D - Flat No. 606 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 47 | 646727 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
54 | 646734 | D - Flat No. 607 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 47 | 646727 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
55 | 646735 | D - Flat No. 608 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 47 | 646727 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
56 | 646736 | D - Flat No. 609 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 47 | 646727 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
57 | 646737 | D - Flat No. 610 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 47 | 646727 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
58 | 646738 | D - Flat No. 611 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 47 | 646727 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
59 | 646739 | D - Flat No. 612 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 47 | 646727 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
60 | 646740 | D - Flat No. 613 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 47 | 646727 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
61 | 646741 | D - Flat No. 614 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 47 | 646727 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
62 | 646742 | D - 7th Floor | NA | 0.0000 | 0.0000 | 1 | 646680 | 31 | 0 | [6 empty] | 0.0000
63 | 646743 | D - Flat No. 701 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 62 | 646742 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
64 | 646744 | D - Flat No. 702 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 62 | 646742 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
65 | 646745 | D - Flat No. 703 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 62 | 646742 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
66 | 646746 | D - Flat No. 704 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 62 | 646742 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
67 | 646747 | D - Flat No. 705 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 62 | 646742 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
68 | 646748 | D - Flat No. 706 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 62 | 646742 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
69 | 646749 | D - Flat No. 707 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 62 | 646742 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
70 | 646750 | D - Flat No. 708 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 62 | 646742 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
71 | 646751 | D - Flat No. 709 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 62 | 646742 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
72 | 646752 | D - Flat No. 710 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 62 | 646742 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
73 | 646753 | D - Flat No. 711 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 62 | 646742 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
74 | 646754 | D - Flat No. 712 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 62 | 646742 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
75 | 646755 | D - Flat No. 713 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 62 | 646742 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
76 | 646756 | D - Flat No. 714 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 62 | 646742 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
77 | 646757 | D - 8th Floor | NA | 0.0000 | 0.0000 | 1 | 646680 | 31 | 0 | [6 empty] | 0.0000
78 | 646758 | D - Flat No. 801 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 77 | 646757 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
79 | 646759 | D - Flat No. 802 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 77 | 646757 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
80 | 646760 | D - Flat No. 803 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 77 | 646757 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
81 | 646761 | D - Flat No. 804 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 77 | 646757 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
82 | 646762 | D - Flat No. 805 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 77 | 646757 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
83 | 646763 | D - Flat No. 806 Wall OBD Painting Work | Sq.Ft | 0 | 0 | 77 | 646757 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
84 | 646764 | D - Flat No. 807 Wall OBD Painting Work | Sq.Ft | 0 | 0 | 77 | 646757 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
85 | 646765 | D - Flat No. 808 Wall OBD Painting Work | Sq.Ft | 0 | 0 | 77 | 646757 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
86 | 646766 | D - Flat No. 809 Wall OBD Painting Work | Sq.Ft | 0 | 0 | 77 | 646757 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
87 | 646767 | D - Flat No. 810 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 77 | 646757 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
88 | 646768 | D - Flat No. 811 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 77 | 646757 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
89 | 646769 | D - Flat No. 812 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 77 | 646757 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
90 | 646770 | D - Flat No. 813 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 77 | 646757 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
91 | 646771 | D - Flat No. 814 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 77 | 646757 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
92 | 646772 | D - 9th Floor | NA | 0.0000 | 0.0000 | 1 | 646680 | 31 | 0 | [6 empty] | 0.0000
93 | 646773 | D - Flat No. 901 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 92 | 646772 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
94 | 646774 | D - Flat No. 902 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 92 | 646772 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
95 | 646775 | D - Flat No. 903 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 92 | 646772 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
96 | 646776 | D - Flat No. 904 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 92 | 646772 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
97 | 646777 | D - Flat No. 905 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 92 | 646772 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
98 | 646778 | D - Flat No. 906 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 92 | 646772 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
99 | 646779 | D - Flat No. 907 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 92 | 646772 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
100 | 646780 | D - Flat No. 908 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 92 | 646772 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
101 | 646781 | D - Flat No. 909 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 92 | 646772 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
102 | 646782 | D - Flat No. 910 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 92 | 646772 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
103 | 646783 | D - Flat No. 911 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 92 | 646772 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
104 | 646784 | D - Flat No. 912 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 92 | 646772 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
105 | 646785 | D - Flat No. 913 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 92 | 646772 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
106 | 646786 | D - Flat No. 914 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 92 | 646772 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
107 | 646787 | D - 10th Floor | NA | 0.0000 | 0.0000 | 1 | 646680 | 31 | 0 | [6 empty] | 0.0000
108 | 646788 | D - Flat No. 1001 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 107 | 646787 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
109 | 646789 | D - Flat No. 1002 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 107 | 646787 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
110 | 646790 | D - Flat No. 1003 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 107 | 646787 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
111 | 646791 | D - Flat No. 1004 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 107 | 646787 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
112 | 646792 | D - Flat No. 1005 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 107 | 646787 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
113 | 646793 | D - Flat No. 1006 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 107 | 646787 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
114 | 646794 | D - Flat No. 1007 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 107 | 646787 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
115 | 646795 | D - Flat No. 1008 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 107 | 646787 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
116 | 646796 | D - Flat No. 1009 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 107 | 646787 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
117 | 646797 | D - Flat No. 1010 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 107 | 646787 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
118 | 646798 | D - Flat No. 1011 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 107 | 646787 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
119 | 646799 | D - Flat No. 1012 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 107 | 646787 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
120 | 646800 | D - Flat No. 1013 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 107 | 646787 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
121 | 646801 | D - Flat No. 1014 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 107 | 646787 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
122 | 646802 | D - 11th Floor | NA | 0.0000 | 0.0000 | 1 | 646680 | 31 | 0 | [6 empty] | 0.0000
123 | 646803 | D - Flat No. 1101 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 122 | 646802 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
124 | 646804 | D - Flat No. 1102 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 122 | 646802 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
125 | 646805 | D - Flat No. 1103 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 122 | 646802 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
126 | 646806 | D - Flat No. 1104 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 122 | 646802 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
127 | 646807 | D - Flat No. 1105 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 122 | 646802 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
128 | 646808 | D - Flat No. 1106 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 122 | 646802 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
129 | 646809 | D - Flat No. 1107 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 122 | 646802 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
130 | 646810 | D - Flat No. 1108 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 122 | 646802 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
131 | 646811 | D - Flat No. 1109 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 122 | 646802 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
132 | 646812 | D - Flat No. 1110 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 122 | 646802 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
133 | 646813 | D - Flat No. 1111 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 122 | 646802 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
134 | 646814 | D - Flat No. 1112 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 122 | 646802 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
135 | 646815 | D - Flat No. 1113 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 122 | 646802 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
136 | 646816 | D - Flat No. 1114 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 122 | 646802 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
137 | 647133 | D - 12th Floor | NA | 0.0000 | 0.0000 | 1 | 646680 | 31 | 0 | [6 empty] | 0.0000
138 | 647134 | D - Flat No. 1201 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 137 | 647133 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
139 | 647135 | D - Flat No. 1202 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 137 | 647133 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
140 | 647136 | D - Flat No. 1203 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 137 | 647133 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
141 | 647137 | D - Flat No. 1204 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 137 | 647133 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
142 | 647138 | D - Flat No. 1205 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 137 | 647133 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
143 | 647139 | D - Flat No. 1206 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 137 | 647133 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
144 | 647140 | D - Flat No. 1207 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 137 | 647133 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
145 | 647141 | D - Flat No. 1208 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 137 | 647133 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
146 | 647142 | D - Flat No. 1209 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 137 | 647133 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
147 | 647143 | D - Flat No. 1210 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 137 | 647133 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
148 | 647144 | D - Flat No. 1211 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 137 | 647133 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
149 | 647145 | D - Flat No. 1212 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 137 | 647133 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
150 | 647146 | D - Flat No. 1213 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 137 | 647133 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
151 | 647147 | D - Flat No. 1214 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 137 | 647133 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
152 | 646817 | D - 13th Floor | NA | 0.0000 | 0.0000 | 1 | 646680 | 31 | 0 | [6 empty] | 0.0000
153 | 646818 | D - Flat No. 1301 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 152 | 646817 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
154 | 646819 | D - Flat No. 1302 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 152 | 646817 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
155 | 646820 | D - Flat No. 1303 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 152 | 646817 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
156 | 646821 | D - Flat No. 1304 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 152 | 646817 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
157 | 646822 | D - Flat No. 1305 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 152 | 646817 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
158 | 646823 | D - Flat No. 1306 Wall OBD Painting Work | Sq.Ft | 0 | 0 | 152 | 646817 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
159 | 646824 | D - Flat No. 1307 Wall OBD Painting Work | Sq.Ft | 0 | 0 | 152 | 646817 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
160 | 646825 | D - Flat No. 1308 Wall OBD Painting Work | Sq.Ft | 0 | 0 | 152 | 646817 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
161 | 646826 | D - Flat No. 1309 Wall OBD Painting Work | Sq.Ft | 0 | 0 | 152 | 646817 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
162 | 646827 | D - Flat No. 1310 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 152 | 646817 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
163 | 646828 | D - Flat No. 1311 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 152 | 646817 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
164 | 646829 | D - Flat No. 1312 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 152 | 646817 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
165 | 646830 | D - Flat No. 1313 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 152 | 646817 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
166 | 646831 | D - Flat No. 1314 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 152 | 646817 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
167 | 647148 | D - 14th Floor | NA | 0.0000 | 0.0000 | 1 | 646680 | 31 | 0 | [6 empty] | 0.0000
168 | 647149 | D - Flat No. 1401 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 167 | 647148 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
169 | 647150 | D - Flat No. 1402 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 167 | 647148 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
170 | 647151 | D - Flat No. 1403 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 167 | 647148 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
171 | 647152 | D - Flat No. 1404 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 167 | 647148 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
172 | 647153 | D - Flat No. 1405 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 167 | 647148 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
173 | 647154 | D - Flat No. 1406 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 167 | 647148 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
174 | 647155 | D - Flat No. 1407 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 167 | 647148 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
175 | 647156 | D - Flat No. 1408 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 167 | 647148 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
176 | 647157 | D - Flat No. 1409 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 167 | 647148 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
177 | 647158 | D - Flat No. 1410 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 167 | 647148 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
178 | 647159 | D - Flat No. 1411 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 167 | 647148 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
179 | 647160 | D - Flat No. 1412 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 167 | 647148 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
180 | 647161 | D - Flat No. 1413 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 167 | 647148 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000
181 | 647162 | D - Flat No. 1414 Wall OBD Painting Work | Sq.Ft | 792.31 | 792.31 | 167 | 647148 | 4 | 33782 | G- Internal Flat Wall Painting Work | [5 empty] | 0.0000