## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- D - Internal Flat Ceiling Painting Work | Selected Group :- D - Internal Flat Ceiling Painting Work | Selected Group :- D - Internal Flat Ceiling Painting Work | Selected Group :- D - Internal Flat Ceiling Painting Work | Selected Group :- D - Internal Flat Ceiling Painting Work | Selected Group :- D - Internal Flat Ceiling Painting Work | Selected Group :- D - Internal Flat Ceiling Painting Work | Selected Group :- D - Internal Flat Ceiling Painting Work | Selected Group :- D - Internal Flat Ceiling Painting Work | Selected Group :- D - Internal Flat Ceiling Painting Work | Selected Group :- D - Internal Flat Ceiling Painting Work | Selected Group :- D - Internal Flat Ceiling Painting Work | Selected Group :- D - Internal Flat Ceiling Painting Work | Selected Group :- D - Internal Flat Ceiling Painting Work | Selected Group :- D - Internal Flat Ceiling Painting Work | Selected Group :- D - Internal Flat Ceiling Painting Work | Selected Group :- D - Internal Flat Ceiling Painting Work
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 646681 | D - Internal Flat Ceiling Painting Work | NA | 0.0000 | 0.0000 | 0 | 646679 | 31 | 0 | [6 empty] | 0.0000
2 | 646832 | D - 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 646681 | 31 | 0 | [6 empty] | 0.0000
3 | 646833 | D - Flat No. 301 Ceiling OBD Painting Work | Sq.Ft | 281.586 | 281.586 | 2 | 646832 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
4 | 646834 | D - Flat No. 302 Ceiling OBD Painting Work | Sq.Ft | 281.586 | 281.586 | 2 | 646832 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
5 | 646835 | D - Flat No. 303 Ceiling OBD Painting Work | Sq.Ft | 281.586 | 281.586 | 2 | 646832 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
6 | 646836 | D - Flat No. 304 Ceiling OBD Painting Work | Sq.Ft | 281.586 | 281.586 | 2 | 646832 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
7 | 646837 | D - Flat No. 305 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 2 | 646832 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
8 | 646838 | D - Flat No. 306 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 2 | 646832 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
9 | 646839 | D - Flat No. 307 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 2 | 646832 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
10 | 646840 | D - Flat No. 308 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 2 | 646832 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
11 | 646841 | D - Flat No. 309 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 2 | 646832 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
12 | 646842 | D - Flat No. 310 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 2 | 646832 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
13 | 646843 | D - Flat No. 311 Ceiling OBD Painting Work | Sq.Ft | 281.586 | 281.586 | 2 | 646832 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
14 | 646844 | D - Flat No. 312 Ceiling OBD Painting Work | Sq.Ft | 281.586 | 281.586 | 2 | 646832 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
15 | 646845 | D - Flat No. 313 Ceiling OBD Painting Work | Sq.Ft | 281.586 | 281.586 | 2 | 646832 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
16 | 646846 | D - Flat No. 314 Ceiling OBD Painting Work | Sq.Ft | 281.586 | 281.586 | 2 | 646832 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
17 | 646847 | D - 4th Floor | NA | 0.0000 | 0.0000 | 1 | 646681 | 31 | 0 | [6 empty] | 0.0000
18 | 646848 | D - Flat No. 401 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 17 | 646847 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
19 | 646849 | D - Flat No. 402 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 17 | 646847 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
20 | 646850 | D - Flat No. 403 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 17 | 646847 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
21 | 646851 | D - Flat No. 404 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 17 | 646847 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
22 | 646852 | D - Flat No. 405 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 17 | 646847 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
23 | 646853 | D - Flat No. 406 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 17 | 646847 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
24 | 646854 | D - Flat No. 407 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 17 | 646847 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
25 | 646855 | D - Flat No. 408 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 17 | 646847 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
26 | 646856 | D - Flat No. 409 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 17 | 646847 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
27 | 646857 | D - Flat No. 410 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 17 | 646847 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
28 | 646858 | D - Flat No. 411 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 17 | 646847 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
29 | 646859 | D - Flat No. 412 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 17 | 646847 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
30 | 646860 | D - Flat No. 413 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 17 | 646847 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
31 | 646861 | D - Flat No. 414 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 17 | 646847 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
32 | 646862 | D - 5th Floor | NA | 0.0000 | 0.0000 | 1 | 646681 | 31 | 0 | [6 empty] | 0.0000
33 | 646863 | D - Flat No. 501 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 32 | 646862 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
34 | 646864 | D - Flat No. 502 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 32 | 646862 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
35 | 646865 | D - Flat No. 503 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 32 | 646862 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
36 | 646866 | D - Flat No. 504 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 32 | 646862 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
37 | 646867 | D - Flat No. 505 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 32 | 646862 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
38 | 646868 | D - Flat No. 506 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 32 | 646862 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
39 | 646869 | D - Flat No. 507 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 32 | 646862 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
40 | 646870 | D - Flat No. 508 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 32 | 646862 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
41 | 646871 | D - Flat No. 509 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 32 | 646862 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
42 | 646872 | D - Flat No. 510 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 32 | 646862 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
43 | 646873 | D - Flat No. 511 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 32 | 646862 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
44 | 646874 | D - Flat No. 512 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 32 | 646862 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
45 | 646875 | D - Flat No. 513 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 32 | 646862 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
46 | 646876 | D - Flat No. 514 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 32 | 646862 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
47 | 646877 | D - 6th Floor | NA | 0.0000 | 0.0000 | 1 | 646681 | 31 | 0 | [6 empty] | 0.0000
48 | 646878 | D - Flat No. 601 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 47 | 646877 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
49 | 646879 | D - Flat No. 602 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 47 | 646877 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
50 | 646880 | D - Flat No. 603 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 47 | 646877 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
51 | 646881 | D - Flat No. 604 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 47 | 646877 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
52 | 646882 | D - Flat No. 605 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 47 | 646877 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
53 | 646883 | D - Flat No. 606 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 47 | 646877 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
54 | 646884 | D - Flat No. 607 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 47 | 646877 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
55 | 646885 | D - Flat No. 608 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 47 | 646877 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
56 | 646886 | D - Flat No. 609 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 47 | 646877 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
57 | 646887 | D - Flat No. 610 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 47 | 646877 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
58 | 646888 | D - Flat No. 611 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 47 | 646877 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
59 | 646889 | D - Flat No. 612 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 47 | 646877 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
60 | 646890 | D - Flat No. 613 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 47 | 646877 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
61 | 646891 | D - Flat No. 614 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 47 | 646877 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
62 | 646892 | D - 7th Floor | NA | 0.0000 | 0.0000 | 1 | 646681 | 31 | 0 | [6 empty] | 0.0000
63 | 646893 | D - Flat No. 701 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 62 | 646892 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
64 | 646894 | D - Flat No. 702 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 62 | 646892 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
65 | 646895 | D - Flat No. 703 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 62 | 646892 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
66 | 646896 | D - Flat No. 704 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 62 | 646892 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
67 | 646897 | D - Flat No. 705 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 62 | 646892 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
68 | 646898 | D - Flat No. 706 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 62 | 646892 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
69 | 646899 | D - Flat No. 707 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 62 | 646892 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
70 | 646900 | D - Flat No. 708 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 62 | 646892 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
71 | 646901 | D - Flat No. 709 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 62 | 646892 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
72 | 646902 | D - Flat No. 710 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 62 | 646892 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
73 | 646903 | D - Flat No. 711 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 62 | 646892 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
74 | 646904 | D - Flat No. 712 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 62 | 646892 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
75 | 646905 | D - Flat No. 713 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 62 | 646892 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
76 | 646906 | D - Flat No. 714 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 62 | 646892 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
77 | 646907 | D - 8th Floor | NA | 0.0000 | 0.0000 | 1 | 646681 | 31 | 0 | [6 empty] | 0.0000
78 | 646908 | D - Flat No. 801 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 77 | 646907 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
79 | 646909 | D - Flat No. 802 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 77 | 646907 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
80 | 646910 | D - Flat No. 803 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 77 | 646907 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
81 | 646911 | D - Flat No. 804 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 77 | 646907 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
82 | 646912 | D - Flat No. 805 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 77 | 646907 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
83 | 646913 | D - Flat No. 806 Ceiling OBD Painting Work | Sq.Ft | 0 | 0 | 77 | 646907 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
84 | 646914 | D - Flat No. 807 Ceiling OBD Painting Work | Sq.Ft | 0 | 0 | 77 | 646907 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
85 | 646915 | D - Flat No. 808 Ceiling OBD Painting Work | Sq.Ft | 0 | 0 | 77 | 646907 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
86 | 646916 | D - Flat No. 809 Ceiling OBD Painting Work | Sq.Ft | 0 | 0 | 77 | 646907 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
87 | 646917 | D - Flat No. 810 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 77 | 646907 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
88 | 646918 | D - Flat No. 811 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 77 | 646907 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
89 | 646919 | D - Flat No. 812 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 77 | 646907 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
90 | 646920 | D - Flat No. 813 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 77 | 646907 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
91 | 646921 | D - Flat No. 814 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 77 | 646907 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
92 | 646922 | D - 9th Floor | NA | 0.0000 | 0.0000 | 1 | 646681 | 31 | 0 | [6 empty] | 0.0000
93 | 646923 | D - Flat No. 901 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 92 | 646922 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
94 | 646924 | D - Flat No. 902 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 92 | 646922 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
95 | 646925 | D - Flat No. 903 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 92 | 646922 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
96 | 646926 | D - Flat No. 904 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 92 | 646922 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
97 | 646927 | D - Flat No. 905 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 92 | 646922 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
98 | 646928 | D - Flat No. 906 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 92 | 646922 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
99 | 646929 | D - Flat No. 907 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 92 | 646922 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
100 | 646930 | D - Flat No. 908 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 92 | 646922 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
101 | 646931 | D - Flat No. 909 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 92 | 646922 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
102 | 646932 | D - Flat No. 910 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 92 | 646922 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
103 | 646933 | D - Flat No. 911 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 92 | 646922 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
104 | 646934 | D - Flat No. 912 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 92 | 646922 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
105 | 646935 | D - Flat No. 913 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 92 | 646922 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
106 | 646936 | D - Flat No. 914 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 92 | 646922 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
107 | 646937 | D - 10th Floor | NA | 0.0000 | 0.0000 | 1 | 646681 | 31 | 0 | [6 empty] | 0.0000
108 | 646938 | D - Flat No. 1001 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 107 | 646937 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
109 | 646939 | D - Flat No. 1002 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 107 | 646937 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
110 | 646940 | D - Flat No. 1003 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 107 | 646937 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
111 | 646941 | D - Flat No. 1004 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 107 | 646937 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
112 | 646942 | D - Flat No. 1005 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 107 | 646937 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
113 | 646943 | D - Flat No. 1006 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 107 | 646937 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
114 | 646944 | D - Flat No. 1007 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 107 | 646937 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
115 | 646945 | D - Flat No. 1008 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 107 | 646937 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
116 | 646946 | D - Flat No. 1009 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 107 | 646937 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
117 | 646947 | D - Flat No. 1010 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 107 | 646937 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
118 | 646948 | D - Flat No. 1011 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 107 | 646937 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
119 | 646949 | D - Flat No. 1012 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 107 | 646937 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
120 | 646950 | D - Flat No. 1013 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 107 | 646937 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
121 | 646951 | D - Flat No. 1014 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 107 | 646937 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
122 | 646952 | D - 11th Floor | NA | 0.0000 | 0.0000 | 1 | 646681 | 31 | 0 | [6 empty] | 0.0000
123 | 646953 | D - Flat No. 1101 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 122 | 646952 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
124 | 646954 | D - Flat No. 1102 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 122 | 646952 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
125 | 646955 | D - Flat No. 1103 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 122 | 646952 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
126 | 646956 | D - Flat No. 1104 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 122 | 646952 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
127 | 646957 | D - Flat No. 1105 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 122 | 646952 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
128 | 646958 | D - Flat No. 1106 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 122 | 646952 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
129 | 646959 | D - Flat No. 1107 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 122 | 646952 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
130 | 646960 | D - Flat No. 1108 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 122 | 646952 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
131 | 646961 | D - Flat No. 1109 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 122 | 646952 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
132 | 646962 | D - Flat No. 1110 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 122 | 646952 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
133 | 646963 | D - Flat No. 1111 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 122 | 646952 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
134 | 646964 | D - Flat No. 1112 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 122 | 646952 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
135 | 646965 | D - Flat No. 1113 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 122 | 646952 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
136 | 646966 | D - Flat No. 1114 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 122 | 646952 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
137 | 647163 | D - 12th Floor | NA | 0.0000 | 0.0000 | 1 | 646681 | 31 | 0 | [6 empty] | 0.0000
138 | 647164 | D - Flat No. 1201 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 137 | 647163 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
139 | 647165 | D - Flat No. 1202 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 137 | 647163 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
140 | 647166 | D - Flat No. 1203 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 137 | 647163 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
141 | 647167 | D - Flat No. 1204 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 137 | 647163 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
142 | 647168 | D - Flat No. 1205 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 137 | 647163 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
143 | 647169 | D - Flat No. 1206 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 137 | 647163 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
144 | 647170 | D - Flat No. 1207 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 137 | 647163 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
145 | 647171 | D - Flat No. 1208 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 137 | 647163 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
146 | 647172 | D - Flat No. 1209 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 137 | 647163 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
147 | 647173 | D - Flat No. 1210 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 137 | 647163 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
148 | 647174 | D - Flat No. 1211 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 137 | 647163 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
149 | 647175 | D - Flat No. 1212 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 137 | 647163 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
150 | 647176 | D - Flat No. 1213 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 137 | 647163 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
151 | 647177 | D - Flat No. 1214 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 137 | 647163 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
152 | 646967 | D - 13th Floor | NA | 0.0000 | 0.0000 | 1 | 646681 | 31 | 0 | [6 empty] | 0.0000
153 | 646968 | D - Flat No. 1301 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 152 | 646967 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
154 | 646969 | D - Flat No. 1302 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 152 | 646967 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
155 | 646970 | D - Flat No. 1303 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 152 | 646967 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
156 | 646971 | D - Flat No. 1304 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 152 | 646967 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
157 | 646972 | D - Flat No. 1305 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 152 | 646967 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
158 | 646973 | D - Flat No. 1306 Ceiling OBD Painting Work | Sq.Ft | 0 | 0 | 152 | 646967 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
159 | 646974 | D - Flat No. 1307 Ceiling OBD Painting Work | Sq.Ft | 0 | 0 | 152 | 646967 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
160 | 646975 | D - Flat No. 1308 Ceiling OBD Painting Work | Sq.Ft | 0 | 0 | 152 | 646967 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
161 | 646976 | D - Flat No. 1309 Ceiling OBD Painting Work | Sq.Ft | 0 | 0 | 152 | 646967 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
162 | 646977 | D - Flat No. 1310 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 152 | 646967 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
163 | 646978 | D - Flat No. 1311 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 152 | 646967 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
164 | 646979 | D - Flat No. 1312 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 152 | 646967 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
165 | 646980 | D - Flat No. 1313 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 152 | 646967 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
166 | 646981 | D - Flat No. 1314 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 152 | 646967 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
167 | 647178 | D - 14th Floor | NA | 0.0000 | 0.0000 | 1 | 646681 | 31 | 0 | [6 empty] | 0.0000
168 | 647179 | D - Flat No. 1401 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 167 | 647178 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
169 | 647180 | D - Flat No. 1402 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 167 | 647178 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
170 | 647181 | D - Flat No. 1403 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 167 | 647178 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
171 | 647182 | D - Flat No. 1404 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 167 | 647178 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
172 | 647183 | D - Flat No. 1405 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 167 | 647178 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
173 | 647184 | D - Flat No. 1406 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 167 | 647178 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
174 | 647185 | D - Flat No. 1407 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 167 | 647178 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
175 | 647186 | D - Flat No. 1408 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 167 | 647178 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
176 | 647187 | D - Flat No. 1409 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 167 | 647178 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
177 | 647188 | D - Flat No. 1410 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 167 | 647178 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
178 | 647189 | D - Flat No. 1411 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 167 | 647178 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
179 | 647190 | D - Flat No. 1412 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 167 | 647178 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
180 | 647191 | D - Flat No. 1413 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 167 | 647178 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000
181 | 647192 | D - Flat No. 1414 Ceiling OBD Painting Work | Sq.Ft | 262.857 | 262.857 | 167 | 647178 | 4 | 33785 | G- Internal Flat Ceiling Painting Work | [5 empty] | 0.0000