## Sheet1
Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW
Selected Group :- Staircase Landing Flooring & Skirting Work | Selected Group :- Staircase Landing Flooring & Skirting Work | Selected Group :- Staircase Landing Flooring & Skirting Work | Selected Group :- Staircase Landing Flooring & Skirting Work | Selected Group :- Staircase Landing Flooring & Skirting Work | Selected Group :- Staircase Landing Flooring & Skirting Work | Selected Group :- Staircase Landing Flooring & Skirting Work | Selected Group :- Staircase Landing Flooring & Skirting Work | Selected Group :- Staircase Landing Flooring & Skirting Work | Selected Group :- Staircase Landing Flooring & Skirting Work | Selected Group :- Staircase Landing Flooring & Skirting Work | Selected Group :- Staircase Landing Flooring & Skirting Work | Selected Group :- Staircase Landing Flooring & Skirting Work | Selected Group :- Staircase Landing Flooring & Skirting Work | Selected Group :- Staircase Landing Flooring & Skirting Work | Selected Group :- Staircase Landing Flooring & Skirting Work | Selected Group :- Staircase Landing Flooring & Skirting Work
Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters] | Task Qty [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 667599 | Staircase Landing Flooring & Skirting Work | NA | 0.0000 | 0.0000 | 0 | 500599 | 31 | 0 | [6 empty] | 0.0000
2 | 667600 | Staircase 1 | NA | 0.0000 | 0.0000 | 1 | 667599 | 31 | 0 | [6 empty] | 0.0000
3 | 667601 | A - Ground Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
4 | 667602 | A - Ground Floor Staircase 1 Flooring Work | Sq.Ft | 95.7990 | 95.7990 | 3 | 667601 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
5 | 667603 | A - Ground Floor Staircase 1 Skirting Work | Sq.Ft | 11.431 | 11.431 | 3 | 667601 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
6 | 667604 | A - 1st Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
7 | 667605 | A - 1st Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 6 | 667604 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
8 | 667606 | A - 1st Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 6 | 667604 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
9 | 668049 | A - 2nd Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
10 | 668050 | A - 2nd Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 9 | 668049 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
11 | 668051 | A - 2nd Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 9 | 668049 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
12 | 668052 | A - 3rd Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
13 | 668053 | A - 3rd Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 12 | 668052 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
14 | 668054 | A - 3rd Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 12 | 668052 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
15 | 668055 | A - 4th Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
16 | 668056 | A - 4th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 15 | 668055 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
17 | 668057 | A - 4th Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 15 | 668055 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
18 | 668058 | A - 5th Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
19 | 668059 | A - 5th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 18 | 668058 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
20 | 668060 | A - 5th Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 18 | 668058 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
21 | 668061 | A - 6th Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
22 | 668062 | A - 6th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 21 | 668061 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
23 | 668063 | A - 6th Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 21 | 668061 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
24 | 668064 | A - 7th Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
25 | 668065 | A - 7th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 24 | 668064 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
26 | 668066 | A - 7th Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 24 | 668064 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
27 | 668067 | A - 8th Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
28 | 668068 | A - 8th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 27 | 668067 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
29 | 668069 | A - 8th Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 27 | 668067 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
30 | 668070 | A - 9th Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
31 | 668071 | A - 9th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 30 | 668070 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
32 | 668072 | A - 9th Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 30 | 668070 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
33 | 668073 | A - 10th Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
34 | 668074 | A - 10th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 33 | 668073 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
35 | 668075 | A - 10th Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 33 | 668073 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
36 | 668076 | A - 11th Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
37 | 668077 | A - 11th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 36 | 668076 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
38 | 668078 | A - 11th Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 36 | 668076 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
39 | 668079 | A - 12th Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
40 | 668080 | A - 12th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 39 | 668079 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
41 | 668081 | A - 12th Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 39 | 668079 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
42 | 668082 | A - 13th Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
43 | 668083 | A - 13th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 42 | 668082 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
44 | 668084 | A - 13th Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 42 | 668082 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
45 | 668085 | A - 14th Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
46 | 668086 | A - 14th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 45 | 668085 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
47 | 668087 | A - 14th Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 45 | 668085 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
48 | 668088 | A - 15th Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
49 | 668089 | A - 15thFloor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 48 | 668088 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
50 | 668090 | A - 15th Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 48 | 668088 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
51 | 668091 | A - 16th Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
52 | 668092 | A - 16th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 51 | 668091 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
53 | 668093 | A - 16th Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 51 | 668091 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
54 | 668094 | A - 17th Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
55 | 668095 | A - 17th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 54 | 668094 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
56 | 668096 | A - 17th Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 54 | 668094 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
57 | 668097 | A - 18th Floor | NA | 0.0000 | 0.0000 | 2 | 667600 | 31 | 0 | [6 empty] | 0.0000
58 | 668098 | A - 18th Floor Staircase 1 Flooring Work | Sq.Ft | 96.9830 | 96.9830 | 57 | 668097 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
59 | 668099 | A - 18th Floor Staircase 1 Skirting Work | Sq.Ft | 11.356 | 11.356 | 57 | 668097 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
60 | 668100 | Staircase 2 | NA | 0.0000 | 0.0000 | 1 | 667599 | 31 | 0 | [6 empty] | 0.0000
61 | 668101 | A - Ground Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
62 | 668102 | A - Ground Floor Staircase 2 Flooring Work | Sq.Ft | 99.4590 | 99.4590 | 61 | 668101 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
63 | 668103 | A - Ground Floor Staircase 2 Skirting Work | Sq.Ft | 15.123 | 15.123 | 61 | 668101 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
64 | 668104 | A - 1st Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
65 | 668105 | A - 1st Floor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 64 | 668104 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
66 | 668106 | A - 1st Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 64 | 668104 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
67 | 668107 | A - 2nd Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
68 | 668108 | A - 2nd Floor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 67 | 668107 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
69 | 668109 | A - 2nd Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 67 | 668107 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
70 | 668110 | A - 3rd Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
71 | 668111 | A - 3rd Floor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 70 | 668110 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
72 | 668112 | A - 3rd Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 70 | 668110 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
73 | 668113 | A - 4th Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
74 | 668114 | A - 4th Floor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 73 | 668113 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
75 | 668115 | A - 4th Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 73 | 668113 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
76 | 668116 | A - 5th Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
77 | 668117 | A - 5th Floor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 76 | 668116 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
78 | 668118 | A - 5th Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 76 | 668116 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
79 | 668119 | A - 6th Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
80 | 668120 | A - 6th Floor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 79 | 668119 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
81 | 668121 | A - 6th Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 79 | 668119 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
82 | 668122 | A - 7th Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
83 | 668123 | A - 7th Floor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 82 | 668122 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
84 | 668124 | A - 7th Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 82 | 668122 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
85 | 668125 | A - 8th Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
86 | 668126 | A - 8th Floor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 85 | 668125 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
87 | 668127 | A - 8th Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 85 | 668125 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
88 | 668128 | A - 9th Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
89 | 668129 | A - 9th Floor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 88 | 668128 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
90 | 668130 | A - 9th Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 88 | 668128 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
91 | 668131 | A - 10th Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
92 | 668132 | A - 10th Floor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 91 | 668131 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
93 | 668133 | A - 10th Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 91 | 668131 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
94 | 668134 | A - 11th Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
95 | 668135 | A - 11th Floor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 94 | 668134 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
96 | 668136 | A - 11th Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 94 | 668134 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
97 | 668137 | A - 12th Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
98 | 668138 | A - 12th Floor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 97 | 668137 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
99 | 668139 | A - 12th Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 97 | 668137 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
100 | 668140 | A - 13th Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
101 | 668141 | A - 13th Floor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 100 | 668140 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
102 | 668142 | A - 13th Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 100 | 668140 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
103 | 668143 | A - 14th Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
104 | 668144 | A - 14th Floor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 103 | 668143 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
105 | 668145 | A - 14th Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 103 | 668143 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
106 | 668146 | A - 15th Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
107 | 668147 | A - 15thFloor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 106 | 668146 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
108 | 668148 | A - 15th Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 106 | 668146 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
109 | 668149 | A - 16th Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
110 | 668150 | A - 16th Floor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 109 | 668149 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
111 | 668151 | A - 16th Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 109 | 668149 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
112 | 668152 | A - 17th Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
113 | 668153 | A - 17th Floor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 112 | 668152 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
114 | 668154 | A - 17th Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 112 | 668152 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000
115 | 668155 | A - 18th Floor | NA | 0.0000 | 0.0000 | 60 | 668100 | 31 | 0 | [6 empty] | 0.0000
116 | 668156 | A - 18th Floor Staircase 2 Flooring Work | Sq.Ft | 50.1600 | 50.1600 | 115 | 668155 | 4 | 34763 | A - Ground Floor Staircase 1 Flooring Work | [5 empty] | 0.0000
117 | 668157 | A - 18th Floor Staircase 2 Skirting Work | Sq.Ft | 6.62 | 6.62 | 115 | 668155 | 4 | 34764 | A - Ground Floor Staircase 1 Skirting Work | [5 empty] | 0.0000