## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - Dado Work | Selected Group :- C - Dado Work | Selected Group :- C - Dado Work | Selected Group :- C - Dado Work | Selected Group :- C - Dado Work | Selected Group :- C - Dado Work | Selected Group :- C - Dado Work | Selected Group :- C - Dado Work | Selected Group :- C - Dado Work | Selected Group :- C - Dado Work | Selected Group :- C - Dado Work | Selected Group :- C - Dado Work | Selected Group :- C - Dado Work | Selected Group :- C - Dado Work | Selected Group :- C - Dado Work | Selected Group :- C - Dado Work | Selected Group :- C - Dado Work
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 564157 | C - Dado Work | NA | 0.0000 | 0.0000 | 0 | 540541 | 31 | 0 | [6 empty] | 0.0000
2 | 564158 | C - 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 564157 | 31 | 0 | [6 empty] | 0.0000
3 | 564159 | C - 301 Dado Work | NA | 0.0000 | 0.0000 | 2 | 564158 | 31 | 0 | [6 empty] | 0.0000
4 | 564160 | C- 301 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 3 | 564159 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
5 | 564161 | C- 301 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 3 | 564159 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
6 | 564162 | C- 301 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 3 | 564159 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
7 | 564163 | C - 302 Dado Work | NA | 0.0000 | 0.0000 | 2 | 564158 | 31 | 0 | [6 empty] | 0.0000
8 | 564164 | C. 302 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 7 | 564163 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
9 | 564165 | C. 302 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 7 | 564163 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
10 | 564166 | C. 302 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 7 | 564163 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
11 | 564167 | C - 303 Dado Work | NA | 0.0000 | 0.0000 | 2 | 564158 | 31 | 0 | [6 empty] | 0.0000
12 | 564168 | C. 303 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 11 | 564167 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
13 | 564169 | C. 303 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 11 | 564167 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
14 | 564170 | C. 303 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 11 | 564167 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
15 | 564171 | C - 304 Dado Work | NA | 0.0000 | 0.0000 | 2 | 564158 | 31 | 0 | [6 empty] | 0.0000
16 | 564172 | C. 304 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 15 | 564171 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
17 | 564173 | C. 304 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 15 | 564171 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
18 | 564174 | C. 304 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 15 | 564171 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
19 | 564175 | C - 305 Dado Work | NA | 0.0000 | 0.0000 | 2 | 564158 | 31 | 0 | [6 empty] | 0.0000
20 | 564176 | C. 305 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 19 | 564175 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
21 | 564177 | C. 305 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 19 | 564175 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
22 | 564178 | C. 305 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 19 | 564175 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
23 | 564179 | C - 306 Dado Work | NA | 0.0000 | 0.0000 | 2 | 564158 | 31 | 0 | [6 empty] | 0.0000
24 | 564180 | C. 306 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 23 | 564179 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
25 | 564181 | C. 306 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 23 | 564179 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
26 | 564182 | C. 306 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 23 | 564179 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
27 | 564183 | C - 307 Dado Work | NA | 0.0000 | 0.0000 | 2 | 564158 | 31 | 0 | [6 empty] | 0.0000
28 | 564184 | C. 307 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 27 | 564183 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
29 | 564185 | C. 307 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 27 | 564183 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
30 | 564186 | C. 307 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 27 | 564183 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
31 | 564187 | C - 308 Dado Work | NA | 0.0000 | 0.0000 | 2 | 564158 | 31 | 0 | [6 empty] | 0.0000
32 | 564188 | C. 308 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 31 | 564187 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
33 | 564189 | C. 308 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 31 | 564187 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
34 | 564190 | C. 308 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 31 | 564187 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
35 | 564191 | C - 309 Dado Work | NA | 0.0000 | 0.0000 | 2 | 564158 | 31 | 0 | [6 empty] | 0.0000
36 | 564192 | C. 309 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 35 | 564191 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
37 | 564193 | C. 309 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 35 | 564191 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
38 | 564194 | C. 309 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 35 | 564191 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
39 | 564195 | C - 310 Dado Work | NA | 0.0000 | 0.0000 | 2 | 564158 | 31 | 0 | [6 empty] | 0.0000
40 | 564196 | C. 310 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 39 | 564195 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
41 | 564197 | C. 310 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 39 | 564195 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
42 | 564198 | C. 310 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 39 | 564195 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
43 | 564199 | C - 311 Dado Work | NA | 0.0000 | 0.0000 | 2 | 564158 | 31 | 0 | [6 empty] | 0.0000
44 | 564200 | C. 311 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 43 | 564199 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
45 | 564201 | C. 311 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 43 | 564199 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
46 | 564202 | C. 311 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 43 | 564199 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
47 | 564203 | C - 312 Dado Work | NA | 0.0000 | 0.0000 | 2 | 564158 | 31 | 0 | [6 empty] | 0.0000
48 | 564204 | C. 312 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 47 | 564203 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
49 | 564205 | C. 312 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 47 | 564203 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
50 | 564206 | C. 312 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 47 | 564203 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
51 | 564207 | C - 313 Dado Work | NA | 0.0000 | 0.0000 | 2 | 564158 | 31 | 0 | [6 empty] | 0.0000
52 | 564208 | C. 313 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 51 | 564207 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
53 | 564209 | C. 313 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 51 | 564207 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
54 | 564210 | C. 313 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 51 | 564207 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
55 | 564211 | C - 314 Dado Work | NA | 0.0000 | 0.0000 | 2 | 564158 | 31 | 0 | [6 empty] | 0.0000
56 | 564212 | C. 314 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 55 | 564211 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
57 | 564213 | C. 314 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 55 | 564211 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
58 | 564214 | C. 314 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 55 | 564211 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
59 | 564215 | C - 4th Floor | NA | 0.0000 | 0.0000 | 1 | 564157 | 31 | 0 | [6 empty] | 0.0000
60 | 564216 | C - 401 Dado Work | NA | 0.0000 | 0.0000 | 59 | 564215 | 31 | 0 | [6 empty] | 0.0000
61 | 564217 | C- 401 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 60 | 564216 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
62 | 564218 | C- 401 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 60 | 564216 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
63 | 564219 | C- 401 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 60 | 564216 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
64 | 564220 | C - 402 Dado Work | NA | 0.0000 | 0.0000 | 59 | 564215 | 31 | 0 | [6 empty] | 0.0000
65 | 564221 | C. 402 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 64 | 564220 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
66 | 564222 | C. 402 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 64 | 564220 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
67 | 564223 | C. 402 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 64 | 564220 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
68 | 564224 | C - 403 Dado Work | NA | 0.0000 | 0.0000 | 59 | 564215 | 31 | 0 | [6 empty] | 0.0000
69 | 564225 | C. 403 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 68 | 564224 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
70 | 564226 | C. 403 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 68 | 564224 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
71 | 564227 | C. 403 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 68 | 564224 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
72 | 564228 | C - 404 Dado Work | NA | 0.0000 | 0.0000 | 59 | 564215 | 31 | 0 | [6 empty] | 0.0000
73 | 564229 | C. 404 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 72 | 564228 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
74 | 564230 | C. 404 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 72 | 564228 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
75 | 564231 | C. 404 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 72 | 564228 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
76 | 564232 | C - 405 Dado Work | NA | 0.0000 | 0.0000 | 59 | 564215 | 31 | 0 | [6 empty] | 0.0000
77 | 564233 | C. 405 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 76 | 564232 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
78 | 564234 | C. 405 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 76 | 564232 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
79 | 564235 | C. 405 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 76 | 564232 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
80 | 564236 | C - 406 Dado Work | NA | 0.0000 | 0.0000 | 59 | 564215 | 31 | 0 | [6 empty] | 0.0000
81 | 564237 | C. 406 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 80 | 564236 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
82 | 564238 | C. 406 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 80 | 564236 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
83 | 564239 | C. 406 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 80 | 564236 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
84 | 564240 | C - 407 Dado Work | NA | 0.0000 | 0.0000 | 59 | 564215 | 31 | 0 | [6 empty] | 0.0000
85 | 564241 | C. 407 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 84 | 564240 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
86 | 564242 | C. 407 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 84 | 564240 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
87 | 564243 | C. 407 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 84 | 564240 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
88 | 564244 | C - 408 Dado Work | NA | 0.0000 | 0.0000 | 59 | 564215 | 31 | 0 | [6 empty] | 0.0000
89 | 564245 | C. 408 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 88 | 564244 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
90 | 564246 | C. 408 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 88 | 564244 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
91 | 564247 | C. 408 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 88 | 564244 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
92 | 564248 | C - 409 Dado Work | NA | 0.0000 | 0.0000 | 59 | 564215 | 31 | 0 | [6 empty] | 0.0000
93 | 564249 | C. 409 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 92 | 564248 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
94 | 564250 | C. 409 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 92 | 564248 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
95 | 564251 | C. 409 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 92 | 564248 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
96 | 564252 | C - 410 Dado Work | NA | 0.0000 | 0.0000 | 59 | 564215 | 31 | 0 | [6 empty] | 0.0000
97 | 564253 | C. 410 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 96 | 564252 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
98 | 564254 | C. 410 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 96 | 564252 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
99 | 564255 | C. 410 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 96 | 564252 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
100 | 564256 | C - 411 Dado Work | NA | 0.0000 | 0.0000 | 59 | 564215 | 31 | 0 | [6 empty] | 0.0000
101 | 564257 | C. 411 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 100 | 564256 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
102 | 564258 | C. 411 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 100 | 564256 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
103 | 564259 | C. 411 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 100 | 564256 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
104 | 564260 | C - 412 Dado Work | NA | 0.0000 | 0.0000 | 59 | 564215 | 31 | 0 | [6 empty] | 0.0000
105 | 564261 | C. 412 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 104 | 564260 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
106 | 564262 | C. 412 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 104 | 564260 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
107 | 564263 | C. 412 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 104 | 564260 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
108 | 564264 | C - 413 Dado Work | NA | 0.0000 | 0.0000 | 59 | 564215 | 31 | 0 | [6 empty] | 0.0000
109 | 564265 | C. 413 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 564264 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
110 | 564266 | C. 413 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 564264 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
111 | 564267 | C. 413 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 564264 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
112 | 564268 | C - 414 Dado Work | NA | 0.0000 | 0.0000 | 59 | 564215 | 31 | 0 | [6 empty] | 0.0000
113 | 564269 | C. 414 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 112 | 564268 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
114 | 564270 | C. 414 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 112 | 564268 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
115 | 564271 | C. 414 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 112 | 564268 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
116 | 564272 | C - 5th Floor | NA | 0.0000 | 0.0000 | 1 | 564157 | 31 | 0 | [6 empty] | 0.0000
117 | 564273 | C - 501 Dado Work | NA | 0.0000 | 0.0000 | 116 | 564272 | 31 | 0 | [6 empty] | 0.0000
118 | 564274 | C- 501 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 117 | 564273 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
119 | 564275 | C- 501 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 117 | 564273 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
120 | 564276 | C- 501 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 117 | 564273 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
121 | 564277 | C - 502 Dado Work | NA | 0.0000 | 0.0000 | 116 | 564272 | 31 | 0 | [6 empty] | 0.0000
122 | 564278 | C. 502 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 121 | 564277 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
123 | 564279 | C. 502 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 121 | 564277 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
124 | 564280 | C. 502 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 121 | 564277 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
125 | 564281 | C - 503 Dado Work | NA | 0.0000 | 0.0000 | 116 | 564272 | 31 | 0 | [6 empty] | 0.0000
126 | 564282 | C. 503 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 125 | 564281 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
127 | 564283 | C. 503 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 125 | 564281 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
128 | 564284 | C. 503 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 125 | 564281 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
129 | 564285 | C - 504 Dado Work | NA | 0.0000 | 0.0000 | 116 | 564272 | 31 | 0 | [6 empty] | 0.0000
130 | 564286 | C. 504 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 129 | 564285 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
131 | 564287 | C. 504 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 129 | 564285 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
132 | 564288 | C. 504 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 129 | 564285 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
133 | 564289 | C - 505 Dado Work | NA | 0.0000 | 0.0000 | 116 | 564272 | 31 | 0 | [6 empty] | 0.0000
134 | 564290 | C. 505 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 133 | 564289 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
135 | 564291 | C. 505 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 133 | 564289 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
136 | 564292 | C. 505 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 133 | 564289 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
137 | 564293 | C - 506 Dado Work | NA | 0.0000 | 0.0000 | 116 | 564272 | 31 | 0 | [6 empty] | 0.0000
138 | 564294 | C. 506 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 137 | 564293 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
139 | 564295 | C. 506 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 137 | 564293 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
140 | 564296 | C. 506 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 137 | 564293 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
141 | 564297 | C - 507 Dado Work | NA | 0.0000 | 0.0000 | 116 | 564272 | 31 | 0 | [6 empty] | 0.0000
142 | 564298 | C. 507 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 141 | 564297 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
143 | 564299 | C. 507 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 141 | 564297 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
144 | 564300 | C. 507 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 141 | 564297 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
145 | 564301 | C - 508 Dado Work | NA | 0.0000 | 0.0000 | 116 | 564272 | 31 | 0 | [6 empty] | 0.0000
146 | 564302 | C. 508 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 145 | 564301 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
147 | 564303 | C. 508 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 145 | 564301 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
148 | 564304 | C. 508 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 145 | 564301 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
149 | 564305 | C - 509 Dado Work | NA | 0.0000 | 0.0000 | 116 | 564272 | 31 | 0 | [6 empty] | 0.0000
150 | 564306 | C. 509 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 149 | 564305 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
151 | 564307 | C. 509 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 149 | 564305 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
152 | 564308 | C. 509 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 149 | 564305 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
153 | 564309 | C - 510 Dado Work | NA | 0.0000 | 0.0000 | 116 | 564272 | 31 | 0 | [6 empty] | 0.0000
154 | 564310 | C. 510 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 153 | 564309 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
155 | 564311 | C. 510 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 153 | 564309 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
156 | 564312 | C. 510 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 153 | 564309 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
157 | 564313 | C - 511 Dado Work | NA | 0.0000 | 0.0000 | 116 | 564272 | 31 | 0 | [6 empty] | 0.0000
158 | 564314 | C. 511 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 157 | 564313 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
159 | 564315 | C. 511 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 157 | 564313 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
160 | 564316 | C. 511 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 157 | 564313 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
161 | 564317 | C - 512 Dado Work | NA | 0.0000 | 0.0000 | 116 | 564272 | 31 | 0 | [6 empty] | 0.0000
162 | 564318 | C. 512 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 161 | 564317 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
163 | 564319 | C. 512 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 161 | 564317 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
164 | 564320 | C. 512 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 161 | 564317 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
165 | 564321 | C - 513 Dado Work | NA | 0.0000 | 0.0000 | 116 | 564272 | 31 | 0 | [6 empty] | 0.0000
166 | 564322 | C. 513 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 165 | 564321 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
167 | 564323 | C. 513 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 165 | 564321 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
168 | 564324 | C. 513 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 165 | 564321 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
169 | 564325 | C - 514 Dado Work | NA | 0.0000 | 0.0000 | 116 | 564272 | 31 | 0 | [6 empty] | 0.0000
170 | 564326 | C. 514 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 169 | 564325 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
171 | 564327 | C. 514 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 169 | 564325 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
172 | 564328 | C. 514 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 169 | 564325 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
173 | 564332 | C - 6th Floor | NA | 0.0000 | 0.0000 | 1 | 564157 | 31 | 0 | [6 empty] | 0.0000
174 | 564333 | C - 601 Dado Work | NA | 0.0000 | 0.0000 | 173 | 564332 | 31 | 0 | [6 empty] | 0.0000
175 | 564334 | C- 601 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 174 | 564333 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
176 | 564335 | C- 601 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 174 | 564333 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
177 | 564336 | C- 601 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 174 | 564333 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
178 | 564337 | C - 602 Dado Work | NA | 0.0000 | 0.0000 | 173 | 564332 | 31 | 0 | [6 empty] | 0.0000
179 | 564338 | C. 602 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 178 | 564337 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
180 | 564339 | C. 602 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 178 | 564337 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
181 | 564340 | C. 602 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 178 | 564337 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
182 | 564341 | C - 603 Dado Work | NA | 0.0000 | 0.0000 | 173 | 564332 | 31 | 0 | [6 empty] | 0.0000
183 | 564342 | C. 603 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 182 | 564341 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
184 | 564343 | C. 603 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 182 | 564341 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
185 | 564344 | C. 603 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 182 | 564341 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
186 | 564345 | C - 604 Dado Work | NA | 0.0000 | 0.0000 | 173 | 564332 | 31 | 0 | [6 empty] | 0.0000
187 | 564346 | C. 604 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 186 | 564345 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
188 | 564347 | C. 604 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 186 | 564345 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
189 | 564348 | C. 604 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 186 | 564345 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
190 | 564349 | C - 605 Dado Work | NA | 0.0000 | 0.0000 | 173 | 564332 | 31 | 0 | [6 empty] | 0.0000
191 | 564350 | C. 605 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 190 | 564349 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
192 | 564351 | C. 605 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 190 | 564349 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
193 | 564352 | C. 605 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 190 | 564349 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
194 | 564353 | C - 606 Dado Work | NA | 0.0000 | 0.0000 | 173 | 564332 | 31 | 0 | [6 empty] | 0.0000
195 | 564354 | C. 606 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 194 | 564353 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
196 | 564355 | C. 606 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 194 | 564353 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
197 | 564356 | C. 606 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 194 | 564353 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
198 | 564357 | C - 607 Dado Work | NA | 0.0000 | 0.0000 | 173 | 564332 | 31 | 0 | [6 empty] | 0.0000
199 | 564358 | C. 607 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 198 | 564357 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
200 | 564359 | C. 607 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 198 | 564357 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
201 | 564360 | C. 607 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 198 | 564357 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
202 | 564361 | C - 608 Dado Work | NA | 0.0000 | 0.0000 | 173 | 564332 | 31 | 0 | [6 empty] | 0.0000
203 | 564362 | C. 608 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 202 | 564361 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
204 | 564363 | C. 608 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 202 | 564361 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
205 | 564364 | C. 608 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 202 | 564361 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
206 | 564365 | C - 609 Dado Work | NA | 0.0000 | 0.0000 | 173 | 564332 | 31 | 0 | [6 empty] | 0.0000
207 | 564366 | C. 609 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 206 | 564365 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
208 | 564367 | C. 609 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 206 | 564365 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
209 | 564368 | C. 609 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 206 | 564365 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
210 | 564369 | C - 610 Dado Work | NA | 0.0000 | 0.0000 | 173 | 564332 | 31 | 0 | [6 empty] | 0.0000
211 | 564370 | C. 610 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 210 | 564369 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
212 | 564371 | C. 610 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 210 | 564369 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
213 | 564372 | C. 610 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 210 | 564369 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
214 | 564373 | C - 611 Dado Work | NA | 0.0000 | 0.0000 | 173 | 564332 | 31 | 0 | [6 empty] | 0.0000
215 | 564374 | C. 611 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 214 | 564373 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
216 | 564375 | C. 611 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 214 | 564373 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
217 | 564376 | C. 611 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 214 | 564373 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
218 | 564377 | C - 612 Dado Work | NA | 0.0000 | 0.0000 | 173 | 564332 | 31 | 0 | [6 empty] | 0.0000
219 | 564378 | C. 612 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 218 | 564377 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
220 | 564379 | C. 612 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 218 | 564377 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
221 | 564380 | C. 612 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 218 | 564377 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
222 | 564381 | C - 613 Dado Work | NA | 0.0000 | 0.0000 | 173 | 564332 | 31 | 0 | [6 empty] | 0.0000
223 | 564382 | C. 613 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 222 | 564381 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
224 | 564383 | C. 613 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 222 | 564381 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
225 | 564384 | C. 613 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 222 | 564381 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
226 | 564385 | C - 614 Dado Work | NA | 0.0000 | 0.0000 | 173 | 564332 | 31 | 0 | [6 empty] | 0.0000
227 | 564386 | C. 614 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 226 | 564385 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
228 | 564387 | C. 614 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 226 | 564385 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
229 | 564388 | C. 614 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 226 | 564385 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
230 | 564389 | C - 7th Floor | NA | 0.0000 | 0.0000 | 1 | 564157 | 31 | 0 | [6 empty] | 0.0000
231 | 564390 | C - 701 Dado Work | NA | 0.0000 | 0.0000 | 230 | 564389 | 31 | 0 | [6 empty] | 0.0000
232 | 564391 | C- 701 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 231 | 564390 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
233 | 564392 | C- 701 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 231 | 564390 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
234 | 564393 | C- 701 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 231 | 564390 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
235 | 564394 | C - 702 Dado Work | NA | 0.0000 | 0.0000 | 230 | 564389 | 31 | 0 | [6 empty] | 0.0000
236 | 564395 | C. 702 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 235 | 564394 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
237 | 564396 | C. 702 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 235 | 564394 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
238 | 564397 | C. 702 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 235 | 564394 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
239 | 564398 | C - 703 Dado Work | NA | 0.0000 | 0.0000 | 230 | 564389 | 31 | 0 | [6 empty] | 0.0000
240 | 564399 | C. 703 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 239 | 564398 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
241 | 564400 | C. 703 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 239 | 564398 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
242 | 564401 | C. 703 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 239 | 564398 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
243 | 564402 | C - 704 Dado Work | NA | 0.0000 | 0.0000 | 230 | 564389 | 31 | 0 | [6 empty] | 0.0000
244 | 564403 | C. 704 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 243 | 564402 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
245 | 564404 | C. 704 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 243 | 564402 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
246 | 564405 | C. 704 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 243 | 564402 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
247 | 564406 | C - 705 Dado Work | NA | 0.0000 | 0.0000 | 230 | 564389 | 31 | 0 | [6 empty] | 0.0000
248 | 564407 | C. 705 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 247 | 564406 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
249 | 564408 | C. 705 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 247 | 564406 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
250 | 564409 | C. 705 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 247 | 564406 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
251 | 564410 | C - 706 Dado Work | NA | 0.0000 | 0.0000 | 230 | 564389 | 31 | 0 | [6 empty] | 0.0000
252 | 564411 | C. 706 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 251 | 564410 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
253 | 564412 | C. 706 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 251 | 564410 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
254 | 564413 | C. 706 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 251 | 564410 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
255 | 564414 | C - 707 Dado Work | NA | 0.0000 | 0.0000 | 230 | 564389 | 31 | 0 | [6 empty] | 0.0000
256 | 564415 | C. 707 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 255 | 564414 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
257 | 564416 | C. 707 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 255 | 564414 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
258 | 564417 | C. 707 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 255 | 564414 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
259 | 564418 | C - 708 Dado Work | NA | 0.0000 | 0.0000 | 230 | 564389 | 31 | 0 | [6 empty] | 0.0000
260 | 564419 | C. 708 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 259 | 564418 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
261 | 564420 | C. 708 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 259 | 564418 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
262 | 564421 | C. 708 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 259 | 564418 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
263 | 564422 | C - 709 Dado Work | NA | 0.0000 | 0.0000 | 230 | 564389 | 31 | 0 | [6 empty] | 0.0000
264 | 564423 | C. 709 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 263 | 564422 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
265 | 564424 | C. 709 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 263 | 564422 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
266 | 564425 | C. 709 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 263 | 564422 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
267 | 564426 | C - 710 Dado Work | NA | 0.0000 | 0.0000 | 230 | 564389 | 31 | 0 | [6 empty] | 0.0000
268 | 564427 | C. 710 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 267 | 564426 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
269 | 564428 | C. 710 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 267 | 564426 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
270 | 564429 | C. 710 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 267 | 564426 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
271 | 564430 | C - 711 Dado Work | NA | 0.0000 | 0.0000 | 230 | 564389 | 31 | 0 | [6 empty] | 0.0000
272 | 564431 | C. 711 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 271 | 564430 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
273 | 564432 | C. 711 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 271 | 564430 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
274 | 564433 | C. 711 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 271 | 564430 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
275 | 564434 | C - 712 Dado Work | NA | 0.0000 | 0.0000 | 230 | 564389 | 31 | 0 | [6 empty] | 0.0000
276 | 564435 | C. 712 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 275 | 564434 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
277 | 564436 | C. 712 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 275 | 564434 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
278 | 564437 | C. 712 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 275 | 564434 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
279 | 564438 | C - 713 Dado Work | NA | 0.0000 | 0.0000 | 230 | 564389 | 31 | 0 | [6 empty] | 0.0000
280 | 564439 | C. 713 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 279 | 564438 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
281 | 564440 | C. 713 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 279 | 564438 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
282 | 564441 | C. 713 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 279 | 564438 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
283 | 564442 | C - 714 Dado Work | NA | 0.0000 | 0.0000 | 230 | 564389 | 31 | 0 | [6 empty] | 0.0000
284 | 564443 | C. 714 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 283 | 564442 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
285 | 564444 | C. 714 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 283 | 564442 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
286 | 564445 | C. 714 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 283 | 564442 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
287 | 564446 | C - 8th Floor | NA | 0.0000 | 0.0000 | 1 | 564157 | 31 | 0 | [6 empty] | 0.0000
288 | 564447 | C - 801 Dado Work | NA | 0.0000 | 0.0000 | 287 | 564446 | 31 | 0 | [6 empty] | 0.0000
289 | 564448 | C- 801 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 288 | 564447 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
290 | 564449 | C- 801 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 288 | 564447 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
291 | 564450 | C- 801 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 288 | 564447 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
292 | 564451 | C - 802 Dado Work | NA | 0.0000 | 0.0000 | 287 | 564446 | 31 | 0 | [6 empty] | 0.0000
293 | 564452 | C. 802 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 292 | 564451 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
294 | 564453 | C. 802 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 292 | 564451 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
295 | 564454 | C. 802 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 292 | 564451 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
296 | 564455 | C - 803 Dado Work | NA | 0.0000 | 0.0000 | 287 | 564446 | 31 | 0 | [6 empty] | 0.0000
297 | 564456 | C. 803 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 296 | 564455 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
298 | 564457 | C. 803 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 296 | 564455 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
299 | 564458 | C. 803 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 296 | 564455 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
300 | 564459 | C - 804 Dado Work | NA | 0.0000 | 0.0000 | 287 | 564446 | 31 | 0 | [6 empty] | 0.0000
301 | 564460 | C. 804 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 300 | 564459 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
302 | 564461 | C. 804 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 300 | 564459 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
303 | 564462 | C. 804 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 300 | 564459 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
304 | 564463 | C - 805 Dado Work | NA | 0.0000 | 0.0000 | 287 | 564446 | 31 | 0 | [6 empty] | 0.0000
305 | 564464 | C. 805 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 304 | 564463 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
306 | 564465 | C. 805 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 304 | 564463 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
307 | 564466 | C. 805 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 304 | 564463 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
308 | 564467 | C - 806 Dado Work | NA | 0.0000 | 0.0000 | 287 | 564446 | 31 | 0 | [6 empty] | 0.0000
309 | 564468 | C. 806 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 308 | 564467 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
310 | 564469 | C. 806 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 308 | 564467 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
311 | 564470 | C. 806 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 308 | 564467 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
312 | 564471 | C - 807 Dado Work | NA | 0.0000 | 0.0000 | 287 | 564446 | 31 | 0 | [6 empty] | 0.0000
313 | 564472 | C. 807 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 312 | 564471 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
314 | 564473 | C. 807 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 312 | 564471 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
315 | 564474 | C. 807 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 312 | 564471 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
316 | 564475 | C - 808 Dado Work | NA | 0.0000 | 0.0000 | 287 | 564446 | 31 | 0 | [6 empty] | 0.0000
317 | 564476 | C. 808 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 316 | 564475 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
318 | 564477 | C. 808 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 316 | 564475 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
319 | 564478 | C. 808 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 316 | 564475 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
320 | 564479 | C - 809 Dado Work | NA | 0.0000 | 0.0000 | 287 | 564446 | 31 | 0 | [6 empty] | 0.0000
321 | 564480 | C. 809 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 320 | 564479 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
322 | 564481 | C. 809 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 320 | 564479 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
323 | 564482 | C. 809 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 320 | 564479 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
324 | 564483 | C - 810 Dado Work | NA | 0.0000 | 0.0000 | 287 | 564446 | 31 | 0 | [6 empty] | 0.0000
325 | 564484 | C. 810 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 324 | 564483 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
326 | 564485 | C. 810 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 324 | 564483 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
327 | 564486 | C. 810 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 324 | 564483 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
328 | 564487 | C - 811 Dado Work | NA | 0.0000 | 0.0000 | 287 | 564446 | 31 | 0 | [6 empty] | 0.0000
329 | 564488 | C. 811 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 328 | 564487 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
330 | 564489 | C. 811 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 328 | 564487 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
331 | 564490 | C. 811 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 328 | 564487 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
332 | 564491 | C - 812 Dado Work | NA | 0.0000 | 0.0000 | 287 | 564446 | 31 | 0 | [6 empty] | 0.0000
333 | 564492 | C. 812 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 332 | 564491 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
334 | 564493 | C. 812 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 332 | 564491 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
335 | 564494 | C. 812 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 332 | 564491 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
336 | 564495 | C - 813 Dado Work | NA | 0.0000 | 0.0000 | 287 | 564446 | 31 | 0 | [6 empty] | 0.0000
337 | 564496 | C. 813 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 336 | 564495 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
338 | 564497 | C. 813 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 336 | 564495 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
339 | 564498 | C. 813 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 336 | 564495 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
340 | 564499 | C - 814 Dado Work | NA | 0.0000 | 0.0000 | 287 | 564446 | 31 | 0 | [6 empty] | 0.0000
341 | 564500 | C. 814 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 340 | 564499 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
342 | 564501 | C. 814 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 340 | 564499 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
343 | 564502 | C. 814 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 340 | 564499 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000