## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 567312 | G - Staircase 2 | NA | 0.0000 | 0.0000 | 0 | 567273 | 31 | 0 | [6 empty] | 0.0000
2 | 567313 | G - Ground Floor | NA | 0.0000 | 0.0000 | 1 | 567312 | 31 | 0 | [6 empty] | 0.0000
3 | 567314 | G - G.F. Staircase 2 Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 567313 | 4 | 33914 | G - 1st Staircase 1 Flooring Work | [5 empty] | 0.0000
4 | 567315 | G - G.F. Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 567313 | 4 | 33915 | G - 1st Staircase 1 Skirting Work | [5 empty] | 0.0000
5 | 567316 | G - 1st Floor | NA | 0.0000 | 0.0000 | 1 | 567312 | 31 | 0 | [6 empty] | 0.0000
6 | 567317 | G -1st Floor Staircase 2 Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 5 | 567316 | 4 | 33914 | G - 1st Staircase 1 Flooring Work | [5 empty] | 0.0000
7 | 567318 | G -1st Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 5 | 567316 | 4 | 33915 | G - 1st Staircase 1 Skirting Work | [5 empty] | 0.0000
8 | 567319 | G - 2nd Floor | NA | 0.0000 | 0.0000 | 1 | 567312 | 31 | 0 | [6 empty] | 0.0000
9 | 567320 | G - 2nd Floor Staircase 2 Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 8 | 567319 | 4 | 33914 | G - 1st Staircase 1 Flooring Work | [5 empty] | 0.0000
10 | 567321 | G - 2nd Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 8 | 567319 | 4 | 33915 | G - 1st Staircase 1 Skirting Work | [5 empty] | 0.0000
11 | 567322 | G - 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 567312 | 31 | 0 | [6 empty] | 0.0000
12 | 567323 | G - 3rd Floor Staircase 2 Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 11 | 567322 | 4 | 33914 | G - 1st Staircase 1 Flooring Work | [5 empty] | 0.0000
13 | 567324 | G - 3rd Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 11 | 567322 | 4 | 33915 | G - 1st Staircase 1 Skirting Work | [5 empty] | 0.0000
14 | 567325 | G - 4th Floor | NA | 0.0000 | 0.0000 | 1 | 567312 | 31 | 0 | [6 empty] | 0.0000
15 | 567326 | G - 4th Floor Staircase 2 Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 567325 | 4 | 33914 | G - 1st Staircase 1 Flooring Work | [5 empty] | 0.0000
16 | 567327 | G - 4th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 567325 | 4 | 33915 | G - 1st Staircase 1 Skirting Work | [5 empty] | 0.0000
17 | 567328 | G - 5th Floor | NA | 0.0000 | 0.0000 | 1 | 567312 | 31 | 0 | [6 empty] | 0.0000
18 | 567329 | G - 5th Floor Staircase 2 Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 17 | 567328 | 4 | 33914 | G - 1st Staircase 1 Flooring Work | [5 empty] | 0.0000
19 | 567330 | G - 5th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 17 | 567328 | 4 | 33915 | G - 1st Staircase 1 Skirting Work | [5 empty] | 0.0000
20 | 567331 | G - 6th Floor | NA | 0.0000 | 0.0000 | 1 | 567312 | 31 | 0 | [6 empty] | 0.0000
21 | 567332 | G - 6th Floor Staircase 2 Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 20 | 567331 | 4 | 33914 | G - 1st Staircase 1 Flooring Work | [5 empty] | 0.0000
22 | 567333 | G - 6th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 20 | 567331 | 4 | 33915 | G - 1st Staircase 1 Skirting Work | [5 empty] | 0.0000