## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 567589 | C - 3rd Floor | NA | 0.0000 | 0.0000 | 0 | 567587 | 31 | 0 | [6 empty] | 0.0000
2 | 567591 | C - Flat No. 301 | NA | 0.0000 | 0.0000 | 1 | 567589 | 31 | 0 | [6 empty] | 0.0000
3 | 567817 | C - Flat No 301 Balcony Flooring Work | Sq.Ft | 27.1300 | 27.1300 | 2 | 567591 | 4 | 33927 | C - Flat No 101 Balcony Flooring Work | [5 empty] | 0.0000
4 | 567818 | C - Flat No 301 Bath & WC Flooring Work | Sq.Ft | 27.5600 | 27.5600 | 2 | 567591 | 4 | 33928 | C - Flat No 101 Bath & WC Flooring Work | [5 empty] | 0.0000
5 | 567819 | C - Flat No 301 Internal Flat Vitrified Flooring Work | Sq.Ft | 245.3100 | 245.3100 | 2 | 567591 | 4 | 33929 | C - Flat No 101 Internal Flat Vitrified | [5 empty] | 0.0000
6 | 567820 | C - Flat No. 302 | NA | 0.0000 | 0.0000 | 1 | 567589 | 31 | 0 | [6 empty] | 0.0000
7 | 567821 | C - Flat No 302 Balcony Flooring Work | Sq.Ft | 27.1300 | 27.1300 | 6 | 567820 | 4 | 33927 | C - Flat No 101 Balcony Flooring Work | [5 empty] | 0.0000
8 | 567822 | C - Flat No 302 Bath & WC Flooring Work | Sq.Ft | 27.5600 | 27.5600 | 6 | 567820 | 4 | 33928 | C - Flat No 101 Bath & WC Flooring Work | [5 empty] | 0.0000
9 | 567823 | C - Flat No 302 Internal Flat Vitrified Flooring Work | Sq.Ft | 245.3100 | 245.3100 | 6 | 567820 | 4 | 33929 | C - Flat No 101 Internal Flat Vitrified | [5 empty] | 0.0000
10 | 567824 | C - Flat No. 303 | NA | 0.0000 | 0.0000 | 1 | 567589 | 31 | 0 | [6 empty] | 0.0000
11 | 567825 | C - Flat No 303 Balcony Flooring Work | Sq.Ft | 26.9100 | 26.9100 | 10 | 567824 | 4 | 33927 | C - Flat No 101 Balcony Flooring Work | [5 empty] | 0.0000
12 | 567826 | C - Flat No 303 Bath & WC Flooring Work | Sq.Ft | 27.5600 | 27.5600 | 10 | 567824 | 4 | 33928 | C - Flat No 101 Bath & WC Flooring Work | [5 empty] | 0.0000
13 | 567827 | C - Flat No 303 Internal Flat Vitrified Flooring Work | Sq.Ft | 245.3100 | 245.3100 | 10 | 567824 | 4 | 33929 | C - Flat No 101 Internal Flat Vitrified | [5 empty] | 0.0000
14 | 567828 | C - Flat No. 304 | NA | 0.0000 | 0.0000 | 1 | 567589 | 31 | 0 | [6 empty] | 0.0000
15 | 567829 | C - Flat No 304 Balcony Flooring Work | Sq.Ft | 26.9100 | 26.9100 | 14 | 567828 | 4 | 33927 | C - Flat No 101 Balcony Flooring Work | [5 empty] | 0.0000
16 | 567830 | C - Flat No 304 Bath & WC Flooring Work | Sq.Ft | 27.5600 | 27.5600 | 14 | 567828 | 4 | 33928 | C - Flat No 101 Bath & WC Flooring Work | [5 empty] | 0.0000
17 | 567831 | C - Flat No 304 Internal Flat Vitrified Flooring Work | Sq.Ft | 245.4200 | 245.4200 | 14 | 567828 | 4 | 33929 | C - Flat No 101 Internal Flat Vitrified | [5 empty] | 0.0000
18 | 567832 | C - Flat No. 305 | NA | 0.0000 | 0.0000 | 1 | 567589 | 31 | 0 | [6 empty] | 0.0000
19 | 567833 | C - Flat No 305 Balcony Flooring Work | Sq.Ft | 27.1300 | 27.1300 | 18 | 567832 | 4 | 33927 | C - Flat No 101 Balcony Flooring Work | [5 empty] | 0.0000
20 | 567834 | C - Flat No 305 Bath & WC Flooring Work | Sq.Ft | 27.5600 | 27.5600 | 18 | 567832 | 4 | 33928 | C - Flat No 101 Bath & WC Flooring Work | [5 empty] | 0.0000
21 | 567835 | C - Flat No 305 Internal Flat Vitrified Flooring Work | Sq.Ft | 245.3100 | 245.3100 | 18 | 567832 | 4 | 33929 | C - Flat No 101 Internal Flat Vitrified | [5 empty] | 0.0000
22 | 567836 | C - Flat No. 306 | NA | 0.0000 | 0.0000 | 1 | 567589 | 31 | 0 | [6 empty] | 0.0000
23 | 567837 | C - Flat No 306 Balcony Flooring Work | Sq.Ft | 26.2600 | 26.2600 | 22 | 567836 | 4 | 33927 | C - Flat No 101 Balcony Flooring Work | [5 empty] | 0.0000
24 | 567838 | C - Flat No 306 Bath & WC Flooring Work | Sq.Ft | 27.5600 | 27.5600 | 22 | 567836 | 4 | 33928 | C - Flat No 101 Bath & WC Flooring Work | [5 empty] | 0.0000
25 | 567839 | C - Flat No 306 Internal Flat Vitrified Flooring Work | Sq.Ft | 245.3100 | 245.3100 | 22 | 567836 | 4 | 33929 | C - Flat No 101 Internal Flat Vitrified | [5 empty] | 0.0000
26 | 567840 | C - Flat No. 307 | NA | 0.0000 | 0.0000 | 1 | 567589 | 31 | 0 | [6 empty] | 0.0000
27 | 567841 | C - Flat No 307 Balcony Flooring Work | Sq.Ft | 24.9700 | 24.9700 | 26 | 567840 | 4 | 33927 | C - Flat No 101 Balcony Flooring Work | [5 empty] | 0.0000
28 | 567842 | C - Flat No 307 Bath & WC Flooring Work | Sq.Ft | 27.6600 | 27.6600 | 26 | 567840 | 4 | 33928 | C - Flat No 101 Bath & WC Flooring Work | [5 empty] | 0.0000
29 | 567843 | C - Flat No 307 Internal Flat Vitrified Flooring Work | Sq.Ft | 245.4200 | 245.4200 | 26 | 567840 | 4 | 33929 | C - Flat No 101 Internal Flat Vitrified | [5 empty] | 0.0000
30 | 567844 | C - Flat No. 308 | NA | 0.0000 | 0.0000 | 1 | 567589 | 31 | 0 | [6 empty] | 0.0000
31 | 567845 | C - Flat No 308 Balcony Flooring Work | Sq.Ft | 24.9700 | 24.9700 | 30 | 567844 | 4 | 33927 | C - Flat No 101 Balcony Flooring Work | [5 empty] | 0.0000
32 | 567846 | C - Flat No 308 Bath & WC Flooring Work | Sq.Ft | 27.0200 | 27.0200 | 30 | 567844 | 4 | 33928 | C - Flat No 101 Bath & WC Flooring Work | [5 empty] | 0.0000
33 | 567847 | C - Flat No 308 Internal Flat Vitrified Flooring Work | Sq.Ft | 245.3100 | 245.3100 | 30 | 567844 | 4 | 33929 | C - Flat No 101 Internal Flat Vitrified | [5 empty] | 0.0000
34 | 567848 | C - Flat No. 309 | NA | 0.0000 | 0.0000 | 1 | 567589 | 31 | 0 | [6 empty] | 0.0000
35 | 567849 | C - Flat No 309 Balcony Flooring Work | Sq.Ft | 24.9700 | 24.9700 | 34 | 567848 | 4 | 33927 | C - Flat No 101 Balcony Flooring Work | [5 empty] | 0.0000
36 | 567850 | C - Flat No 309 Bath & WC Flooring Work | Sq.Ft | 27.5600 | 27.5600 | 34 | 567848 | 4 | 33928 | C - Flat No 101 Bath & WC Flooring Work | [5 empty] | 0.0000
37 | 567851 | C - Flat No 309 Internal Flat Vitrified Flooring Work | Sq.Ft | 245.3100 | 245.3100 | 34 | 567848 | 4 | 33929 | C - Flat No 101 Internal Flat Vitrified | [5 empty] | 0.0000
38 | 567852 | C - Flat No. 310 | NA | 0.0000 | 0.0000 | 1 | 567589 | 31 | 0 | [6 empty] | 0.0000
39 | 567853 | C - Flat No 310 Balcony Flooring Work | Sq.Ft | 26.0500 | 26.0500 | 38 | 567852 | 4 | 33927 | C - Flat No 101 Balcony Flooring Work | [5 empty] | 0.0000
40 | 567854 | C - Flat No 310 Bath & WC Flooring Work | Sq.Ft | 27.5600 | 27.5600 | 38 | 567852 | 4 | 33928 | C - Flat No 101 Bath & WC Flooring Work | [5 empty] | 0.0000
41 | 567855 | C - Flat No 310 Internal Flat Vitrified Flooring Work | Sq.Ft | 245.3100 | 245.3100 | 38 | 567852 | 4 | 33929 | C - Flat No 101 Internal Flat Vitrified | [5 empty] | 0.0000
42 | 567856 | C - Flat No. 311 | NA | 0.0000 | 0.0000 | 1 | 567589 | 31 | 0 | [6 empty] | 0.0000
43 | 567857 | C - Flat No 311 Balcony Flooring Work | Sq.Ft | 26.0500 | 26.0500 | 42 | 567856 | 4 | 33927 | C - Flat No 101 Balcony Flooring Work | [5 empty] | 0.0000
44 | 567858 | C - Flat No 311 Bath & WC Flooring Work | Sq.Ft | 27.5600 | 27.5600 | 42 | 567856 | 4 | 33928 | C - Flat No 101 Bath & WC Flooring Work | [5 empty] | 0.0000
45 | 567859 | C - Flat No 311 Internal Flat Vitrified Flooring Work | Sq.Ft | 245.3100 | 245.3100 | 42 | 567856 | 4 | 33929 | C - Flat No 101 Internal Flat Vitrified | [5 empty] | 0.0000
46 | 567860 | C - Flat No. 312 | NA | 0.0000 | 0.0000 | 1 | 567589 | 31 | 0 | [6 empty] | 0.0000
47 | 567861 | C - Flat No 312 Balcony Flooring Work | Sq.Ft | 26.0500 | 26.0500 | 46 | 567860 | 4 | 33927 | C - Flat No 101 Balcony Flooring Work | [5 empty] | 0.0000
48 | 567862 | C - Flat No 312 Bath & WC Flooring Work | Sq.Ft | 27.5600 | 27.5600 | 46 | 567860 | 4 | 33928 | C - Flat No 101 Bath & WC Flooring Work | [5 empty] | 0.0000
49 | 567863 | C - Flat No 312 Internal Flat Vitrified Flooring Work | Sq.Ft | 245.3100 | 245.3100 | 46 | 567860 | 4 | 33929 | C - Flat No 101 Internal Flat Vitrified | [5 empty] | 0.0000
50 | 567864 | C - Flat No. 313 | NA | 0.0000 | 0.0000 | 1 | 567589 | 31 | 0 | [6 empty] | 0.0000
51 | 567865 | C - Flat No 313 Balcony Flooring Work | Sq.Ft | 26.0500 | 26.0500 | 50 | 567864 | 4 | 33927 | C - Flat No 101 Balcony Flooring Work | [5 empty] | 0.0000
52 | 567866 | C - Flat No 313 Bath & WC Flooring Work | Sq.Ft | 27.5600 | 27.5600 | 50 | 567864 | 4 | 33928 | C - Flat No 101 Bath & WC Flooring Work | [5 empty] | 0.0000
53 | 567867 | C - Flat No 313 Internal Flat Vitrified Flooring Work | Sq.Ft | 245.3100 | 245.3100 | 50 | 567864 | 4 | 33929 | C - Flat No 101 Internal Flat Vitrified | [5 empty] | 0.0000
54 | 567868 | C - Flat No. 314 | NA | 0.0000 | 0.0000 | 1 | 567589 | 31 | 0 | [6 empty] | 0.0000
55 | 567869 | C - Flat No 314 Balcony Flooring Work | Sq.Ft | 27.1300 | 27.1300 | 54 | 567868 | 4 | 33927 | C - Flat No 101 Balcony Flooring Work | [5 empty] | 0.0000
56 | 567870 | C - Flat No 314 Bath & WC Flooring Work | Sq.Ft | 27.5600 | 27.5600 | 54 | 567868 | 4 | 33928 | C - Flat No 101 Bath & WC Flooring Work | [5 empty] | 0.0000
57 | 567871 | C - Flat No 314 Internal Flat Vitrified Flooring Work | Sq.Ft | 245.3100 | 245.3100 | 54 | 567868 | 4 | 33929 | C - Flat No 101 Internal Flat Vitrified | [5 empty] | 0.0000