## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 568551 | C - 3rd Floor | NA | 0.0000 | 0.0000 | 0 | 567588 | 31 | 0 | [6 empty] | 0.0000
2 | 568552 | C - Flat No 301 | NA | 0.0000 | 0.0000 | 1 | 568551 | 31 | 0 | [6 empty] | 0.0000
3 | 568553 | C - Flat No 301 Flat Skirting Work | R.Ft | 1.0000 | 1.0000 | 2 | 568552 | 4 | 33934 | C - Flat No 301 Flat Skirting Work | [5 empty] | 0.0000
4 | 568554 | C - Flat No 301 Balcony Skirting Work | R.Ft | 1.0000 | 1.0000 | 2 | 568552 | 4 | 33935 | C - Flat No 301 Balcony Skirting Work | [5 empty] | 0.0000
5 | 568555 | C - Flat No 302 | NA | 0.0000 | 0.0000 | 1 | 568551 | 31 | 0 | [6 empty] | 0.0000
6 | 568556 | C . Flat No 302 Flat Skirting Work | R.Ft | 1.0000 | 1.0000 | 5 | 568555 | 4 | 33934 | C - Flat No 301 Flat Skirting Work | [5 empty] | 0.0000
7 | 568557 | C . Flat No 302 Balcony Skirting Work | R.Ft | 1.0000 | 1.0000 | 5 | 568555 | 4 | 33935 | C - Flat No 301 Balcony Skirting Work | [5 empty] | 0.0000
8 | 568558 | C - Flat No 303 | NA | 0.0000 | 0.0000 | 1 | 568551 | 31 | 0 | [6 empty] | 0.0000
9 | 568559 | C . Flat No 303 Flat Skirting Work | R.Ft | 1.0000 | 1.0000 | 8 | 568558 | 4 | 33934 | C - Flat No 301 Flat Skirting Work | [5 empty] | 0.0000
10 | 568560 | C . Flat No 303 Balcony Skirting Work | R.Ft | 1.0000 | 1.0000 | 8 | 568558 | 4 | 33935 | C - Flat No 301 Balcony Skirting Work | [5 empty] | 0.0000
11 | 568561 | C - Flat No 304 | NA | 0.0000 | 0.0000 | 1 | 568551 | 31 | 0 | [6 empty] | 0.0000
12 | 568562 | C . Flat No 304 Flat Skirting Work | R.Ft | 1.0000 | 1.0000 | 11 | 568561 | 4 | 33934 | C - Flat No 301 Flat Skirting Work | [5 empty] | 0.0000
13 | 568563 | C . Flat No 304 Balcony Skirting Work | R.Ft | 1.0000 | 1.0000 | 11 | 568561 | 4 | 33935 | C - Flat No 301 Balcony Skirting Work | [5 empty] | 0.0000
14 | 568564 | C - Flat No 305 | NA | 0.0000 | 0.0000 | 1 | 568551 | 31 | 0 | [6 empty] | 0.0000
15 | 568565 | C . Flat No 305 Flat Skirting Work | R.Ft | 1.0000 | 1.0000 | 14 | 568564 | 4 | 33934 | C - Flat No 301 Flat Skirting Work | [5 empty] | 0.0000
16 | 568566 | C . Flat No 305 Balcony Skirting Work | R.Ft | 1.0000 | 1.0000 | 14 | 568564 | 4 | 33935 | C - Flat No 301 Balcony Skirting Work | [5 empty] | 0.0000
17 | 568567 | C - Flat No 306 | NA | 0.0000 | 0.0000 | 1 | 568551 | 31 | 0 | [6 empty] | 0.0000
18 | 568568 | C . Flat No 306 Flat Skirting Work | R.Ft | 1.0000 | 1.0000 | 17 | 568567 | 4 | 33934 | C - Flat No 301 Flat Skirting Work | [5 empty] | 0.0000
19 | 568569 | C . Flat No 306 Balcony Skirting Work | R.Ft | 1.0000 | 1.0000 | 17 | 568567 | 4 | 33935 | C - Flat No 301 Balcony Skirting Work | [5 empty] | 0.0000
20 | 568570 | C - Flat No 307 | NA | 0.0000 | 0.0000 | 1 | 568551 | 31 | 0 | [6 empty] | 0.0000
21 | 568571 | C . Flat No 307 Flat Skirting Work | R.Ft | 1.0000 | 1.0000 | 20 | 568570 | 4 | 33934 | C - Flat No 301 Flat Skirting Work | [5 empty] | 0.0000
22 | 568572 | C . Flat No 307 Balcony Skirting Work | R.Ft | 1.0000 | 1.0000 | 20 | 568570 | 4 | 33935 | C - Flat No 301 Balcony Skirting Work | [5 empty] | 0.0000
23 | 568576 | C - Flat No 308 | NA | 0.0000 | 0.0000 | 1 | 568551 | 31 | 0 | [6 empty] | 0.0000
24 | 568577 | C . Flat No 308 Flat Skirting Work | R.Ft | 1.0000 | 1.0000 | 23 | 568576 | 4 | 33934 | C - Flat No 301 Flat Skirting Work | [5 empty] | 0.0000
25 | 568578 | C . Flat No 308 Balcony Skirting Work | R.Ft | 1.0000 | 1.0000 | 23 | 568576 | 4 | 33935 | C - Flat No 301 Balcony Skirting Work | [5 empty] | 0.0000
26 | 568579 | C - Flat No 309 | NA | 0.0000 | 0.0000 | 1 | 568551 | 31 | 0 | [6 empty] | 0.0000
27 | 568580 | C . Flat No 309 Flat Skirting Work | R.Ft | 1.0000 | 1.0000 | 26 | 568579 | 4 | 33934 | C - Flat No 301 Flat Skirting Work | [5 empty] | 0.0000
28 | 568581 | C . Flat No 309 Balcony Skirting Work | R.Ft | 1.0000 | 1.0000 | 26 | 568579 | 4 | 33935 | C - Flat No 301 Balcony Skirting Work | [5 empty] | 0.0000
29 | 568582 | C - Flat No 310 | NA | 0.0000 | 0.0000 | 1 | 568551 | 31 | 0 | [6 empty] | 0.0000
30 | 568583 | C . Flat No 310 Flat Skirting Work | R.Ft | 1.0000 | 1.0000 | 29 | 568582 | 4 | 33934 | C - Flat No 301 Flat Skirting Work | [5 empty] | 0.0000
31 | 568584 | C . Flat No 310 Balcony Skirting Work | R.Ft | 1.0000 | 1.0000 | 29 | 568582 | 4 | 33935 | C - Flat No 301 Balcony Skirting Work | [5 empty] | 0.0000
32 | 568585 | C - Flat No 311 | NA | 0.0000 | 0.0000 | 1 | 568551 | 31 | 0 | [6 empty] | 0.0000
33 | 568586 | C . Flat No 311 Flat Skirting Work | R.Ft | 1.0000 | 1.0000 | 32 | 568585 | 4 | 33934 | C - Flat No 301 Flat Skirting Work | [5 empty] | 0.0000
34 | 568587 | C . Flat No 311 Balcony Skirting Work | R.Ft | 1.0000 | 1.0000 | 32 | 568585 | 4 | 33935 | C - Flat No 301 Balcony Skirting Work | [5 empty] | 0.0000
35 | 568588 | C - Flat No 312 | NA | 0.0000 | 0.0000 | 1 | 568551 | 31 | 0 | [6 empty] | 0.0000
36 | 568589 | C . Flat No 312 Flat Skirting Work | R.Ft | 1.0000 | 1.0000 | 35 | 568588 | 4 | 33934 | C - Flat No 301 Flat Skirting Work | [5 empty] | 0.0000
37 | 568590 | C . Flat No 312 Balcony Skirting Work | R.Ft | 1.0000 | 1.0000 | 35 | 568588 | 4 | 33935 | C - Flat No 301 Balcony Skirting Work | [5 empty] | 0.0000
38 | 568591 | C - Flat No 313 | NA | 0.0000 | 0.0000 | 1 | 568551 | 31 | 0 | [6 empty] | 0.0000
39 | 568592 | C . Flat No 313 Flat Skirting Work | R.Ft | 1.0000 | 1.0000 | 38 | 568591 | 4 | 33934 | C - Flat No 301 Flat Skirting Work | [5 empty] | 0.0000
40 | 568593 | C . Flat No 313 Balcony Skirting Work | R.Ft | 1.0000 | 1.0000 | 38 | 568591 | 4 | 33935 | C - Flat No 301 Balcony Skirting Work | [5 empty] | 0.0000
41 | 568594 | C - Flat No 314 | NA | 0.0000 | 0.0000 | 1 | 568551 | 31 | 0 | [6 empty] | 0.0000
42 | 568595 | C . Flat No 314 Flat Skirting Work | R.Ft | 1.0000 | 1.0000 | 41 | 568594 | 4 | 33934 | C - Flat No 301 Flat Skirting Work | [5 empty] | 0.0000
43 | 568596 | C . Flat No 314 Balcony Skirting Work | R.Ft | 1.0000 | 1.0000 | 41 | 568594 | 4 | 33935 | C - Flat No 301 Balcony Skirting Work | [5 empty] | 0.0000