## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor | Selected Group :- C - 3rd Floor
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 569252 | C - 3rd Floor | NA | 0.0000 | 0.0000 | 0 | 569251 | 31 | 0 | [6 empty] | 0.0000
2 | 569253 | C - Flat No 301 | NA | 0.0000 | 0.0000 | 1 | 569252 | 31 | 0 | [6 empty] | 0.0000
3 | 569254 | C - Flat No. 301 Bath & WC Dado | Sq.Ft | 1.0000 | 1.0000 | 2 | 569253 | 4 | 33939 | C - Flat No. 301 Bath & WC Dado | [5 empty] | 0.0000
4 | 569255 | C - Flat No. 301 Kitchen Dado | Sq.Ft | 1.0000 | 1.0000 | 2 | 569253 | 4 | 33940 | C - Flat No. 301 Kitchen Dado | [5 empty] | 0.0000
5 | 569256 | C - Flat No 302 | NA | 0.0000 | 0.0000 | 1 | 569252 | 31 | 0 | [6 empty] | 0.0000
6 | 569257 | C - Flat No. 302 Bath & WC Dado | Sq.Ft | 1.0000 | 1.0000 | 5 | 569256 | 4 | 33939 | C - Flat No. 301 Bath & WC Dado | [5 empty] | 0.0000
7 | 569258 | C - Flat No. 302 Kitchen Dado | Sq.Ft | 1.0000 | 1.0000 | 5 | 569256 | 4 | 33940 | C - Flat No. 301 Kitchen Dado | [5 empty] | 0.0000
8 | 569259 | C - Flat No 303 | NA | 0.0000 | 0.0000 | 1 | 569252 | 31 | 0 | [6 empty] | 0.0000
9 | 569260 | C - Flat No. 303 Bath & WC Dado | Sq.Ft | 1.0000 | 1.0000 | 8 | 569259 | 4 | 33939 | C - Flat No. 301 Bath & WC Dado | [5 empty] | 0.0000
10 | 569261 | C - Flat No. 303 Kitchen Dado | Sq.Ft | 1.0000 | 1.0000 | 8 | 569259 | 4 | 33940 | C - Flat No. 301 Kitchen Dado | [5 empty] | 0.0000
11 | 569262 | C - Flat No 304 | NA | 0.0000 | 0.0000 | 1 | 569252 | 31 | 0 | [6 empty] | 0.0000
12 | 569263 | C - Flat No. 304 Bath & WC Dado | Sq.Ft | 1.0000 | 1.0000 | 11 | 569262 | 4 | 33939 | C - Flat No. 301 Bath & WC Dado | [5 empty] | 0.0000
13 | 569264 | C - Flat No. 304 Kitchen Dado | Sq.Ft | 1.0000 | 1.0000 | 11 | 569262 | 4 | 33940 | C - Flat No. 301 Kitchen Dado | [5 empty] | 0.0000
14 | 569265 | C - Flat No 305 | NA | 0.0000 | 0.0000 | 1 | 569252 | 31 | 0 | [6 empty] | 0.0000
15 | 569266 | C - Flat No. 305 Bath & WC Dado | Sq.Ft | 1.0000 | 1.0000 | 14 | 569265 | 4 | 33939 | C - Flat No. 301 Bath & WC Dado | [5 empty] | 0.0000
16 | 569267 | C - Flat No. 305 Kitchen Dado | Sq.Ft | 1.0000 | 1.0000 | 14 | 569265 | 4 | 33940 | C - Flat No. 301 Kitchen Dado | [5 empty] | 0.0000
17 | 569268 | C - Flat No 306 | NA | 0.0000 | 0.0000 | 1 | 569252 | 31 | 0 | [6 empty] | 0.0000
18 | 569269 | C - Flat No. 306 Bath & WC Dado | Sq.Ft | 1.0000 | 1.0000 | 17 | 569268 | 4 | 33939 | C - Flat No. 301 Bath & WC Dado | [5 empty] | 0.0000
19 | 569270 | C - Flat No. 306 Kitchen Dado | Sq.Ft | 1.0000 | 1.0000 | 17 | 569268 | 4 | 33940 | C - Flat No. 301 Kitchen Dado | [5 empty] | 0.0000
20 | 569271 | C - Flat No 307 | NA | 0.0000 | 0.0000 | 1 | 569252 | 31 | 0 | [6 empty] | 0.0000
21 | 569272 | C - Flat No. 307 Bath & WC Dado | Sq.Ft | 1.0000 | 1.0000 | 20 | 569271 | 4 | 33939 | C - Flat No. 301 Bath & WC Dado | [5 empty] | 0.0000
22 | 569273 | C - Flat No. 307 Kitchen Dado | Sq.Ft | 1.0000 | 1.0000 | 20 | 569271 | 4 | 33940 | C - Flat No. 301 Kitchen Dado | [5 empty] | 0.0000
23 | 569274 | C - Flat No 308 | NA | 0.0000 | 0.0000 | 1 | 569252 | 31 | 0 | [6 empty] | 0.0000
24 | 569275 | C - Flat No. 308 Bath & WC Dado | Sq.Ft | 1.0000 | 1.0000 | 23 | 569274 | 4 | 33939 | C - Flat No. 301 Bath & WC Dado | [5 empty] | 0.0000
25 | 569276 | C - Flat No. 308 Kitchen Dado | Sq.Ft | 1.0000 | 1.0000 | 23 | 569274 | 4 | 33940 | C - Flat No. 301 Kitchen Dado | [5 empty] | 0.0000
26 | 569277 | C - Flat No 309 | NA | 0.0000 | 0.0000 | 1 | 569252 | 31 | 0 | [6 empty] | 0.0000
27 | 569278 | C - Flat No. 309 Bath & WC Dado | Sq.Ft | 1.0000 | 1.0000 | 26 | 569277 | 4 | 33939 | C - Flat No. 301 Bath & WC Dado | [5 empty] | 0.0000
28 | 569279 | C - Flat No. 309 Kitchen Dado | Sq.Ft | 1.0000 | 1.0000 | 26 | 569277 | 4 | 33940 | C - Flat No. 301 Kitchen Dado | [5 empty] | 0.0000
29 | 569280 | C - Flat No 310 | NA | 0.0000 | 0.0000 | 1 | 569252 | 31 | 0 | [6 empty] | 0.0000
30 | 569281 | C - Flat No. 310 Bath & WC Dado | Sq.Ft | 1.0000 | 1.0000 | 29 | 569280 | 4 | 33939 | C - Flat No. 301 Bath & WC Dado | [5 empty] | 0.0000
31 | 569282 | C - Flat No. 310 Kitchen Dado | Sq.Ft | 1.0000 | 1.0000 | 29 | 569280 | 4 | 33940 | C - Flat No. 301 Kitchen Dado | [5 empty] | 0.0000
32 | 569283 | C - Flat No 311 | NA | 0.0000 | 0.0000 | 1 | 569252 | 31 | 0 | [6 empty] | 0.0000
33 | 569284 | C - Flat No. 311 Bath & WC Dado | Sq.Ft | 1.0000 | 1.0000 | 32 | 569283 | 4 | 33939 | C - Flat No. 301 Bath & WC Dado | [5 empty] | 0.0000
34 | 569285 | C - Flat No. 311 Kitchen Dado | Sq.Ft | 1.0000 | 1.0000 | 32 | 569283 | 4 | 33940 | C - Flat No. 301 Kitchen Dado | [5 empty] | 0.0000
35 | 569286 | C - Flat No 312 | NA | 0.0000 | 0.0000 | 1 | 569252 | 31 | 0 | [6 empty] | 0.0000
36 | 569287 | C - Flat No. 312 Bath & WC Dado | Sq.Ft | 1.0000 | 1.0000 | 35 | 569286 | 4 | 33939 | C - Flat No. 301 Bath & WC Dado | [5 empty] | 0.0000
37 | 569288 | C - Flat No. 312 Kitchen Dado | Sq.Ft | 1.0000 | 1.0000 | 35 | 569286 | 4 | 33940 | C - Flat No. 301 Kitchen Dado | [5 empty] | 0.0000
38 | 569290 | C - Flat No 313 | NA | 0.0000 | 0.0000 | 1 | 569252 | 31 | 0 | [6 empty] | 0.0000
39 | 569291 | C - Flat No. 313 Bath & WC Dado | Sq.Ft | 1.0000 | 1.0000 | 38 | 569290 | 4 | 33939 | C - Flat No. 301 Bath & WC Dado | [5 empty] | 0.0000
40 | 569292 | C - Flat No. 313 Kitchen Dado | Sq.Ft | 1.0000 | 1.0000 | 38 | 569290 | 4 | 33940 | C - Flat No. 301 Kitchen Dado | [5 empty] | 0.0000
41 | 569293 | C - Flat No 314 | NA | 0.0000 | 0.0000 | 1 | 569252 | 31 | 0 | [6 empty] | 0.0000
42 | 569294 | C - Flat No. 314 Bath & WC Dado | Sq.Ft | 1.0000 | 1.0000 | 41 | 569293 | 4 | 33939 | C - Flat No. 301 Bath & WC Dado | [5 empty] | 0.0000
43 | 569295 | C - Flat No. 314 Kitchen Dado | Sq.Ft | 1.0000 | 1.0000 | 41 | 569293 | 4 | 33940 | C - Flat No. 301 Kitchen Dado | [5 empty] | 0.0000