## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- D - Waterproofing (M) | Selected Group :- D - Waterproofing (M) | Selected Group :- D - Waterproofing (M) | Selected Group :- D - Waterproofing (M) | Selected Group :- D - Waterproofing (M) | Selected Group :- D - Waterproofing (M) | Selected Group :- D - Waterproofing (M) | Selected Group :- D - Waterproofing (M) | Selected Group :- D - Waterproofing (M) | Selected Group :- D - Waterproofing (M) | Selected Group :- D - Waterproofing (M) | Selected Group :- D - Waterproofing (M) | Selected Group :- D - Waterproofing (M) | Selected Group :- D - Waterproofing (M) | Selected Group :- D - Waterproofing (M) | Selected Group :- D - Waterproofing (M) | Selected Group :- D - Waterproofing (M)
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 571442 | D - Waterproofing (M) | NA | 0.0000 | 0.0000 | 0 | 571441 | 31 | 0 | [6 empty] | 0.0000
2 | 571443 | D - 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 571442 | 31 | 0 | [6 empty] | 0.0000
3 | 571444 | D - 4th Floor | NA | 0.0000 | 0.0000 | 1 | 571442 | 31 | 0 | [6 empty] | 0.0000
4 | 571445 | D - Flat No 401 | NA | 0.0000 | 0.0000 | 3 | 571444 | 31 | 0 | [6 empty] | 0.0000
5 | 571446 | D - 401 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 4 | 571445 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
6 | 571447 | D - 401 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 4 | 571445 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
7 | 571448 | D - 401 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 4 | 571445 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
8 | 571449 | D - Flat No 402 | NA | 0.0000 | 0.0000 | 3 | 571444 | 31 | 0 | [6 empty] | 0.0000
9 | 571450 | D . 402 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 8 | 571449 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
10 | 571451 | D . 402 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 8 | 571449 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
11 | 571452 | D . 402 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 8 | 571449 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
12 | 571453 | D - Flat No 403 | NA | 0.0000 | 0.0000 | 3 | 571444 | 31 | 0 | [6 empty] | 0.0000
13 | 571454 | D . 403 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 12 | 571453 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
14 | 571455 | D . 403 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 12 | 571453 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
15 | 571456 | D . 403 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 12 | 571453 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
16 | 571457 | D - Flat No 404 | NA | 0.0000 | 0.0000 | 3 | 571444 | 31 | 0 | [6 empty] | 0.0000
17 | 571458 | D . 404 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 16 | 571457 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
18 | 571459 | D . 404 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 16 | 571457 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
19 | 571460 | D . 404 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 16 | 571457 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
20 | 571461 | D - Flat No 405 | NA | 0.0000 | 0.0000 | 3 | 571444 | 31 | 0 | [6 empty] | 0.0000
21 | 571462 | D . 405 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 20 | 571461 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
22 | 571463 | D . 405 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 20 | 571461 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
23 | 571464 | D . 405 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 20 | 571461 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
24 | 571465 | D - Flat No 406 | NA | 0.0000 | 0.0000 | 3 | 571444 | 31 | 0 | [6 empty] | 0.0000
25 | 571466 | D . 406 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 24 | 571465 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
26 | 571467 | D . 406 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 24 | 571465 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
27 | 571468 | D . 406 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 24 | 571465 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
28 | 571469 | D - Flat No 407 | NA | 0.0000 | 0.0000 | 3 | 571444 | 31 | 0 | [6 empty] | 0.0000
29 | 571470 | D . 407 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 28 | 571469 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
30 | 571471 | D . 407 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 28 | 571469 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
31 | 571472 | D . 407 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 28 | 571469 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
32 | 571473 | D - Flat No 408 | NA | 0.0000 | 0.0000 | 3 | 571444 | 31 | 0 | [6 empty] | 0.0000
33 | 571474 | D . 408 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 32 | 571473 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
34 | 571475 | D . 408 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 32 | 571473 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
35 | 571476 | D . 408 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 32 | 571473 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
36 | 571477 | D - Flat No 409 | NA | 0.0000 | 0.0000 | 3 | 571444 | 31 | 0 | [6 empty] | 0.0000
37 | 571478 | D . 409 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 571477 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
38 | 571479 | D . 409 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 571477 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
39 | 571480 | D . 409 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 36 | 571477 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
40 | 571481 | D - Flat No 410 | NA | 0.0000 | 0.0000 | 3 | 571444 | 31 | 0 | [6 empty] | 0.0000
41 | 571482 | D . 410 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 40 | 571481 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
42 | 571483 | D . 410 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 40 | 571481 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
43 | 571484 | D . 410 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 40 | 571481 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
44 | 571485 | D - Flat No 411 | NA | 0.0000 | 0.0000 | 3 | 571444 | 31 | 0 | [6 empty] | 0.0000
45 | 571486 | D . 411 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 44 | 571485 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
46 | 571487 | D . 411 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 44 | 571485 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
47 | 571488 | D . 411 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 44 | 571485 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
48 | 571489 | D - Flat No 412 | NA | 0.0000 | 0.0000 | 3 | 571444 | 31 | 0 | [6 empty] | 0.0000
49 | 571490 | D . 412 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 48 | 571489 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
50 | 571491 | D . 412 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 48 | 571489 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
51 | 571492 | D . 412 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 48 | 571489 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
52 | 571493 | D - Flat No 413 | NA | 0.0000 | 0.0000 | 3 | 571444 | 31 | 0 | [6 empty] | 0.0000
53 | 571494 | D . 413 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 571493 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
54 | 571495 | D . 413 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 571493 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
55 | 571496 | D . 413 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 52 | 571493 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
56 | 571497 | D - Flat No 414 | NA | 0.0000 | 0.0000 | 3 | 571444 | 31 | 0 | [6 empty] | 0.0000
57 | 571498 | D . 414 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 56 | 571497 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
58 | 571499 | D . 414 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 56 | 571497 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
59 | 571500 | D . 414 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 56 | 571497 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
60 | 571682 | D - 5th Floor | NA | 0.0000 | 0.0000 | 1 | 571442 | 31 | 0 | [6 empty] | 0.0000
61 | 571683 | D - Flat No 501 | NA | 0.0000 | 0.0000 | 60 | 571682 | 31 | 0 | [6 empty] | 0.0000
62 | 571684 | D - 501 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 61 | 571683 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
63 | 571685 | D - 501 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 61 | 571683 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
64 | 571686 | D - 501 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 61 | 571683 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
65 | 571687 | D - Flat No 502 | NA | 0.0000 | 0.0000 | 60 | 571682 | 31 | 0 | [6 empty] | 0.0000
66 | 571688 | D . 502 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 65 | 571687 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
67 | 571689 | D . 502 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 65 | 571687 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
68 | 571690 | D . 502 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 65 | 571687 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
69 | 571691 | D - Flat No 503 | NA | 0.0000 | 0.0000 | 60 | 571682 | 31 | 0 | [6 empty] | 0.0000
70 | 571692 | D . 503 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 69 | 571691 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
71 | 571693 | D . 503 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 69 | 571691 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
72 | 571694 | D . 503 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 69 | 571691 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
73 | 571695 | D - Flat No 504 | NA | 0.0000 | 0.0000 | 60 | 571682 | 31 | 0 | [6 empty] | 0.0000
74 | 571696 | D . 504 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 73 | 571695 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
75 | 571697 | D . 504 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 73 | 571695 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
76 | 571698 | D . 504 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 73 | 571695 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
77 | 571699 | D - Flat No 505 | NA | 0.0000 | 0.0000 | 60 | 571682 | 31 | 0 | [6 empty] | 0.0000
78 | 571700 | D . 505 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 77 | 571699 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
79 | 571701 | D . 505 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 77 | 571699 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
80 | 571702 | D . 505 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 77 | 571699 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
81 | 571703 | D - Flat No 506 | NA | 0.0000 | 0.0000 | 60 | 571682 | 31 | 0 | [6 empty] | 0.0000
82 | 571704 | D . 506 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 81 | 571703 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
83 | 571705 | D . 506 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 81 | 571703 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
84 | 571706 | D . 506 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 81 | 571703 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
85 | 571707 | D - Flat No 507 | NA | 0.0000 | 0.0000 | 60 | 571682 | 31 | 0 | [6 empty] | 0.0000
86 | 571708 | D . 507 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 85 | 571707 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
87 | 571709 | D . 507 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 85 | 571707 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
88 | 571710 | D . 507 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 85 | 571707 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
89 | 571711 | D - Flat No 508 | NA | 0.0000 | 0.0000 | 60 | 571682 | 31 | 0 | [6 empty] | 0.0000
90 | 571712 | D . 508 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 89 | 571711 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
91 | 571713 | D . 508 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 89 | 571711 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
92 | 571714 | D . 508 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 89 | 571711 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
93 | 571715 | D - Flat No 509 | NA | 0.0000 | 0.0000 | 60 | 571682 | 31 | 0 | [6 empty] | 0.0000
94 | 571716 | D . 509 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 93 | 571715 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
95 | 571717 | D . 509 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 93 | 571715 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
96 | 571718 | D . 509 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 93 | 571715 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
97 | 571719 | D - Flat No 510 | NA | 0.0000 | 0.0000 | 60 | 571682 | 31 | 0 | [6 empty] | 0.0000
98 | 571720 | D . 510 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 97 | 571719 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
99 | 571721 | D . 510 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 97 | 571719 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
100 | 571722 | D . 510 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 97 | 571719 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
101 | 571723 | D - Flat No 511 | NA | 0.0000 | 0.0000 | 60 | 571682 | 31 | 0 | [6 empty] | 0.0000
102 | 571724 | D . 511 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 101 | 571723 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
103 | 571725 | D . 511 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 101 | 571723 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
104 | 571726 | D . 511 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 101 | 571723 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
105 | 571727 | D - Flat No 512 | NA | 0.0000 | 0.0000 | 60 | 571682 | 31 | 0 | [6 empty] | 0.0000
106 | 571728 | D . 512 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 105 | 571727 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
107 | 571729 | D . 512 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 105 | 571727 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
108 | 571730 | D . 512 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 105 | 571727 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
109 | 571731 | D - Flat No 513 | NA | 0.0000 | 0.0000 | 60 | 571682 | 31 | 0 | [6 empty] | 0.0000
110 | 571732 | D . 513 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 109 | 571731 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
111 | 571733 | D . 513 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 109 | 571731 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
112 | 571734 | D . 513 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 109 | 571731 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
113 | 571735 | D - Flat No 514 | NA | 0.0000 | 0.0000 | 60 | 571682 | 31 | 0 | [6 empty] | 0.0000
114 | 571736 | D . 514 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 113 | 571735 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
115 | 571737 | D . 514 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 113 | 571735 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
116 | 571738 | D . 514 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 113 | 571735 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
117 | 571739 | D - 6th Floor | NA | 0.0000 | 0.0000 | 1 | 571442 | 31 | 0 | [6 empty] | 0.0000
118 | 571740 | D - Flat No 601 | NA | 0.0000 | 0.0000 | 117 | 571739 | 31 | 0 | [6 empty] | 0.0000
119 | 571741 | D - 601 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 118 | 571740 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
120 | 571742 | D - 601 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 118 | 571740 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
121 | 571743 | D - 601 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 118 | 571740 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
122 | 571744 | D - Flat No 602 | NA | 0.0000 | 0.0000 | 117 | 571739 | 31 | 0 | [6 empty] | 0.0000
123 | 571745 | D . 602 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 122 | 571744 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
124 | 571746 | D . 602 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 122 | 571744 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
125 | 571747 | D . 602 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 122 | 571744 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
126 | 571748 | D - Flat No 603 | NA | 0.0000 | 0.0000 | 117 | 571739 | 31 | 0 | [6 empty] | 0.0000
127 | 571749 | D . 603 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 126 | 571748 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
128 | 571750 | D . 603 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 126 | 571748 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
129 | 571751 | D . 603 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 126 | 571748 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
130 | 571752 | D - Flat No 604 | NA | 0.0000 | 0.0000 | 117 | 571739 | 31 | 0 | [6 empty] | 0.0000
131 | 571753 | D . 604 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 130 | 571752 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
132 | 571754 | D . 604 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 130 | 571752 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
133 | 571755 | D . 604 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 130 | 571752 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
134 | 571756 | D - Flat No 605 | NA | 0.0000 | 0.0000 | 117 | 571739 | 31 | 0 | [6 empty] | 0.0000
135 | 571757 | D . 605 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 134 | 571756 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
136 | 571758 | D . 605 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 134 | 571756 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
137 | 571759 | D . 605 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 134 | 571756 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
138 | 571760 | D - Flat No 606 | NA | 0.0000 | 0.0000 | 117 | 571739 | 31 | 0 | [6 empty] | 0.0000
139 | 571761 | D . 606 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 138 | 571760 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
140 | 571762 | D . 606 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 138 | 571760 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
141 | 571763 | D . 606 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 138 | 571760 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
142 | 571764 | D - Flat No 607 | NA | 0.0000 | 0.0000 | 117 | 571739 | 31 | 0 | [6 empty] | 0.0000
143 | 571765 | D . 607 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 142 | 571764 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
144 | 571766 | D . 607 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 142 | 571764 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
145 | 571767 | D . 607 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 142 | 571764 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
146 | 571768 | D - Flat No 608 | NA | 0.0000 | 0.0000 | 117 | 571739 | 31 | 0 | [6 empty] | 0.0000
147 | 571769 | D . 608 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 146 | 571768 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
148 | 571770 | D . 608 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 146 | 571768 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
149 | 571771 | D . 608 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 146 | 571768 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
150 | 571772 | D - Flat No 609 | NA | 0.0000 | 0.0000 | 117 | 571739 | 31 | 0 | [6 empty] | 0.0000
151 | 571773 | D . 609 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 150 | 571772 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
152 | 571774 | D . 609 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 150 | 571772 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
153 | 571775 | D . 609 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 150 | 571772 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
154 | 571776 | D - Flat No 610 | NA | 0.0000 | 0.0000 | 117 | 571739 | 31 | 0 | [6 empty] | 0.0000
155 | 571777 | D . 610 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 154 | 571776 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
156 | 571778 | D . 610 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 154 | 571776 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
157 | 571779 | D . 610 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 154 | 571776 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
158 | 571780 | D - Flat No 611 | NA | 0.0000 | 0.0000 | 117 | 571739 | 31 | 0 | [6 empty] | 0.0000
159 | 571781 | D . 611 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 158 | 571780 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
160 | 571782 | D . 611 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 158 | 571780 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
161 | 571783 | D . 611 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 158 | 571780 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
162 | 571784 | D - Flat No 612 | NA | 0.0000 | 0.0000 | 117 | 571739 | 31 | 0 | [6 empty] | 0.0000
163 | 571785 | D . 612 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 162 | 571784 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
164 | 571786 | D . 612 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 162 | 571784 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
165 | 571787 | D . 612 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 162 | 571784 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
166 | 571788 | D - Flat No 613 | NA | 0.0000 | 0.0000 | 117 | 571739 | 31 | 0 | [6 empty] | 0.0000
167 | 571789 | D . 613 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 166 | 571788 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
168 | 571790 | D . 613 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 166 | 571788 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
169 | 571791 | D . 613 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 166 | 571788 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
170 | 571792 | D - Flat No 614 | NA | 0.0000 | 0.0000 | 117 | 571739 | 31 | 0 | [6 empty] | 0.0000
171 | 571793 | D . 614 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 170 | 571792 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
172 | 571794 | D . 614 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 170 | 571792 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
173 | 571795 | D . 614 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 170 | 571792 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
174 | 571796 | D - 7th Floor | NA | 0.0000 | 0.0000 | 1 | 571442 | 31 | 0 | [6 empty] | 0.0000
175 | 571797 | D - Flat No 701 | NA | 0.0000 | 0.0000 | 174 | 571796 | 31 | 0 | [6 empty] | 0.0000
176 | 571798 | D - 701 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 175 | 571797 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
177 | 571799 | D - 701 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 175 | 571797 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
178 | 571800 | D - 701 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 175 | 571797 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
179 | 571801 | D - Flat No 702 | NA | 0.0000 | 0.0000 | 174 | 571796 | 31 | 0 | [6 empty] | 0.0000
180 | 571802 | D . 702 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 179 | 571801 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
181 | 571803 | D . 702 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 179 | 571801 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
182 | 571804 | D . 702 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 179 | 571801 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
183 | 571805 | D - Flat No 703 | NA | 0.0000 | 0.0000 | 174 | 571796 | 31 | 0 | [6 empty] | 0.0000
184 | 571806 | D . 703 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 183 | 571805 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
185 | 571807 | D . 703 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 183 | 571805 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
186 | 571808 | D . 703 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 183 | 571805 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
187 | 571809 | D - Flat No 704 | NA | 0.0000 | 0.0000 | 174 | 571796 | 31 | 0 | [6 empty] | 0.0000
188 | 571810 | D . 704 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 187 | 571809 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
189 | 571811 | D . 704 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 187 | 571809 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
190 | 571812 | D . 704 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 187 | 571809 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
191 | 571813 | D - Flat No 705 | NA | 0.0000 | 0.0000 | 174 | 571796 | 31 | 0 | [6 empty] | 0.0000
192 | 571814 | D . 705 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 191 | 571813 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
193 | 571815 | D . 705 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 191 | 571813 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
194 | 571816 | D . 705 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 191 | 571813 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
195 | 571817 | D - Flat No 706 | NA | 0.0000 | 0.0000 | 174 | 571796 | 31 | 0 | [6 empty] | 0.0000
196 | 571818 | D . 706 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 195 | 571817 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
197 | 571819 | D . 706 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 195 | 571817 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
198 | 571820 | D . 706 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 195 | 571817 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
199 | 571821 | D - Flat No 707 | NA | 0.0000 | 0.0000 | 174 | 571796 | 31 | 0 | [6 empty] | 0.0000
200 | 571822 | D . 707 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 199 | 571821 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
201 | 571823 | D . 707 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 199 | 571821 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
202 | 571824 | D . 707 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 199 | 571821 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
203 | 571825 | D - Flat No 708 | NA | 0.0000 | 0.0000 | 174 | 571796 | 31 | 0 | [6 empty] | 0.0000
204 | 571826 | D . 708 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 203 | 571825 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
205 | 571827 | D . 708 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 203 | 571825 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
206 | 571828 | D . 708 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 203 | 571825 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
207 | 571829 | D - Flat No 709 | NA | 0.0000 | 0.0000 | 174 | 571796 | 31 | 0 | [6 empty] | 0.0000
208 | 571830 | D . 709 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 207 | 571829 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
209 | 571831 | D . 709 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 207 | 571829 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
210 | 571832 | D . 709 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 207 | 571829 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
211 | 571833 | D - Flat No 710 | NA | 0.0000 | 0.0000 | 174 | 571796 | 31 | 0 | [6 empty] | 0.0000
212 | 571834 | D . 710 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 211 | 571833 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
213 | 571835 | D . 710 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 211 | 571833 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
214 | 571836 | D . 710 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 211 | 571833 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
215 | 571837 | D - Flat No 711 | NA | 0.0000 | 0.0000 | 174 | 571796 | 31 | 0 | [6 empty] | 0.0000
216 | 571838 | D . 711 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 215 | 571837 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
217 | 571839 | D . 711 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 215 | 571837 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
218 | 571840 | D . 711 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 215 | 571837 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
219 | 571841 | D - Flat No 712 | NA | 0.0000 | 0.0000 | 174 | 571796 | 31 | 0 | [6 empty] | 0.0000
220 | 571842 | D . 712 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 219 | 571841 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
221 | 571843 | D . 712 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 219 | 571841 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
222 | 571844 | D . 712 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 219 | 571841 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
223 | 571845 | D - Flat No 713 | NA | 0.0000 | 0.0000 | 174 | 571796 | 31 | 0 | [6 empty] | 0.0000
224 | 571846 | D . 713 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 223 | 571845 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
225 | 571847 | D . 713 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 223 | 571845 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
226 | 571848 | D . 713 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 223 | 571845 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
227 | 571849 | D - Flat No 714 | NA | 0.0000 | 0.0000 | 174 | 571796 | 31 | 0 | [6 empty] | 0.0000
228 | 571850 | D . 714 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 227 | 571849 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
229 | 571851 | D . 714 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 227 | 571849 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
230 | 571852 | D . 714 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 227 | 571849 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
231 | 571853 | D - 8th Floor | NA | 0.0000 | 0.0000 | 1 | 571442 | 31 | 0 | [6 empty] | 0.0000
232 | 571854 | D - Flat No 801 | NA | 0.0000 | 0.0000 | 231 | 571853 | 31 | 0 | [6 empty] | 0.0000
233 | 571855 | D - 801 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 232 | 571854 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
234 | 571856 | D - 801 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 232 | 571854 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
235 | 571857 | D - 801 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 232 | 571854 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
236 | 571858 | D - Flat No 802 | NA | 0.0000 | 0.0000 | 231 | 571853 | 31 | 0 | [6 empty] | 0.0000
237 | 571859 | D . 802 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 236 | 571858 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
238 | 571860 | D . 802 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 236 | 571858 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
239 | 571861 | D . 802 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 236 | 571858 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
240 | 571862 | D - Flat No 803 | NA | 0.0000 | 0.0000 | 231 | 571853 | 31 | 0 | [6 empty] | 0.0000
241 | 571863 | D . 803 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 240 | 571862 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
242 | 571864 | D . 803 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 240 | 571862 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
243 | 571865 | D . 803 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 240 | 571862 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
244 | 571866 | D - Flat No 804 | NA | 0.0000 | 0.0000 | 231 | 571853 | 31 | 0 | [6 empty] | 0.0000
245 | 571867 | D . 804 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 244 | 571866 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
246 | 571868 | D . 804 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 244 | 571866 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
247 | 571869 | D . 804 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 244 | 571866 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
248 | 571870 | D - Flat No 805 | NA | 0.0000 | 0.0000 | 231 | 571853 | 31 | 0 | [6 empty] | 0.0000
249 | 571871 | D . 805 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 248 | 571870 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
250 | 571872 | D . 805 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 248 | 571870 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
251 | 571873 | D . 805 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 248 | 571870 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
252 | 571874 | D - Flat No 806 | NA | 0.0000 | 0.0000 | 231 | 571853 | 31 | 0 | [6 empty] | 0.0000
253 | 571875 | D . 806 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 252 | 571874 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
254 | 571876 | D . 806 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 252 | 571874 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
255 | 571877 | D . 806 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 252 | 571874 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
256 | 571878 | D - Flat No 807 | NA | 0.0000 | 0.0000 | 231 | 571853 | 31 | 0 | [6 empty] | 0.0000
257 | 571879 | D . 807 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 256 | 571878 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
258 | 571880 | D . 807 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 256 | 571878 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
259 | 571881 | D . 807 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 256 | 571878 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
260 | 571882 | D - Flat No 808 | NA | 0.0000 | 0.0000 | 231 | 571853 | 31 | 0 | [6 empty] | 0.0000
261 | 571883 | D . 808 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 260 | 571882 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
262 | 571884 | D . 808 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 260 | 571882 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
263 | 571885 | D . 808 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 260 | 571882 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
264 | 571886 | D - Flat No 809 | NA | 0.0000 | 0.0000 | 231 | 571853 | 31 | 0 | [6 empty] | 0.0000
265 | 571887 | D . 809 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 264 | 571886 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
266 | 571888 | D . 809 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 264 | 571886 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
267 | 571889 | D . 809 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 264 | 571886 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
268 | 571890 | D - Flat No 810 | NA | 0.0000 | 0.0000 | 231 | 571853 | 31 | 0 | [6 empty] | 0.0000
269 | 571891 | D . 810 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 268 | 571890 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
270 | 571892 | D . 810 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 268 | 571890 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
271 | 571893 | D . 810 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 268 | 571890 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
272 | 571894 | D - Flat No 811 | NA | 0.0000 | 0.0000 | 231 | 571853 | 31 | 0 | [6 empty] | 0.0000
273 | 571895 | D . 811 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 272 | 571894 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
274 | 571896 | D . 811 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 272 | 571894 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
275 | 571897 | D . 811 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 272 | 571894 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
276 | 571898 | D - Flat No 812 | NA | 0.0000 | 0.0000 | 231 | 571853 | 31 | 0 | [6 empty] | 0.0000
277 | 571899 | D . 812 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 276 | 571898 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
278 | 571900 | D . 812 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 276 | 571898 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
279 | 571901 | D . 812 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 276 | 571898 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
280 | 571902 | D - Flat No 813 | NA | 0.0000 | 0.0000 | 231 | 571853 | 31 | 0 | [6 empty] | 0.0000
281 | 571903 | D . 813 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 280 | 571902 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
282 | 571904 | D . 813 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 280 | 571902 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
283 | 571905 | D . 813 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 280 | 571902 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
284 | 571906 | D - Flat No 814 | NA | 0.0000 | 0.0000 | 231 | 571853 | 31 | 0 | [6 empty] | 0.0000
285 | 571907 | D . 814 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 284 | 571906 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
286 | 571908 | D . 814 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 284 | 571906 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
287 | 571909 | D . 814 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 284 | 571906 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000