## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 576555 | G- 7th Floor | NA | 0.0000 | 0.0000 | 0 | 557089 | 31 | 0 | [6 empty] | 0.0000
2 | 576556 | G- 701 Flooring Work | NA | 0.0000 | 0.0000 | 1 | 576555 | 31 | 0 | [6 empty] | 0.0000
3 | 576557 | G. 701 Internal Flat Vitrified Flooring | Sq.Ft | 1.0000 | 1.0000 | 2 | 576556 | 4 | 33553 | G- Internal Flat Vitrified Flooring Work | [5 empty] | 0.0000
4 | 576558 | G. 701 Bath Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 576556 | 4 | 33556 | G- Bath Flooring Work | [5 empty] | 0.0000
5 | 576559 | G. 701 WC Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 576556 | 4 | 33555 | G- WC Flooring Work | [5 empty] | 0.0000
6 | 576560 | G- 702 Flooring Work | NA | 0.0000 | 0.0000 | 1 | 576555 | 31 | 0 | [6 empty] | 0.0000
7 | 576561 | G. 702 Internal Flat Vitrified Flooring | Sq.Ft | 1.0000 | 1.0000 | 6 | 576560 | 4 | 33553 | G- Internal Flat Vitrified Flooring Work | [5 empty] | 0.0000
8 | 576562 | G. 702 Bath Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 576560 | 4 | 33556 | G- Bath Flooring Work | [5 empty] | 0.0000
9 | 576563 | G. 702 WC Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 576560 | 4 | 33555 | G- WC Flooring Work | [5 empty] | 0.0000
10 | 576564 | G- 703 Flooring Work | NA | 0.0000 | 0.0000 | 1 | 576555 | 31 | 0 | [6 empty] | 0.0000
11 | 576565 | G. 703 Internal Flat Vitrified Flooring | Sq.Ft | 1.0000 | 1.0000 | 10 | 576564 | 4 | 33553 | G- Internal Flat Vitrified Flooring Work | [5 empty] | 0.0000
12 | 576566 | G. 703 Bath Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 576564 | 4 | 33556 | G- Bath Flooring Work | [5 empty] | 0.0000
13 | 576567 | G. 703 WC Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 576564 | 4 | 33555 | G- WC Flooring Work | [5 empty] | 0.0000
14 | 576568 | G- 704 Flooring Work | NA | 0.0000 | 0.0000 | 1 | 576555 | 31 | 0 | [6 empty] | 0.0000
15 | 576569 | G. 704 Internal Flat Vitrified Flooring | Sq.Ft | 1.0000 | 1.0000 | 14 | 576568 | 4 | 33553 | G- Internal Flat Vitrified Flooring Work | [5 empty] | 0.0000
16 | 576570 | G. 704 Bath Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 576568 | 4 | 33556 | G- Bath Flooring Work | [5 empty] | 0.0000
17 | 576571 | G. 704 WC Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 576568 | 4 | 33555 | G- WC Flooring Work | [5 empty] | 0.0000
18 | 576572 | G- 705 Flooring Work | NA | 0.0000 | 0.0000 | 1 | 576555 | 31 | 0 | [6 empty] | 0.0000
19 | 576573 | G. 705 Internal Flat Vitrified Flooring | Sq.Ft | 1.0000 | 1.0000 | 18 | 576572 | 4 | 33553 | G- Internal Flat Vitrified Flooring Work | [5 empty] | 0.0000
20 | 576574 | G. 705 Bath Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 576572 | 4 | 33556 | G- Bath Flooring Work | [5 empty] | 0.0000
21 | 576575 | G. 705 WC Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 576572 | 4 | 33555 | G- WC Flooring Work | [5 empty] | 0.0000
22 | 576576 | G- 706 Flooring Work | NA | 0.0000 | 0.0000 | 1 | 576555 | 31 | 0 | [6 empty] | 0.0000
23 | 576577 | G. 706 Internal Flat Vitrified Flooring | Sq.Ft | 1.0000 | 1.0000 | 22 | 576576 | 4 | 33553 | G- Internal Flat Vitrified Flooring Work | [5 empty] | 0.0000
24 | 576578 | G. 706 Bath Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 576576 | 4 | 33556 | G- Bath Flooring Work | [5 empty] | 0.0000
25 | 576579 | G. 706 WC Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 576576 | 4 | 33555 | G- WC Flooring Work | [5 empty] | 0.0000
26 | 576580 | G- 707 Flooring Work | NA | 0.0000 | 0.0000 | 1 | 576555 | 31 | 0 | [6 empty] | 0.0000
27 | 576581 | G. 707 Internal Flat Vitrified Flooring | Sq.Ft | 1.0000 | 1.0000 | 26 | 576580 | 4 | 33553 | G- Internal Flat Vitrified Flooring Work | [5 empty] | 0.0000
28 | 576582 | G. 707 Bath Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 576580 | 4 | 33556 | G- Bath Flooring Work | [5 empty] | 0.0000
29 | 576583 | G. 707 WC Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 576580 | 4 | 33555 | G- WC Flooring Work | [5 empty] | 0.0000
30 | 576584 | G- 708 Flooring Work | NA | 0.0000 | 0.0000 | 1 | 576555 | 31 | 0 | [6 empty] | 0.0000
31 | 576585 | G. 708 Internal Flat Vitrified Flooring | Sq.Ft | 1.0000 | 1.0000 | 30 | 576584 | 4 | 33553 | G- Internal Flat Vitrified Flooring Work | [5 empty] | 0.0000
32 | 576586 | G. 708 Bath Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 576584 | 4 | 33556 | G- Bath Flooring Work | [5 empty] | 0.0000
33 | 576587 | G. 708 WC Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 576584 | 4 | 33555 | G- WC Flooring Work | [5 empty] | 0.0000
34 | 576588 | G- 709 Flooring Work | NA | 0.0000 | 0.0000 | 1 | 576555 | 31 | 0 | [6 empty] | 0.0000
35 | 576589 | G. 709 Internal Flat Vitrified Flooring | Sq.Ft | 1.0000 | 1.0000 | 34 | 576588 | 4 | 33553 | G- Internal Flat Vitrified Flooring Work | [5 empty] | 0.0000
36 | 576590 | G. 709 Bath Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 576588 | 4 | 33556 | G- Bath Flooring Work | [5 empty] | 0.0000
37 | 576591 | G. 709 WC Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 576588 | 4 | 33555 | G- WC Flooring Work | [5 empty] | 0.0000
38 | 576592 | G- 710 Flooring Work | NA | 0.0000 | 0.0000 | 1 | 576555 | 31 | 0 | [6 empty] | 0.0000
39 | 576593 | G. 710 Internal Flat Vitrified Flooring | Sq.Ft | 1.0000 | 1.0000 | 38 | 576592 | 4 | 33553 | G- Internal Flat Vitrified Flooring Work | [5 empty] | 0.0000
40 | 576594 | G. 710 Bath Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 576592 | 4 | 33556 | G- Bath Flooring Work | [5 empty] | 0.0000
41 | 576595 | G. 710 WC Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 576592 | 4 | 33555 | G- WC Flooring Work | [5 empty] | 0.0000
42 | 576596 | G- 711 Flooring Work | NA | 0.0000 | 0.0000 | 1 | 576555 | 31 | 0 | [6 empty] | 0.0000
43 | 576597 | G. 711 Internal Flat Vitrified Flooring | Sq.Ft | 1.0000 | 1.0000 | 42 | 576596 | 4 | 33553 | G- Internal Flat Vitrified Flooring Work | [5 empty] | 0.0000
44 | 576598 | G. 711 Bath Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 42 | 576596 | 4 | 33556 | G- Bath Flooring Work | [5 empty] | 0.0000
45 | 576599 | G. 711 WC Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 42 | 576596 | 4 | 33555 | G- WC Flooring Work | [5 empty] | 0.0000
46 | 576600 | G- 712 Flooring Work | NA | 0.0000 | 0.0000 | 1 | 576555 | 31 | 0 | [6 empty] | 0.0000
47 | 576601 | G. 712 Internal Flat Vitrified Flooring | Sq.Ft | 1.0000 | 1.0000 | 46 | 576600 | 4 | 33553 | G- Internal Flat Vitrified Flooring Work | [5 empty] | 0.0000
48 | 576602 | G. 712 Bath Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 576600 | 4 | 33556 | G- Bath Flooring Work | [5 empty] | 0.0000
49 | 576603 | G. 712 WC Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 576600 | 4 | 33555 | G- WC Flooring Work | [5 empty] | 0.0000
50 | 576604 | G- 713 Flooring Work | NA | 0.0000 | 0.0000 | 1 | 576555 | 31 | 0 | [6 empty] | 0.0000
51 | 576605 | G. 713 Internal Flat Vitrified Flooring | Sq.Ft | 1.0000 | 1.0000 | 50 | 576604 | 4 | 33553 | G- Internal Flat Vitrified Flooring Work | [5 empty] | 0.0000
52 | 576606 | G. 713 Bath Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 576604 | 4 | 33556 | G- Bath Flooring Work | [5 empty] | 0.0000
53 | 576607 | G. 713 WC Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 576604 | 4 | 33555 | G- WC Flooring Work | [5 empty] | 0.0000
54 | 576608 | G- 714 Flooring Work | NA | 0.0000 | 0.0000 | 1 | 576555 | 31 | 0 | [6 empty] | 0.0000
55 | 576609 | G. 714 Internal Flat Vitrified Flooring | Sq.Ft | 1.0000 | 1.0000 | 54 | 576608 | 4 | 33553 | G- Internal Flat Vitrified Flooring Work | [5 empty] | 0.0000
56 | 576610 | G. 714 Bath Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 54 | 576608 | 4 | 33556 | G- Bath Flooring Work | [5 empty] | 0.0000
57 | 576611 | G. 714 WC Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 54 | 576608 | 4 | 33555 | G- WC Flooring Work | [5 empty] | 0.0000