## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor | Selected Group :- G- 7th Floor
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 578100 | G- 7th Floor | NA | 0.0000 | 0.0000 | 0 | 557992 | 31 | 0 | [6 empty] | 0.0000
2 | 578101 | G- 701 Dado Work | NA | 0.0000 | 0.0000 | 1 | 578100 | 31 | 0 | [6 empty] | 0.0000
3 | 578102 | G- 701 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 578101 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
4 | 578103 | G- 701 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 578101 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
5 | 578104 | G- 701 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 578101 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
6 | 578105 | G- 702 Dado Work | NA | 0.0000 | 0.0000 | 1 | 578100 | 31 | 0 | [6 empty] | 0.0000
7 | 578106 | G. 702 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 578105 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
8 | 578107 | G. 702 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 578105 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
9 | 578108 | G. 702 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 578105 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
10 | 578109 | G- 703 Dado Work | NA | 0.0000 | 0.0000 | 1 | 578100 | 31 | 0 | [6 empty] | 0.0000
11 | 578110 | G. 703 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 578109 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
12 | 578111 | G. 703 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 578109 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
13 | 578112 | G. 703 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 578109 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
14 | 578113 | G- 704 Dado Work | NA | 0.0000 | 0.0000 | 1 | 578100 | 31 | 0 | [6 empty] | 0.0000
15 | 578114 | G. 704 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 578113 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
16 | 578115 | G. 704 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 578113 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
17 | 578116 | G. 704 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 578113 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
18 | 578117 | G- 705 Dado Work | NA | 0.0000 | 0.0000 | 1 | 578100 | 31 | 0 | [6 empty] | 0.0000
19 | 578118 | G. 705 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 578117 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
20 | 578119 | G. 705 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 578117 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
21 | 578120 | G. 705 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 578117 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
22 | 578121 | G- 706 Dado Work | NA | 0.0000 | 0.0000 | 1 | 578100 | 31 | 0 | [6 empty] | 0.0000
23 | 578122 | G. 706 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 578121 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
24 | 578123 | G. 706 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 578121 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
25 | 578124 | G. 706 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 578121 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
26 | 578125 | G- 707 Dado Work | NA | 0.0000 | 0.0000 | 1 | 578100 | 31 | 0 | [6 empty] | 0.0000
27 | 578126 | G. 707 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 578125 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
28 | 578127 | G. 707 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 578125 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
29 | 578128 | G. 707 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 578125 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
30 | 578129 | G- 708 Dado Work | NA | 0.0000 | 0.0000 | 1 | 578100 | 31 | 0 | [6 empty] | 0.0000
31 | 578130 | G. 708 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 578129 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
32 | 578131 | G. 708 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 578129 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
33 | 578132 | G. 708 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 578129 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
34 | 578133 | G- 709 Dado Work | NA | 0.0000 | 0.0000 | 1 | 578100 | 31 | 0 | [6 empty] | 0.0000
35 | 578134 | G. 709 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 578133 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
36 | 578135 | G. 709 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 578133 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
37 | 578136 | G. 709 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 578133 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
38 | 578137 | G- 710 Dado Work | NA | 0.0000 | 0.0000 | 1 | 578100 | 31 | 0 | [6 empty] | 0.0000
39 | 578138 | G. 710 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 578137 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
40 | 578139 | G. 710 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 578137 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
41 | 578140 | G. 710 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 578137 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
42 | 578141 | G- 711 Dado Work | NA | 0.0000 | 0.0000 | 1 | 578100 | 31 | 0 | [6 empty] | 0.0000
43 | 578142 | G. 711 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 42 | 578141 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
44 | 578143 | G. 711 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 42 | 578141 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
45 | 578144 | G. 711 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 42 | 578141 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
46 | 578145 | G- 712 Dado Work | NA | 0.0000 | 0.0000 | 1 | 578100 | 31 | 0 | [6 empty] | 0.0000
47 | 578146 | G. 712 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 578145 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
48 | 578147 | G. 712 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 578145 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
49 | 578148 | G. 712 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 578145 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
50 | 578149 | G- 713 Dado Work | NA | 0.0000 | 0.0000 | 1 | 578100 | 31 | 0 | [6 empty] | 0.0000
51 | 578150 | G. 713 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 578149 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
52 | 578151 | G. 713 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 578149 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
53 | 578152 | G. 713 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 578149 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000
54 | 578153 | G- 714 Dado Work | NA | 0.0000 | 0.0000 | 1 | 578100 | 31 | 0 | [6 empty] | 0.0000
55 | 578154 | G. 714 Kitchen Dado Work | Sq.Ft | 1.0000 | 1.0000 | 54 | 578153 | 4 | 33559 | G- 101 Kitchen Dado Work | [5 empty] | 0.0000
56 | 578155 | G. 714 Bath Dado Work | Sq.Ft | 1.0000 | 1.0000 | 54 | 578153 | 4 | 33561 | G- 101 Bath Dado Work | [5 empty] | 0.0000
57 | 578156 | G. 714 WC Dado Work | Sq.Ft | 1.0000 | 1.0000 | 54 | 578153 | 4 | 33560 | G- 101 WC Dado Work | [5 empty] | 0.0000