## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- E - Waterproofing Work | Selected Group :- E - Waterproofing Work | Selected Group :- E - Waterproofing Work | Selected Group :- E - Waterproofing Work | Selected Group :- E - Waterproofing Work | Selected Group :- E - Waterproofing Work | Selected Group :- E - Waterproofing Work | Selected Group :- E - Waterproofing Work | Selected Group :- E - Waterproofing Work | Selected Group :- E - Waterproofing Work | Selected Group :- E - Waterproofing Work | Selected Group :- E - Waterproofing Work | Selected Group :- E - Waterproofing Work | Selected Group :- E - Waterproofing Work | Selected Group :- E - Waterproofing Work | Selected Group :- E - Waterproofing Work | Selected Group :- E - Waterproofing Work
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 588354 | E - Waterproofing Work | NA | 0.0000 | 0.0000 | 0 | 550108 | 31 | 0 | [6 empty] | 0.0000
2 | 588355 | E - Waterproofing (M) | NA | 0.0000 | 0.0000 | 1 | 588354 | 31 | 0 | [6 empty] | 0.0000
3 | 588356 | E - 3rE Floor | NA | 0.0000 | 0.0000 | 2 | 588355 | 31 | 0 | [6 empty] | 0.0000
4 | 588357 | E - 4th Floor | NA | 0.0000 | 0.0000 | 2 | 588355 | 31 | 0 | [6 empty] | 0.0000
5 | 588358 | E - Flat No 401 | NA | 0.0000 | 0.0000 | 4 | 588357 | 31 | 0 | [6 empty] | 0.0000
6 | 588359 | E - 401 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 5 | 588358 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
7 | 588360 | E - 401 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 5 | 588358 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
8 | 588361 | E - 401 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 5 | 588358 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
9 | 588362 | E - Flat No 402 | NA | 0.0000 | 0.0000 | 4 | 588357 | 31 | 0 | [6 empty] | 0.0000
10 | 588363 | E . 402 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 9 | 588362 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
11 | 588364 | E . 402 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 9 | 588362 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
12 | 588365 | E . 402 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 9 | 588362 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
13 | 588366 | E - Flat No 403 | NA | 0.0000 | 0.0000 | 4 | 588357 | 31 | 0 | [6 empty] | 0.0000
14 | 588367 | E . 403 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 13 | 588366 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
15 | 588368 | E . 403 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 13 | 588366 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
16 | 588369 | E . 403 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 13 | 588366 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
17 | 588370 | E - Flat No 404 | NA | 0.0000 | 0.0000 | 4 | 588357 | 31 | 0 | [6 empty] | 0.0000
18 | 588371 | E . 404 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 17 | 588370 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
19 | 588372 | E . 404 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 17 | 588370 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
20 | 588373 | E . 404 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 17 | 588370 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
21 | 588374 | E - Flat No 405 | NA | 0.0000 | 0.0000 | 4 | 588357 | 31 | 0 | [6 empty] | 0.0000
22 | 588375 | E . 405 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 21 | 588374 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
23 | 588376 | E . 405 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 21 | 588374 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
24 | 588377 | E . 405 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 21 | 588374 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
25 | 588378 | E - Flat No 406 | NA | 0.0000 | 0.0000 | 4 | 588357 | 31 | 0 | [6 empty] | 0.0000
26 | 588379 | E . 406 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 25 | 588378 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
27 | 588380 | E . 406 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 25 | 588378 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
28 | 588381 | E . 406 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 25 | 588378 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
29 | 588382 | E - Flat No 407 | NA | 0.0000 | 0.0000 | 4 | 588357 | 31 | 0 | [6 empty] | 0.0000
30 | 588383 | E . 407 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 29 | 588382 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
31 | 588384 | E . 407 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 29 | 588382 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
32 | 588385 | E . 407 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 29 | 588382 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
33 | 588386 | E - Flat No 408 | NA | 0.0000 | 0.0000 | 4 | 588357 | 31 | 0 | [6 empty] | 0.0000
34 | 588387 | E . 408 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 33 | 588386 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
35 | 588388 | E . 408 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 33 | 588386 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
36 | 588389 | E . 408 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 33 | 588386 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
37 | 588390 | E - Flat No 409 | NA | 0.0000 | 0.0000 | 4 | 588357 | 31 | 0 | [6 empty] | 0.0000
38 | 588391 | E . 409 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 37 | 588390 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
39 | 588392 | E . 409 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 37 | 588390 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
40 | 588393 | E . 409 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 37 | 588390 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
41 | 588394 | E - Flat No 410 | NA | 0.0000 | 0.0000 | 4 | 588357 | 31 | 0 | [6 empty] | 0.0000
42 | 588395 | E . 410 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 41 | 588394 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
43 | 588396 | E . 410 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 41 | 588394 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
44 | 588397 | E . 410 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 41 | 588394 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
45 | 588398 | E - Flat No 411 | NA | 0.0000 | 0.0000 | 4 | 588357 | 31 | 0 | [6 empty] | 0.0000
46 | 588399 | E . 411 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 45 | 588398 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
47 | 588400 | E . 411 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 45 | 588398 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
48 | 588401 | E . 411 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 45 | 588398 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
49 | 588402 | E - Flat No 412 | NA | 0.0000 | 0.0000 | 4 | 588357 | 31 | 0 | [6 empty] | 0.0000
50 | 588403 | E . 412 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 49 | 588402 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
51 | 588404 | E . 412 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 49 | 588402 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
52 | 588405 | E . 412 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 49 | 588402 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
53 | 588406 | E - Flat No 413 | NA | 0.0000 | 0.0000 | 4 | 588357 | 31 | 0 | [6 empty] | 0.0000
54 | 588407 | E . 413 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 53 | 588406 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
55 | 588408 | E . 413 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 53 | 588406 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
56 | 588409 | E . 413 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 53 | 588406 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
57 | 588410 | E - Flat No 414 | NA | 0.0000 | 0.0000 | 4 | 588357 | 31 | 0 | [6 empty] | 0.0000
58 | 588411 | E . 414 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 57 | 588410 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
59 | 588412 | E . 414 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 57 | 588410 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
60 | 588413 | E . 414 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 57 | 588410 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
61 | 588414 | E - 5th Floor | NA | 0.0000 | 0.0000 | 2 | 588355 | 31 | 0 | [6 empty] | 0.0000
62 | 588415 | E - Flat No 501 | NA | 0.0000 | 0.0000 | 61 | 588414 | 31 | 0 | [6 empty] | 0.0000
63 | 588416 | E - 501 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 62 | 588415 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
64 | 588417 | E - 501 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 62 | 588415 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
65 | 588418 | E - 501 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 62 | 588415 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
66 | 588419 | E - Flat No 502 | NA | 0.0000 | 0.0000 | 61 | 588414 | 31 | 0 | [6 empty] | 0.0000
67 | 588420 | E . 502 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 66 | 588419 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
68 | 588421 | E . 502 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 66 | 588419 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
69 | 588422 | E . 502 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 66 | 588419 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
70 | 588423 | E - Flat No 503 | NA | 0.0000 | 0.0000 | 61 | 588414 | 31 | 0 | [6 empty] | 0.0000
71 | 588424 | E . 503 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 70 | 588423 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
72 | 588425 | E . 503 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 70 | 588423 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
73 | 588426 | E . 503 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 70 | 588423 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
74 | 588427 | E - Flat No 504 | NA | 0.0000 | 0.0000 | 61 | 588414 | 31 | 0 | [6 empty] | 0.0000
75 | 588428 | E . 504 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 74 | 588427 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
76 | 588429 | E . 504 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 74 | 588427 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
77 | 588430 | E . 504 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 74 | 588427 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
78 | 588431 | E - Flat No 505 | NA | 0.0000 | 0.0000 | 61 | 588414 | 31 | 0 | [6 empty] | 0.0000
79 | 588432 | E . 505 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 78 | 588431 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
80 | 588433 | E . 505 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 78 | 588431 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
81 | 588434 | E . 505 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 78 | 588431 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
82 | 588435 | E - Flat No 506 | NA | 0.0000 | 0.0000 | 61 | 588414 | 31 | 0 | [6 empty] | 0.0000
83 | 588436 | E . 506 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 82 | 588435 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
84 | 588437 | E . 506 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 82 | 588435 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
85 | 588438 | E . 506 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 82 | 588435 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
86 | 588439 | E - Flat No 507 | NA | 0.0000 | 0.0000 | 61 | 588414 | 31 | 0 | [6 empty] | 0.0000
87 | 588440 | E . 507 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 86 | 588439 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
88 | 588441 | E . 507 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 86 | 588439 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
89 | 588442 | E . 507 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 86 | 588439 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
90 | 588443 | E - Flat No 508 | NA | 0.0000 | 0.0000 | 61 | 588414 | 31 | 0 | [6 empty] | 0.0000
91 | 588444 | E . 508 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 90 | 588443 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
92 | 588445 | E . 508 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 90 | 588443 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
93 | 588446 | E . 508 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 90 | 588443 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
94 | 588447 | E - Flat No 509 | NA | 0.0000 | 0.0000 | 61 | 588414 | 31 | 0 | [6 empty] | 0.0000
95 | 588448 | E . 509 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 94 | 588447 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
96 | 588449 | E . 509 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 94 | 588447 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
97 | 588450 | E . 509 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 94 | 588447 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
98 | 588451 | E - Flat No 510 | NA | 0.0000 | 0.0000 | 61 | 588414 | 31 | 0 | [6 empty] | 0.0000
99 | 588452 | E . 510 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 98 | 588451 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
100 | 588453 | E . 510 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 98 | 588451 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
101 | 588454 | E . 510 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 98 | 588451 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
102 | 588455 | E - Flat No 511 | NA | 0.0000 | 0.0000 | 61 | 588414 | 31 | 0 | [6 empty] | 0.0000
103 | 588456 | E . 511 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 102 | 588455 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
104 | 588457 | E . 511 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 102 | 588455 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
105 | 588458 | E . 511 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 102 | 588455 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
106 | 588459 | E - Flat No 512 | NA | 0.0000 | 0.0000 | 61 | 588414 | 31 | 0 | [6 empty] | 0.0000
107 | 588460 | E . 512 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 106 | 588459 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
108 | 588461 | E . 512 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 106 | 588459 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
109 | 588462 | E . 512 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 106 | 588459 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
110 | 588463 | E - Flat No 513 | NA | 0.0000 | 0.0000 | 61 | 588414 | 31 | 0 | [6 empty] | 0.0000
111 | 588464 | E . 513 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 110 | 588463 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
112 | 588465 | E . 513 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 110 | 588463 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
113 | 588466 | E . 513 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 110 | 588463 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
114 | 588467 | E - Flat No 514 | NA | 0.0000 | 0.0000 | 61 | 588414 | 31 | 0 | [6 empty] | 0.0000
115 | 588468 | E . 514 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 114 | 588467 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
116 | 588469 | E . 514 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 114 | 588467 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
117 | 588470 | E . 514 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 114 | 588467 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
118 | 588471 | E - 6th Floor | NA | 0.0000 | 0.0000 | 2 | 588355 | 31 | 0 | [6 empty] | 0.0000
119 | 588472 | E - Flat No 601 | NA | 0.0000 | 0.0000 | 118 | 588471 | 31 | 0 | [6 empty] | 0.0000
120 | 588473 | E - 601 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 119 | 588472 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
121 | 588474 | E - 601 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 119 | 588472 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
122 | 588475 | E - 601 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 119 | 588472 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
123 | 588476 | E - Flat No 602 | NA | 0.0000 | 0.0000 | 118 | 588471 | 31 | 0 | [6 empty] | 0.0000
124 | 588477 | E . 602 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 123 | 588476 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
125 | 588478 | E . 602 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 123 | 588476 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
126 | 588479 | E . 602 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 123 | 588476 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
127 | 588480 | E - Flat No 603 | NA | 0.0000 | 0.0000 | 118 | 588471 | 31 | 0 | [6 empty] | 0.0000
128 | 588481 | E . 603 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 127 | 588480 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
129 | 588482 | E . 603 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 127 | 588480 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
130 | 588483 | E . 603 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 127 | 588480 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
131 | 588484 | E - Flat No 604 | NA | 0.0000 | 0.0000 | 118 | 588471 | 31 | 0 | [6 empty] | 0.0000
132 | 588485 | E . 604 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 131 | 588484 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
133 | 588486 | E . 604 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 131 | 588484 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
134 | 588487 | E . 604 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 131 | 588484 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
135 | 588488 | E - Flat No 605 | NA | 0.0000 | 0.0000 | 118 | 588471 | 31 | 0 | [6 empty] | 0.0000
136 | 588489 | E . 605 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 135 | 588488 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
137 | 588490 | E . 605 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 135 | 588488 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
138 | 588491 | E . 605 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 135 | 588488 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
139 | 588492 | E - Flat No 606 | NA | 0.0000 | 0.0000 | 118 | 588471 | 31 | 0 | [6 empty] | 0.0000
140 | 588493 | E . 606 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 139 | 588492 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
141 | 588494 | E . 606 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 139 | 588492 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
142 | 588495 | E . 606 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 139 | 588492 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
143 | 588496 | E - Flat No 607 | NA | 0.0000 | 0.0000 | 118 | 588471 | 31 | 0 | [6 empty] | 0.0000
144 | 588497 | E . 607 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 143 | 588496 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
145 | 588498 | E . 607 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 143 | 588496 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
146 | 588499 | E . 607 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 143 | 588496 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
147 | 588500 | E - Flat No 608 | NA | 0.0000 | 0.0000 | 118 | 588471 | 31 | 0 | [6 empty] | 0.0000
148 | 588501 | E . 608 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 147 | 588500 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
149 | 588502 | E . 608 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 147 | 588500 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
150 | 588503 | E . 608 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 147 | 588500 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
151 | 588504 | E - Flat No 609 | NA | 0.0000 | 0.0000 | 118 | 588471 | 31 | 0 | [6 empty] | 0.0000
152 | 588505 | E . 609 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 151 | 588504 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
153 | 588506 | E . 609 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 151 | 588504 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
154 | 588507 | E . 609 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 151 | 588504 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
155 | 588508 | E - Flat No 610 | NA | 0.0000 | 0.0000 | 118 | 588471 | 31 | 0 | [6 empty] | 0.0000
156 | 588509 | E . 610 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 155 | 588508 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
157 | 588510 | E . 610 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 155 | 588508 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
158 | 588511 | E . 610 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 155 | 588508 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
159 | 588512 | E - Flat No 611 | NA | 0.0000 | 0.0000 | 118 | 588471 | 31 | 0 | [6 empty] | 0.0000
160 | 588513 | E . 611 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 159 | 588512 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
161 | 588514 | E . 611 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 159 | 588512 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
162 | 588515 | E . 611 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 159 | 588512 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
163 | 588516 | E - Flat No 612 | NA | 0.0000 | 0.0000 | 118 | 588471 | 31 | 0 | [6 empty] | 0.0000
164 | 588517 | E . 612 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 163 | 588516 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
165 | 588518 | E . 612 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 163 | 588516 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
166 | 588519 | E . 612 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 163 | 588516 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
167 | 588520 | E - Flat No 613 | NA | 0.0000 | 0.0000 | 118 | 588471 | 31 | 0 | [6 empty] | 0.0000
168 | 588521 | E . 613 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 167 | 588520 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
169 | 588522 | E . 613 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 167 | 588520 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
170 | 588523 | E . 613 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 167 | 588520 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
171 | 588524 | E - Flat No 614 | NA | 0.0000 | 0.0000 | 118 | 588471 | 31 | 0 | [6 empty] | 0.0000
172 | 588525 | E . 614 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 171 | 588524 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
173 | 588526 | E . 614 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 171 | 588524 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
174 | 588527 | E . 614 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 171 | 588524 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
175 | 588528 | E - 7th Floor | NA | 0.0000 | 0.0000 | 2 | 588355 | 31 | 0 | [6 empty] | 0.0000
176 | 588529 | E - Flat No 701 | NA | 0.0000 | 0.0000 | 175 | 588528 | 31 | 0 | [6 empty] | 0.0000
177 | 588530 | E - 701 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 176 | 588529 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
178 | 588531 | E - 701 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 176 | 588529 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
179 | 588532 | E - 701 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 176 | 588529 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
180 | 588533 | E - Flat No 702 | NA | 0.0000 | 0.0000 | 175 | 588528 | 31 | 0 | [6 empty] | 0.0000
181 | 588534 | E . 702 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 180 | 588533 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
182 | 588535 | E . 702 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 180 | 588533 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
183 | 588536 | E . 702 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 180 | 588533 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
184 | 588537 | E - Flat No 703 | NA | 0.0000 | 0.0000 | 175 | 588528 | 31 | 0 | [6 empty] | 0.0000
185 | 588538 | E . 703 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 184 | 588537 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
186 | 588539 | E . 703 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 184 | 588537 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
187 | 588540 | E . 703 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 184 | 588537 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
188 | 588541 | E - Flat No 704 | NA | 0.0000 | 0.0000 | 175 | 588528 | 31 | 0 | [6 empty] | 0.0000
189 | 588542 | E . 704 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 188 | 588541 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
190 | 588543 | E . 704 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 188 | 588541 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
191 | 588544 | E . 704 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 188 | 588541 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
192 | 588545 | E - Flat No 705 | NA | 0.0000 | 0.0000 | 175 | 588528 | 31 | 0 | [6 empty] | 0.0000
193 | 588546 | E . 705 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 192 | 588545 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
194 | 588547 | E . 705 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 192 | 588545 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
195 | 588548 | E . 705 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 192 | 588545 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
196 | 588549 | E - Flat No 706 | NA | 0.0000 | 0.0000 | 175 | 588528 | 31 | 0 | [6 empty] | 0.0000
197 | 588550 | E . 706 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 196 | 588549 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
198 | 588551 | E . 706 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 196 | 588549 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
199 | 588552 | E . 706 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 196 | 588549 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
200 | 588553 | E - Flat No 707 | NA | 0.0000 | 0.0000 | 175 | 588528 | 31 | 0 | [6 empty] | 0.0000
201 | 588554 | E . 707 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 200 | 588553 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
202 | 588555 | E . 707 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 200 | 588553 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
203 | 588556 | E . 707 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 200 | 588553 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
204 | 588557 | E - Flat No 708 | NA | 0.0000 | 0.0000 | 175 | 588528 | 31 | 0 | [6 empty] | 0.0000
205 | 588558 | E . 708 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 204 | 588557 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
206 | 588559 | E . 708 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 204 | 588557 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
207 | 588560 | E . 708 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 204 | 588557 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
208 | 588561 | E - Flat No 709 | NA | 0.0000 | 0.0000 | 175 | 588528 | 31 | 0 | [6 empty] | 0.0000
209 | 588562 | E . 709 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 208 | 588561 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
210 | 588563 | E . 709 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 208 | 588561 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
211 | 588564 | E . 709 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 208 | 588561 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
212 | 588565 | E - Flat No 710 | NA | 0.0000 | 0.0000 | 175 | 588528 | 31 | 0 | [6 empty] | 0.0000
213 | 588566 | E . 710 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 212 | 588565 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
214 | 588567 | E . 710 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 212 | 588565 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
215 | 588568 | E . 710 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 212 | 588565 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
216 | 588569 | E - Flat No 711 | NA | 0.0000 | 0.0000 | 175 | 588528 | 31 | 0 | [6 empty] | 0.0000
217 | 588570 | E . 711 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 216 | 588569 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
218 | 588571 | E . 711 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 216 | 588569 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
219 | 588572 | E . 711 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 216 | 588569 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
220 | 588573 | E - Flat No 712 | NA | 0.0000 | 0.0000 | 175 | 588528 | 31 | 0 | [6 empty] | 0.0000
221 | 588574 | E . 712 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 220 | 588573 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
222 | 588575 | E . 712 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 220 | 588573 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
223 | 588576 | E . 712 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 220 | 588573 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
224 | 588577 | E - Flat No 713 | NA | 0.0000 | 0.0000 | 175 | 588528 | 31 | 0 | [6 empty] | 0.0000
225 | 588578 | E . 713 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 224 | 588577 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
226 | 588579 | E . 713 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 224 | 588577 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
227 | 588580 | E . 713 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 224 | 588577 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
228 | 588581 | E - Flat No 714 | NA | 0.0000 | 0.0000 | 175 | 588528 | 31 | 0 | [6 empty] | 0.0000
229 | 588582 | E . 714 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 228 | 588581 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
230 | 588583 | E . 714 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 228 | 588581 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
231 | 588584 | E . 714 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 228 | 588581 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
232 | 588585 | E - 8th Floor | NA | 0.0000 | 0.0000 | 2 | 588355 | 31 | 0 | [6 empty] | 0.0000
233 | 588586 | E - Flat No 801 | NA | 0.0000 | 0.0000 | 232 | 588585 | 31 | 0 | [6 empty] | 0.0000
234 | 588587 | E - 801 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 233 | 588586 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
235 | 588588 | E - 801 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 233 | 588586 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
236 | 588589 | E - 801 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 233 | 588586 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
237 | 588590 | E - Flat No 802 | NA | 0.0000 | 0.0000 | 232 | 588585 | 31 | 0 | [6 empty] | 0.0000
238 | 588591 | E . 802 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 237 | 588590 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
239 | 588592 | E . 802 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 237 | 588590 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
240 | 588593 | E . 802 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 237 | 588590 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
241 | 588594 | E - Flat No 803 | NA | 0.0000 | 0.0000 | 232 | 588585 | 31 | 0 | [6 empty] | 0.0000
242 | 588595 | E . 803 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 241 | 588594 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
243 | 588596 | E . 803 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 241 | 588594 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
244 | 588597 | E . 803 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 241 | 588594 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
245 | 588598 | E - Flat No 804 | NA | 0.0000 | 0.0000 | 232 | 588585 | 31 | 0 | [6 empty] | 0.0000
246 | 588599 | E . 804 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 245 | 588598 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
247 | 588600 | E . 804 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 245 | 588598 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
248 | 588601 | E . 804 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 245 | 588598 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
249 | 588602 | E - Flat No 805 | NA | 0.0000 | 0.0000 | 232 | 588585 | 31 | 0 | [6 empty] | 0.0000
250 | 588603 | E . 805 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 249 | 588602 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
251 | 588604 | E . 805 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 249 | 588602 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
252 | 588605 | E . 805 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 249 | 588602 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
253 | 588606 | E - Flat No 810 | NA | 0.0000 | 0.0000 | 232 | 588585 | 31 | 0 | [6 empty] | 0.0000
254 | 588607 | E . 810 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 253 | 588606 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
255 | 588608 | E . 810 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 253 | 588606 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
256 | 588609 | E . 810 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 253 | 588606 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
257 | 588610 | E - Flat No 811 | NA | 0.0000 | 0.0000 | 232 | 588585 | 31 | 0 | [6 empty] | 0.0000
258 | 588611 | E . 811 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 257 | 588610 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
259 | 588612 | E . 811 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 257 | 588610 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
260 | 588613 | E . 811 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 257 | 588610 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
261 | 588614 | E - Flat No 812 | NA | 0.0000 | 0.0000 | 232 | 588585 | 31 | 0 | [6 empty] | 0.0000
262 | 588615 | E . 812 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 261 | 588614 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
263 | 588616 | E . 812 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 261 | 588614 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
264 | 588617 | E . 812 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 261 | 588614 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
265 | 588618 | E - Flat No 813 | NA | 0.0000 | 0.0000 | 232 | 588585 | 31 | 0 | [6 empty] | 0.0000
266 | 588619 | E . 813 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 265 | 588618 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
267 | 588620 | E . 813 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 265 | 588618 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
268 | 588621 | E . 813 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 265 | 588618 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
269 | 588622 | E - Flat No 814 | NA | 0.0000 | 0.0000 | 232 | 588585 | 31 | 0 | [6 empty] | 0.0000
270 | 588623 | E . 814 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 269 | 588622 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
271 | 588624 | E . 814 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 269 | 588622 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
272 | 588625 | E . 814 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 269 | 588622 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000