## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2 | Selected Group :- G - Staircase 2
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 591344 | C - Staircase 2 | NA | 0.0000 | 0.0000 | 0 | 591329 | 31 | 0 | [6 empty] | 0.0000
2 | 591345 | C - 3rd Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 1 | 591344 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
3 | 591346 | C . 4th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 1 | 591344 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
4 | 591347 | C . 5th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 1 | 591344 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
5 | 591348 | C . 6th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 1 | 591344 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
6 | 591349 | C . 7th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 1 | 591344 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
7 | 591350 | C . 8th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 1 | 591344 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
8 | 591351 | C . 9th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 1 | 591344 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
9 | 591352 | C . 10th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 1 | 591344 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
10 | 591353 | C . 11th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 1 | 591344 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
11 | 591354 | C . 12th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 1 | 591344 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
12 | 591355 | C . 13th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 1 | 591344 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
13 | 591356 | C . 14th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 1 | 591344 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000