## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- F - Common Painting Work | Selected Group :- F - Common Painting Work | Selected Group :- F - Common Painting Work | Selected Group :- F - Common Painting Work | Selected Group :- F - Common Painting Work | Selected Group :- F - Common Painting Work | Selected Group :- F - Common Painting Work | Selected Group :- F - Common Painting Work | Selected Group :- F - Common Painting Work | Selected Group :- F - Common Painting Work | Selected Group :- F - Common Painting Work | Selected Group :- F - Common Painting Work | Selected Group :- F - Common Painting Work | Selected Group :- F - Common Painting Work | Selected Group :- F - Common Painting Work | Selected Group :- F - Common Painting Work | Selected Group :- F - Common Painting Work
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 620410 | F - Common Painting Work | NA | 0.0000 | 0.0000 | 0 | 512330 | 31 | 0 | [6 empty] | 0.0000
2 | 620411 | F -Lift Duct Painting | NA | 0.0000 | 0.0000 | 1 | 620410 | 31 | 0 | [6 empty] | 0.0000
3 | 620412 | F - Lift 1 Duct Painting Work | NA | 0.0000 | 0.0000 | 2 | 620411 | 31 | 0 | [6 empty] | 0.0000
4 | 620413 | F -GF Lift 1 Duct Painting Work | Sq.Ft | 182.7100 | 182.7100 | 3 | 620412 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
5 | 620414 | F -1st Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620412 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
6 | 620415 | F -2nd Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620412 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
7 | 620416 | F -3rd Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620412 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
8 | 620417 | F -4th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620412 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
9 | 620418 | F -5th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620412 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
10 | 620419 | F -6th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620412 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
11 | 620420 | F -7th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620412 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
12 | 620421 | F -8th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620412 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
13 | 620422 | F -9th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620412 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
14 | 620423 | F -10th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620412 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
15 | 620424 | F -11th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620412 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
16 | 620425 | F -12th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620412 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
17 | 620426 | F -13th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620412 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
18 | 620427 | F -14th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620412 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
19 | 620428 | F -Terrace Lift 1 Duct Painting Work | Sq.Ft | 232.3900 | 232.3900 | 3 | 620412 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
20 | 620429 | F - Lift 2 Duct Painting Work | NA | 0.0000 | 0.0000 | 2 | 620411 | 31 | 0 | [6 empty] | 0.0000
21 | 620430 | F -GF Lift 2 Duct Painting Work | Sq.Ft | 182.7100 | 182.7100 | 20 | 620429 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
22 | 620431 | F -1st Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620429 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
23 | 620432 | F -2nd Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620429 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
24 | 620433 | F -3rd Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620429 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
25 | 620434 | F -4th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620429 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
26 | 620435 | F -5th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620429 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
27 | 620436 | F -6th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620429 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
28 | 620437 | F -7th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620429 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
29 | 620438 | F -8th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620429 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
30 | 620439 | F -9th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620429 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
31 | 620440 | F -10th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620429 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
32 | 620441 | F -11th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620429 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
33 | 620442 | F -12th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620429 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
34 | 620443 | F -13th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620429 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
35 | 620444 | F -14th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620429 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
36 | 620445 | F -Terrace Lift 2 Duct Painting Work | Sq.Ft | 232.3900 | 232.3900 | 20 | 620429 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000