## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 620447 | D - Common Painting Work | NA | 0.0000 | 0.0000 | 0 | 512341 | 31 | 0 | [6 empty] | 0.0000
2 | 620448 | D -Lift Duct Painting | NA | 0.0000 | 0.0000 | 1 | 620447 | 31 | 0 | [6 empty] | 0.0000
3 | 620449 | D - Lift 1 Duct Painting Work | NA | 0.0000 | 0.0000 | 2 | 620448 | 31 | 0 | [6 empty] | 0.0000
4 | 620450 | D -GF Lift 1 Duct Painting Work | Sq.Ft | 182.7100 | 182.7100 | 3 | 620449 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
5 | 620451 | D -1st Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620449 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
6 | 620452 | D -2nd Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620449 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
7 | 620453 | D -3rd Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620449 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
8 | 620454 | D -4th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620449 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
9 | 620455 | D -5th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620449 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
10 | 620456 | D -6th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620449 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
11 | 620457 | D -7th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620449 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
12 | 620458 | D -8th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620449 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
13 | 620459 | D -9th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620449 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
14 | 620460 | D -10th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620449 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
15 | 620461 | D -11th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620449 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
16 | 620462 | D -12th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620449 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
17 | 620463 | D -13th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620449 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
18 | 620464 | D -14th Floor Lift 1 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 3 | 620449 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
19 | 620465 | D -Terrace Lift 1 Duct Painting Work | Sq.Ft | 232.3900 | 232.3900 | 3 | 620449 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
20 | 620466 | D - Lift 2 Duct Painting Work | NA | 0.0000 | 0.0000 | 2 | 620448 | 31 | 0 | [6 empty] | 0.0000
21 | 620467 | D -GF Lift 2 Duct Painting Work | Sq.Ft | 182.7100 | 182.7100 | 20 | 620466 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
22 | 620468 | D -1st Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620466 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
23 | 620469 | D -2nd Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620466 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
24 | 620470 | D -3rd Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620466 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
25 | 620471 | D -4th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620466 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
26 | 620472 | D -5th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620466 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
27 | 620473 | D -6th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620466 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
28 | 620474 | D -7th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620466 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
29 | 620475 | D -8th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620466 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
30 | 620476 | D -9th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620466 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
31 | 620477 | D -10th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620466 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
32 | 620478 | D -11th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620466 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
33 | 620479 | D -12th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620466 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
34 | 620480 | D -13th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620466 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
35 | 620481 | D -14th Floor Lift 2 Duct Painting Work | Sq.Ft | 102.1100 | 102.1100 | 20 | 620466 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
36 | 620482 | D -Terrace Lift 2 Duct Painting Work | Sq.Ft | 232.3900 | 232.3900 | 20 | 620466 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000