## Sheet1
Project :-GANGA ARCADIA - A BUILDING | Project :-GANGA ARCADIA - A BUILDING | Project :-GANGA ARCADIA - A BUILDING | Project :-GANGA ARCADIA - A BUILDING | Project :-GANGA ARCADIA - A BUILDING | Project :-GANGA ARCADIA - A BUILDING | Project :-GANGA ARCADIA - A BUILDING | Project :-GANGA ARCADIA - A BUILDING | Project :-GANGA ARCADIA - A BUILDING | Project :-GANGA ARCADIA - A BUILDING | Project :-GANGA ARCADIA - A BUILDING | Project :-GANGA ARCADIA - A BUILDING | Project :-GANGA ARCADIA - A BUILDING | Project :-GANGA ARCADIA - A BUILDING | Project :-GANGA ARCADIA - A BUILDING | Project :-GANGA ARCADIA - A BUILDING | Project :-GANGA ARCADIA - A BUILDING
Selected Group :- A - Dry Balcony & Living Terrace | Selected Group :- A - Dry Balcony & Living Terrace | Selected Group :- A - Dry Balcony & Living Terrace | Selected Group :- A - Dry Balcony & Living Terrace | Selected Group :- A - Dry Balcony & Living Terrace | Selected Group :- A - Dry Balcony & Living Terrace | Selected Group :- A - Dry Balcony & Living Terrace | Selected Group :- A - Dry Balcony & Living Terrace | Selected Group :- A - Dry Balcony & Living Terrace | Selected Group :- A - Dry Balcony & Living Terrace | Selected Group :- A - Dry Balcony & Living Terrace | Selected Group :- A - Dry Balcony & Living Terrace | Selected Group :- A - Dry Balcony & Living Terrace | Selected Group :- A - Dry Balcony & Living Terrace | Selected Group :- A - Dry Balcony & Living Terrace | Selected Group :- A - Dry Balcony & Living Terrace | Selected Group :- A - Dry Balcony & Living Terrace
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 620631 | A - Dry Balcony & Living Terrace | NA | 0.0000 | 0.0000 | 0 | 462749 | 31 | 0 | [6 empty] | 0.0000
2 | 620632 | A - 2nd Floor | NA | 0.0000 | 0.0000 | 1 | 620631 | 31 | 0 | [6 empty] | 0.0000
3 | 620633 | A. 201. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 2 | 620632 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
4 | 620634 | A. 202. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 2 | 620632 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
5 | 620635 | A. 203. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 2 | 620632 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
6 | 620636 | A. 204. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 2 | 620632 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
7 | 620637 | A. 205. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 2 | 620632 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
8 | 620638 | A. 206. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 2 | 620632 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
9 | 620639 | A. 207. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 2 | 620632 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
10 | 620640 | A. 208. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 2 | 620632 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
11 | 620641 | A - 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 620631 | 31 | 0 | [6 empty] | 0.0000
12 | 620642 | A. 301. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 11 | 620641 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
13 | 620643 | A. 302. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 11 | 620641 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
14 | 620644 | A. 303. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 11 | 620641 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
15 | 620645 | A. 304. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 11 | 620641 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
16 | 620646 | A. 305. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 11 | 620641 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
17 | 620647 | A. 306. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 11 | 620641 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
18 | 620648 | A. 307. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 11 | 620641 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
19 | 620649 | A. 308. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 11 | 620641 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
20 | 620650 | A - 4th Floor | NA | 0.0000 | 0.0000 | 1 | 620631 | 31 | 0 | [6 empty] | 0.0000
21 | 620651 | A. 401. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 20 | 620650 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
22 | 620652 | A. 402. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 20 | 620650 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
23 | 620653 | A. 403. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 20 | 620650 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
24 | 620654 | A. 404. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 20 | 620650 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
25 | 620655 | A. 405. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 20 | 620650 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
26 | 620656 | A. 406. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 20 | 620650 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
27 | 620657 | A. 407. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 20 | 620650 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
28 | 620658 | A. 408. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 20 | 620650 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
29 | 620659 | A - 5th Floor | NA | 0.0000 | 0.0000 | 1 | 620631 | 31 | 0 | [6 empty] | 0.0000
30 | 620660 | A. 501. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 29 | 620659 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
31 | 620661 | A. 502. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 29 | 620659 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
32 | 620662 | A. 503. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 29 | 620659 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
33 | 620663 | A. 504. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 29 | 620659 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
34 | 620664 | A. 505. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 29 | 620659 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
35 | 620665 | A. 506. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 29 | 620659 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
36 | 620666 | A. 507. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 29 | 620659 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
37 | 620667 | A. 508. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 29 | 620659 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
38 | 620668 | A - 6th Floor | NA | 0.0000 | 0.0000 | 1 | 620631 | 31 | 0 | [6 empty] | 0.0000
39 | 620669 | A. 601. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 38 | 620668 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
40 | 620670 | A. 602. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 38 | 620668 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
41 | 620671 | A. 603. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 38 | 620668 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
42 | 620672 | A. 604. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 38 | 620668 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
43 | 620673 | A. 605. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 38 | 620668 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
44 | 620674 | A. 606. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 38 | 620668 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
45 | 620675 | A. 607. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 38 | 620668 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
46 | 620676 | A. 608. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 38 | 620668 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
47 | 620677 | A - 7th Floor | NA | 0.0000 | 0.0000 | 1 | 620631 | 31 | 0 | [6 empty] | 0.0000
48 | 620678 | A. 701. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 47 | 620677 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
49 | 620679 | A. 702. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 47 | 620677 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
50 | 620680 | A. 703. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 47 | 620677 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
51 | 620681 | A. 704. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 47 | 620677 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
52 | 620682 | A. 705. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 47 | 620677 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
53 | 620683 | A. 706. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 47 | 620677 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
54 | 620684 | A. 707. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 47 | 620677 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
55 | 620685 | A. 708. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 47 | 620677 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
56 | 620686 | A - 8th Floor | NA | 0.0000 | 0.0000 | 1 | 620631 | 31 | 0 | [6 empty] | 0.0000
57 | 620687 | A. 801. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 56 | 620686 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
58 | 620688 | A. 802. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 56 | 620686 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
59 | 620689 | A. 803. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 56 | 620686 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
60 | 620690 | A. 804. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 56 | 620686 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
61 | 620691 | A. 805. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 56 | 620686 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
62 | 620692 | A. 806. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 56 | 620686 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
63 | 620693 | A. 807. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 219.6100 | 219.6100 | 56 | 620686 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
64 | 620694 | A. 808. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 56 | 620686 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
65 | 620695 | A - 9th Floor | NA | 0.0000 | 0.0000 | 1 | 620631 | 31 | 0 | [6 empty] | 0.0000
66 | 620696 | A. 901. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 65 | 620695 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
67 | 620697 | A. 902. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 65 | 620695 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
68 | 620698 | A. 903. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 65 | 620695 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
69 | 620699 | A. 904. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 65 | 620695 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
70 | 620700 | A. 905. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 65 | 620695 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
71 | 620701 | A. 906. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 65 | 620695 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
72 | 620702 | A. 907. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 65 | 620695 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
73 | 620703 | A. 908. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 65 | 620695 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
74 | 620704 | A - 10th Floor | NA | 0.0000 | 0.0000 | 1 | 620631 | 31 | 0 | [6 empty] | 0.0000
75 | 620705 | A. 1001. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 74 | 620704 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
76 | 620706 | A. 1002. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 74 | 620704 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
77 | 620707 | A. 1003. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 74 | 620704 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
78 | 620708 | A. 1004. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 74 | 620704 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
79 | 620709 | A. 1005. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 74 | 620704 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
80 | 620710 | A. 1006. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 74 | 620704 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
81 | 620711 | A. 1007. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 74 | 620704 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
82 | 620712 | A. 1008. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 74 | 620704 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
83 | 620713 | A - 11th Floor | NA | 0.0000 | 0.0000 | 1 | 620631 | 31 | 0 | [6 empty] | 0.0000
84 | 620714 | A. 1101. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 83 | 620713 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
85 | 620715 | A. 1102. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 83 | 620713 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
86 | 620716 | A. 1103. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 83 | 620713 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
87 | 620717 | A. 1104. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 83 | 620713 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
88 | 620718 | A. 1105. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 83 | 620713 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
89 | 620719 | A. 1106. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 83 | 620713 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
90 | 620720 | A. 1107. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 83 | 620713 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
91 | 620721 | A. 1108. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 83 | 620713 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
92 | 620722 | A - 12th Floor | NA | 0.0000 | 0.0000 | 1 | 620631 | 31 | 0 | [6 empty] | 0.0000
93 | 620723 | A. 1201. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 92 | 620722 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
94 | 620724 | A. 1202. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 92 | 620722 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
95 | 620725 | A. 1203. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 92 | 620722 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
96 | 620726 | A. 1204. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 92 | 620722 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
97 | 620727 | A. 1205. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 92 | 620722 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
98 | 620728 | A. 1206. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 92 | 620722 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
99 | 620729 | A. 1207. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 92 | 620722 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
100 | 620730 | A. 1208. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 92 | 620722 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
101 | 620731 | A - 13th Floor | NA | 0.0000 | 0.0000 | 1 | 620631 | 31 | 0 | [6 empty] | 0.0000
102 | 620732 | A. 1301. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 101 | 620731 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
103 | 620733 | A. 1302. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 101 | 620731 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
104 | 620734 | A. 1303. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 101 | 620731 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
105 | 620735 | A. 1304. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 101 | 620731 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
106 | 620736 | A. 1305. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 101 | 620731 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
107 | 620737 | A. 1306. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 101 | 620731 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
108 | 620738 | A. 1307. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 219.6100 | 219.6100 | 101 | 620731 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
109 | 620739 | A. 1308. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 101 | 620731 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
110 | 620740 | A - 14th Floor | NA | 0.0000 | 0.0000 | 1 | 620631 | 31 | 0 | [6 empty] | 0.0000
111 | 620741 | A. 1401. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 110 | 620740 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
112 | 620742 | A. 1402. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 110 | 620740 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
113 | 620743 | A. 1403. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 110 | 620740 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
114 | 620744 | A. 1404. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 110 | 620740 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
115 | 620745 | A. 1405. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 110 | 620740 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
116 | 620746 | A. 1406. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 110 | 620740 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
117 | 620747 | A. 1407. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 110 | 620740 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
118 | 620748 | A. 1408. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 110 | 620740 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
119 | 620749 | A - 15th Floor | NA | 0.0000 | 0.0000 | 1 | 620631 | 31 | 0 | [6 empty] | 0.0000
120 | 620750 | A. 1501. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 119 | 620749 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
121 | 620751 | A. 1502. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 119 | 620749 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
122 | 620752 | A. 1503. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 119 | 620749 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
123 | 620753 | A. 1504. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 119 | 620749 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
124 | 620754 | A. 1505. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 119 | 620749 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
125 | 620755 | A. 1506. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 119 | 620749 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
126 | 620756 | A. 1507. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 119 | 620749 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
127 | 620757 | A. 1508. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 119 | 620749 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
128 | 620758 | A - 16th Floor | NA | 0.0000 | 0.0000 | 1 | 620631 | 31 | 0 | [6 empty] | 0.0000
129 | 620759 | A. 1601. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 128 | 620758 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
130 | 620760 | A. 1602. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 128 | 620758 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
131 | 620761 | A. 1603. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 128 | 620758 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
132 | 620762 | A. 1604. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 128 | 620758 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
133 | 620763 | A. 1605. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.7200 | 248.7200 | 128 | 620758 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
134 | 620764 | A. 1606. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 128 | 620758 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
135 | 620765 | A. 1607. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 248.0100 | 248.0100 | 128 | 620758 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000
136 | 620766 | A. 1608. Dry Balcony & Living Terrace Plaster Work | Sq.Ft | 245.7200 | 245.7200 | 128 | 620758 | 4 | 34314 | A-201-3BHK Dry Balcony Plaster Work | [5 empty] | 0.0000