## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- A-External Painting Work | Selected Group :- A-External Painting Work | Selected Group :- A-External Painting Work | Selected Group :- A-External Painting Work | Selected Group :- A-External Painting Work | Selected Group :- A-External Painting Work | Selected Group :- A-External Painting Work | Selected Group :- A-External Painting Work | Selected Group :- A-External Painting Work | Selected Group :- A-External Painting Work | Selected Group :- A-External Painting Work | Selected Group :- A-External Painting Work | Selected Group :- A-External Painting Work | Selected Group :- A-External Painting Work | Selected Group :- A-External Painting Work | Selected Group :- A-External Painting Work | Selected Group :- A-External Painting Work
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 621062 | C -External Painting Work | NA | 0.0000 | 0.0000 | 0 | 620369 | 31 | 0 | [6 empty] | 0.0000
2 | 621063 | C - West Side External painting Work | NA | 0.0000 | 0.0000 | 1 | 621062 | 31 | 0 | [6 empty] | 0.0000
3 | 621064 | C - West Side GF External Painting Work | Sq.Ft | 339.9380 | 339.9380 | 2 | 621063 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
4 | 621065 | C - West Side 1st Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 2 | 621063 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
5 | 621066 | C - West Side 2nd Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 2 | 621063 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
6 | 621067 | C - West Side 3rd Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 621063 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
7 | 621068 | C - West Side 4th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 621063 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
8 | 621069 | C - West Side 5th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 621063 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
9 | 621070 | C - West Side 6th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 621063 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
10 | 621071 | C - West Side 7th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 621063 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
11 | 621072 | C - West Side 8th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 621063 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
12 | 621073 | C - West Side 9th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 621063 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
13 | 621074 | C - West Side 10th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 621063 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
14 | 621075 | C - West Side 11th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 621063 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
15 | 621076 | C - West Side 12th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 621063 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
16 | 621077 | C - West Side 13th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 621063 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
17 | 621078 | C - West Side 14th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 621063 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
18 | 621079 | C - West Side Terrace Floor External Painting Work | Sq.Ft | 1633.4050 | 1633.4050 | 2 | 621063 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
19 | 621080 | C - East Side External painting Work | NA | 0.0000 | 0.0000 | 1 | 621062 | 31 | 0 | [6 empty] | 0.0000
20 | 621081 | C - East Side GF External Painting Work | Sq.Ft | 413.6070 | 413.6070 | 19 | 621080 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
21 | 621082 | C - East Side 1st Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 19 | 621080 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
22 | 621083 | C - East Side 2nd Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 19 | 621080 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
23 | 621084 | C - East Side 3rd Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 19 | 621080 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
24 | 621085 | C - East Side 4th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 19 | 621080 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
25 | 621086 | C - East Side 5th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 19 | 621080 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
26 | 621087 | C - East Side 6th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 19 | 621080 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
27 | 621088 | C - East Side 7th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 19 | 621080 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
28 | 621089 | C - East Side 8th Floor External Painting Work | Sq.Ft | 638.5700 | 638.5700 | 19 | 621080 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
29 | 621090 | C - East Side 9th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 19 | 621080 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
30 | 621091 | C - East Side 10th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 19 | 621080 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
31 | 621092 | C - East Side 11th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 19 | 621080 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
32 | 621093 | C - East Side 12th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 19 | 621080 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
33 | 621094 | C - East Side 13th Floor External Painting Work | Sq.Ft | 638.5700 | 638.5700 | 19 | 621080 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
34 | 621095 | C - East Side 14th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 19 | 621080 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
35 | 621096 | C - East Side Terrace Floor External Painting Work | Sq.Ft | 834.6620 | 834.6620 | 19 | 621080 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
36 | 621097 | C - North Side External painting Work | NA | 0.0000 | 0.0000 | 1 | 621062 | 31 | 0 | [6 empty] | 0.0000
37 | 621098 | C - North Side GF External Painting Work | Sq.Ft | 353.0480 | 353.0480 | 36 | 621097 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
38 | 621099 | C - North Side 1st Floor External Painting Work | Sq.Ft | 1529.0690 | 1529.0690 | 36 | 621097 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
39 | 621100 | C - North Side 2nd Floor External Painting Work | Sq.Ft | 1529.0690 | 1529.0690 | 36 | 621097 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
40 | 621101 | C - North Side 3rd Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 36 | 621097 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
41 | 621102 | C - North Side 4th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 36 | 621097 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
42 | 621103 | C - North Side 5th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 36 | 621097 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
43 | 621104 | C - North Side 6th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 36 | 621097 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
44 | 621105 | C - North Side 7th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 36 | 621097 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
45 | 621106 | C - North Side 8th Floor External Painting Work | Sq.Ft | 2070.2730 | 2070.2730 | 36 | 621097 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
46 | 621107 | C - North Side 9th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 36 | 621097 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
47 | 621108 | C - North Side 10th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 36 | 621097 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
48 | 621109 | C - North Side 11th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 36 | 621097 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
49 | 621110 | C - North Side 12th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 36 | 621097 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
50 | 621111 | C - North Side 13th Floor External Painting Work | Sq.Ft | 2070.2730 | 2070.2730 | 36 | 621097 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
51 | 621112 | C - North Side 14th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 36 | 621097 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
52 | 621113 | C - North Side Terrace Floor External Painting Work | Sq.Ft | 2100.5300 | 2100.5300 | 36 | 621097 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
53 | 621114 | C - South Side External painting Work | NA | 0.0000 | 0.0000 | 1 | 621062 | 31 | 0 | [6 empty] | 0.0000
54 | 621115 | C - South Side GF External Painting Work | Sq.Ft | 462.6150 | 462.6150 | 53 | 621114 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
55 | 621116 | C - South Side 1st Floor External Painting Work | Sq.Ft | 1498.1870 | 1498.1870 | 53 | 621114 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
56 | 621117 | C - South Side 2nd Floor External Painting Work | Sq.Ft | 1517.5630 | 1517.5630 | 53 | 621114 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
57 | 621118 | C - South Side 3rd Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 53 | 621114 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
58 | 621119 | C - South Side 4th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 53 | 621114 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
59 | 621120 | C - South Side 5th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 53 | 621114 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
60 | 621121 | C - South Side 6th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 53 | 621114 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
61 | 621122 | C - South Side 7th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 53 | 621114 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
62 | 621123 | C - South Side 8th Floor External Painting Work | Sq.Ft | 1972.7840 | 1972.7840 | 53 | 621114 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
63 | 621124 | C - South Side 9th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 53 | 621114 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
64 | 621125 | C - South Side 10th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 53 | 621114 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
65 | 621126 | C - South Side 11th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 53 | 621114 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
66 | 621127 | C - South Side 12th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 53 | 621114 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
67 | 621128 | C - South Side 13th Floor External Painting Work | Sq.Ft | 1972.7840 | 1972.7840 | 53 | 621114 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
68 | 621129 | C - South Side 14th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 53 | 621114 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
69 | 621130 | C - South Side Terrace Floor External Painting Work | Sq.Ft | 1996.4210 | 1996.4210 | 53 | 621114 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000