## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 621433 | C - Umra Patti Work | NA | 0.0000 | 0.0000 | 0 | 567586 | 31 | 0 | [6 empty] | 0.0000
2 | 621461 | C - 2nd Floor | NA | 0.0000 | 0.0000 | 1 | 621433 | 31 | 0 | [6 empty] | 0.0000
3 | 621492 | C - 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 621433 | 31 | 0 | [6 empty] | 0.0000
4 | 621493 | C - Flat No 301 | NA | 0.0000 | 0.0000 | 3 | 621492 | 31 | 0 | [6 empty] | 0.0000
5 | 621494 | C -301 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 4 | 621493 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
6 | 621495 | C - Flat No 302 | NA | 0.0000 | 0.0000 | 3 | 621492 | 31 | 0 | [6 empty] | 0.0000
7 | 621496 | C -302 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 6 | 621495 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
8 | 621497 | C - Flat No 303 | NA | 0.0000 | 0.0000 | 3 | 621492 | 31 | 0 | [6 empty] | 0.0000
9 | 621498 | C -303 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 8 | 621497 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
10 | 621499 | C - Flat No 304 | NA | 0.0000 | 0.0000 | 3 | 621492 | 31 | 0 | [6 empty] | 0.0000
11 | 621500 | C -304 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 10 | 621499 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
12 | 621501 | C - Flat No 305 | NA | 0.0000 | 0.0000 | 3 | 621492 | 31 | 0 | [6 empty] | 0.0000
13 | 621502 | C -305 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 12 | 621501 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
14 | 621503 | C - Flat No 306 | NA | 0.0000 | 0.0000 | 3 | 621492 | 31 | 0 | [6 empty] | 0.0000
15 | 621504 | C -306 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 14 | 621503 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
16 | 621505 | C - Flat No 307 | NA | 0.0000 | 0.0000 | 3 | 621492 | 31 | 0 | [6 empty] | 0.0000
17 | 621506 | C -307 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 16 | 621505 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
18 | 621507 | C - Flat No 308 | NA | 0.0000 | 0.0000 | 3 | 621492 | 31 | 0 | [6 empty] | 0.0000
19 | 621508 | C -308 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 18 | 621507 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
20 | 621509 | C - Flat No 309 | NA | 0.0000 | 0.0000 | 3 | 621492 | 31 | 0 | [6 empty] | 0.0000
21 | 621510 | C -309 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 20 | 621509 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
22 | 621511 | C - Flat No 310 | NA | 0.0000 | 0.0000 | 3 | 621492 | 31 | 0 | [6 empty] | 0.0000
23 | 621512 | C -310 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 22 | 621511 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
24 | 621513 | C - Flat No 311 | NA | 0.0000 | 0.0000 | 3 | 621492 | 31 | 0 | [6 empty] | 0.0000
25 | 621514 | C -311 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 24 | 621513 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
26 | 621515 | C - Flat No 312 | NA | 0.0000 | 0.0000 | 3 | 621492 | 31 | 0 | [6 empty] | 0.0000
27 | 621516 | C -312 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 26 | 621515 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
28 | 621517 | C - Flat No 313 | NA | 0.0000 | 0.0000 | 3 | 621492 | 31 | 0 | [6 empty] | 0.0000
29 | 621518 | C -313 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 28 | 621517 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
30 | 621519 | C - Flat No 314 | NA | 0.0000 | 0.0000 | 3 | 621492 | 31 | 0 | [6 empty] | 0.0000
31 | 621520 | C -314 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 30 | 621519 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
32 | 621521 | C - 4th Floor | NA | 0.0000 | 0.0000 | 1 | 621433 | 31 | 0 | [6 empty] | 0.0000
33 | 621522 | C - Flat No 401 | NA | 0.0000 | 0.0000 | 32 | 621521 | 31 | 0 | [6 empty] | 0.0000
34 | 621523 | C -401 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 33 | 621522 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
35 | 621524 | C - Flat No 402 | NA | 0.0000 | 0.0000 | 32 | 621521 | 31 | 0 | [6 empty] | 0.0000
36 | 621525 | C -402 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 35 | 621524 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
37 | 621526 | C - Flat No 403 | NA | 0.0000 | 0.0000 | 32 | 621521 | 31 | 0 | [6 empty] | 0.0000
38 | 621527 | C -403 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 37 | 621526 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
39 | 621528 | C - Flat No 404 | NA | 0.0000 | 0.0000 | 32 | 621521 | 31 | 0 | [6 empty] | 0.0000
40 | 621529 | C -404 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 39 | 621528 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
41 | 621530 | C - Flat No 405 | NA | 0.0000 | 0.0000 | 32 | 621521 | 31 | 0 | [6 empty] | 0.0000
42 | 621531 | C -405 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 41 | 621530 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
43 | 621532 | C - Flat No 406 | NA | 0.0000 | 0.0000 | 32 | 621521 | 31 | 0 | [6 empty] | 0.0000
44 | 621533 | C -406 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 43 | 621532 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
45 | 621534 | C - Flat No 407 | NA | 0.0000 | 0.0000 | 32 | 621521 | 31 | 0 | [6 empty] | 0.0000
46 | 621535 | C -407 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 45 | 621534 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
47 | 621536 | C - Flat No 408 | NA | 0.0000 | 0.0000 | 32 | 621521 | 31 | 0 | [6 empty] | 0.0000
48 | 621537 | C -408 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 47 | 621536 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
49 | 621538 | C - Flat No 409 | NA | 0.0000 | 0.0000 | 32 | 621521 | 31 | 0 | [6 empty] | 0.0000
50 | 621539 | C -409 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 49 | 621538 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
51 | 621540 | C - Flat No 410 | NA | 0.0000 | 0.0000 | 32 | 621521 | 31 | 0 | [6 empty] | 0.0000
52 | 621541 | C -410 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 51 | 621540 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
53 | 621542 | C - Flat No 411 | NA | 0.0000 | 0.0000 | 32 | 621521 | 31 | 0 | [6 empty] | 0.0000
54 | 621543 | C -411 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 53 | 621542 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
55 | 621544 | C - Flat No 412 | NA | 0.0000 | 0.0000 | 32 | 621521 | 31 | 0 | [6 empty] | 0.0000
56 | 621545 | C -412 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 55 | 621544 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
57 | 621546 | C - Flat No 413 | NA | 0.0000 | 0.0000 | 32 | 621521 | 31 | 0 | [6 empty] | 0.0000
58 | 621547 | C -413 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 57 | 621546 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
59 | 621548 | C - Flat No 414 | NA | 0.0000 | 0.0000 | 32 | 621521 | 31 | 0 | [6 empty] | 0.0000
60 | 621549 | C -414 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 59 | 621548 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
61 | 621550 | C - 5th Floor | NA | 0.0000 | 0.0000 | 1 | 621433 | 31 | 0 | [6 empty] | 0.0000
62 | 621551 | C - Flat No 501 | NA | 0.0000 | 0.0000 | 61 | 621550 | 31 | 0 | [6 empty] | 0.0000
63 | 621552 | C -501 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 62 | 621551 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
64 | 621553 | C - Flat No 502 | NA | 0.0000 | 0.0000 | 61 | 621550 | 31 | 0 | [6 empty] | 0.0000
65 | 621554 | C -502 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 64 | 621553 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
66 | 621555 | C - Flat No 503 | NA | 0.0000 | 0.0000 | 61 | 621550 | 31 | 0 | [6 empty] | 0.0000
67 | 621556 | C -503 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 66 | 621555 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
68 | 621557 | C - Flat No 504 | NA | 0.0000 | 0.0000 | 61 | 621550 | 31 | 0 | [6 empty] | 0.0000
69 | 621558 | C -504 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 68 | 621557 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
70 | 621559 | C - Flat No 505 | NA | 0.0000 | 0.0000 | 61 | 621550 | 31 | 0 | [6 empty] | 0.0000
71 | 621560 | C -505 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 70 | 621559 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
72 | 621561 | C - Flat No 506 | NA | 0.0000 | 0.0000 | 61 | 621550 | 31 | 0 | [6 empty] | 0.0000
73 | 621562 | C -506 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 72 | 621561 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
74 | 621563 | C - Flat No 507 | NA | 0.0000 | 0.0000 | 61 | 621550 | 31 | 0 | [6 empty] | 0.0000
75 | 621564 | C -507 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 74 | 621563 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
76 | 621565 | C - Flat No 508 | NA | 0.0000 | 0.0000 | 61 | 621550 | 31 | 0 | [6 empty] | 0.0000
77 | 621566 | C -508 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 76 | 621565 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
78 | 621567 | C - Flat No 509 | NA | 0.0000 | 0.0000 | 61 | 621550 | 31 | 0 | [6 empty] | 0.0000
79 | 621568 | C -509 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 78 | 621567 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
80 | 621569 | C - Flat No 510 | NA | 0.0000 | 0.0000 | 61 | 621550 | 31 | 0 | [6 empty] | 0.0000
81 | 621570 | C -510 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 80 | 621569 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
82 | 621571 | C - Flat No 511 | NA | 0.0000 | 0.0000 | 61 | 621550 | 31 | 0 | [6 empty] | 0.0000
83 | 621572 | C -511 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 82 | 621571 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
84 | 621573 | C - Flat No 512 | NA | 0.0000 | 0.0000 | 61 | 621550 | 31 | 0 | [6 empty] | 0.0000
85 | 621574 | C -512 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 84 | 621573 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
86 | 621575 | C - Flat No 513 | NA | 0.0000 | 0.0000 | 61 | 621550 | 31 | 0 | [6 empty] | 0.0000
87 | 621576 | C -513 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 86 | 621575 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
88 | 621577 | C - Flat No 514 | NA | 0.0000 | 0.0000 | 61 | 621550 | 31 | 0 | [6 empty] | 0.0000
89 | 621578 | C -514 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 88 | 621577 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
90 | 621579 | C - 6th Floor | NA | 0.0000 | 0.0000 | 1 | 621433 | 31 | 0 | [6 empty] | 0.0000
91 | 621580 | C - Flat No 601 | NA | 0.0000 | 0.0000 | 90 | 621579 | 31 | 0 | [6 empty] | 0.0000
92 | 621581 | C -601 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 91 | 621580 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
93 | 621582 | C - Flat No 602 | NA | 0.0000 | 0.0000 | 90 | 621579 | 31 | 0 | [6 empty] | 0.0000
94 | 621583 | C -602 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 93 | 621582 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
95 | 621584 | C - Flat No 603 | NA | 0.0000 | 0.0000 | 90 | 621579 | 31 | 0 | [6 empty] | 0.0000
96 | 621585 | C -603 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 95 | 621584 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
97 | 621586 | C - Flat No 604 | NA | 0.0000 | 0.0000 | 90 | 621579 | 31 | 0 | [6 empty] | 0.0000
98 | 621587 | C -604 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 97 | 621586 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
99 | 621588 | C - Flat No 605 | NA | 0.0000 | 0.0000 | 90 | 621579 | 31 | 0 | [6 empty] | 0.0000
100 | 621589 | C -605 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 99 | 621588 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
101 | 621590 | C - Flat No 606 | NA | 0.0000 | 0.0000 | 90 | 621579 | 31 | 0 | [6 empty] | 0.0000
102 | 621591 | C -606 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 101 | 621590 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
103 | 621592 | C - Flat No 607 | NA | 0.0000 | 0.0000 | 90 | 621579 | 31 | 0 | [6 empty] | 0.0000
104 | 621593 | C -607 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 103 | 621592 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
105 | 621594 | C - Flat No 608 | NA | 0.0000 | 0.0000 | 90 | 621579 | 31 | 0 | [6 empty] | 0.0000
106 | 621595 | C -608 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 105 | 621594 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
107 | 621596 | C - Flat No 609 | NA | 0.0000 | 0.0000 | 90 | 621579 | 31 | 0 | [6 empty] | 0.0000
108 | 621597 | C -609 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 107 | 621596 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
109 | 621598 | C - Flat No 610 | NA | 0.0000 | 0.0000 | 90 | 621579 | 31 | 0 | [6 empty] | 0.0000
110 | 621599 | C -610 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 109 | 621598 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
111 | 621600 | C - Flat No 611 | NA | 0.0000 | 0.0000 | 90 | 621579 | 31 | 0 | [6 empty] | 0.0000
112 | 621601 | C -611 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 111 | 621600 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
113 | 621602 | C - Flat No 612 | NA | 0.0000 | 0.0000 | 90 | 621579 | 31 | 0 | [6 empty] | 0.0000
114 | 621603 | C -612 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 113 | 621602 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
115 | 621604 | C - Flat No 613 | NA | 0.0000 | 0.0000 | 90 | 621579 | 31 | 0 | [6 empty] | 0.0000
116 | 621605 | C -613 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 115 | 621604 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
117 | 621606 | C - Flat No 614 | NA | 0.0000 | 0.0000 | 90 | 621579 | 31 | 0 | [6 empty] | 0.0000
118 | 621607 | C -614 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 117 | 621606 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
119 | 621608 | C - 7th Floor | NA | 0.0000 | 0.0000 | 1 | 621433 | 31 | 0 | [6 empty] | 0.0000
120 | 621609 | C - Flat No 701 | NA | 0.0000 | 0.0000 | 119 | 621608 | 31 | 0 | [6 empty] | 0.0000
121 | 621610 | C -701 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 120 | 621609 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
122 | 621611 | C - Flat No 702 | NA | 0.0000 | 0.0000 | 119 | 621608 | 31 | 0 | [6 empty] | 0.0000
123 | 621612 | C -702 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 122 | 621611 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
124 | 621613 | C - Flat No 703 | NA | 0.0000 | 0.0000 | 119 | 621608 | 31 | 0 | [6 empty] | 0.0000
125 | 621614 | C -703 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 124 | 621613 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
126 | 621615 | C - Flat No 704 | NA | 0.0000 | 0.0000 | 119 | 621608 | 31 | 0 | [6 empty] | 0.0000
127 | 621616 | C -704 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 126 | 621615 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
128 | 621617 | C - Flat No 705 | NA | 0.0000 | 0.0000 | 119 | 621608 | 31 | 0 | [6 empty] | 0.0000
129 | 621618 | C -705 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 128 | 621617 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
130 | 621619 | C - Flat No 706 | NA | 0.0000 | 0.0000 | 119 | 621608 | 31 | 0 | [6 empty] | 0.0000
131 | 621620 | C -706 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 130 | 621619 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
132 | 621621 | C - Flat No 707 | NA | 0.0000 | 0.0000 | 119 | 621608 | 31 | 0 | [6 empty] | 0.0000
133 | 621622 | C -707 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 132 | 621621 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
134 | 621623 | C - Flat No 708 | NA | 0.0000 | 0.0000 | 119 | 621608 | 31 | 0 | [6 empty] | 0.0000
135 | 621624 | C -708 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 134 | 621623 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
136 | 621625 | C - Flat No 709 | NA | 0.0000 | 0.0000 | 119 | 621608 | 31 | 0 | [6 empty] | 0.0000
137 | 621626 | C -709 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 136 | 621625 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
138 | 621627 | C - Flat No 710 | NA | 0.0000 | 0.0000 | 119 | 621608 | 31 | 0 | [6 empty] | 0.0000
139 | 621628 | C -710 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 138 | 621627 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
140 | 621629 | C - Flat No 711 | NA | 0.0000 | 0.0000 | 119 | 621608 | 31 | 0 | [6 empty] | 0.0000
141 | 621630 | C -711 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 140 | 621629 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
142 | 621631 | C - Flat No 712 | NA | 0.0000 | 0.0000 | 119 | 621608 | 31 | 0 | [6 empty] | 0.0000
143 | 621632 | C -712 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 142 | 621631 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
144 | 621633 | C - Flat No 713 | NA | 0.0000 | 0.0000 | 119 | 621608 | 31 | 0 | [6 empty] | 0.0000
145 | 621634 | C -713 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 144 | 621633 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
146 | 621635 | C - Flat No 714 | NA | 0.0000 | 0.0000 | 119 | 621608 | 31 | 0 | [6 empty] | 0.0000
147 | 621636 | C -714 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 146 | 621635 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
148 | 621637 | C - 8th Floor | NA | 0.0000 | 0.0000 | 1 | 621433 | 31 | 0 | [6 empty] | 0.0000
149 | 621638 | C - Flat No 801 | NA | 0.0000 | 0.0000 | 148 | 621637 | 31 | 0 | [6 empty] | 0.0000
150 | 621639 | C -801 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 149 | 621638 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
151 | 621640 | C - Flat No 802 | NA | 0.0000 | 0.0000 | 148 | 621637 | 31 | 0 | [6 empty] | 0.0000
152 | 621641 | C -802 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 151 | 621640 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
153 | 621642 | C - Flat No 803 | NA | 0.0000 | 0.0000 | 148 | 621637 | 31 | 0 | [6 empty] | 0.0000
154 | 621643 | C -803 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 153 | 621642 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
155 | 621644 | C - Flat No 804 | NA | 0.0000 | 0.0000 | 148 | 621637 | 31 | 0 | [6 empty] | 0.0000
156 | 621645 | C -804 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 155 | 621644 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
157 | 621646 | C - Flat No 805 | NA | 0.0000 | 0.0000 | 148 | 621637 | 31 | 0 | [6 empty] | 0.0000
158 | 621647 | C -805 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 157 | 621646 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
159 | 621648 | C - Flat No 806 | NA | 0.0000 | 0.0000 | 148 | 621637 | 31 | 0 | [6 empty] | 0.0000
160 | 621649 | C -806 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 159 | 621648 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
161 | 621650 | C - Flat No 807 | NA | 0.0000 | 0.0000 | 148 | 621637 | 31 | 0 | [6 empty] | 0.0000
162 | 621651 | C -807 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 161 | 621650 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
163 | 621652 | C - Flat No 808 | NA | 0.0000 | 0.0000 | 148 | 621637 | 31 | 0 | [6 empty] | 0.0000
164 | 621653 | C -808 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 163 | 621652 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
165 | 621654 | C - Flat No 809 | NA | 0.0000 | 0.0000 | 148 | 621637 | 31 | 0 | [6 empty] | 0.0000
166 | 621655 | C -809 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 165 | 621654 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
167 | 621656 | C - Flat No 810 | NA | 0.0000 | 0.0000 | 148 | 621637 | 31 | 0 | [6 empty] | 0.0000
168 | 621657 | C -810 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 167 | 621656 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
169 | 621658 | C - Flat No 811 | NA | 0.0000 | 0.0000 | 148 | 621637 | 31 | 0 | [6 empty] | 0.0000
170 | 621659 | C -811 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 169 | 621658 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
171 | 621660 | C - Flat No 812 | NA | 0.0000 | 0.0000 | 148 | 621637 | 31 | 0 | [6 empty] | 0.0000
172 | 621661 | C -812 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 171 | 621660 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
173 | 621662 | C - Flat No 813 | NA | 0.0000 | 0.0000 | 148 | 621637 | 31 | 0 | [6 empty] | 0.0000
174 | 621663 | C -813 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 173 | 621662 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
175 | 621664 | C - Flat No 814 | NA | 0.0000 | 0.0000 | 148 | 621637 | 31 | 0 | [6 empty] | 0.0000
176 | 621665 | C -814 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 175 | 621664 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
177 | 621666 | C - 9th Floor | NA | 0.0000 | 0.0000 | 1 | 621433 | 31 | 0 | [6 empty] | 0.0000
178 | 621667 | C - Flat No 901 | NA | 0.0000 | 0.0000 | 177 | 621666 | 31 | 0 | [6 empty] | 0.0000
179 | 621668 | C -901 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 178 | 621667 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
180 | 621669 | C - Flat No 902 | NA | 0.0000 | 0.0000 | 177 | 621666 | 31 | 0 | [6 empty] | 0.0000
181 | 621670 | C -902 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 180 | 621669 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
182 | 621671 | C - Flat No 903 | NA | 0.0000 | 0.0000 | 177 | 621666 | 31 | 0 | [6 empty] | 0.0000
183 | 621672 | C -903 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 182 | 621671 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
184 | 621673 | C - Flat No 904 | NA | 0.0000 | 0.0000 | 177 | 621666 | 31 | 0 | [6 empty] | 0.0000
185 | 621674 | C -904 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 184 | 621673 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
186 | 621675 | C - Flat No 905 | NA | 0.0000 | 0.0000 | 177 | 621666 | 31 | 0 | [6 empty] | 0.0000
187 | 621676 | C -905 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 186 | 621675 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
188 | 621677 | C - Flat No 906 | NA | 0.0000 | 0.0000 | 177 | 621666 | 31 | 0 | [6 empty] | 0.0000
189 | 621678 | C -906 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 188 | 621677 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
190 | 621679 | C - Flat No 907 | NA | 0.0000 | 0.0000 | 177 | 621666 | 31 | 0 | [6 empty] | 0.0000
191 | 621680 | C -907 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 190 | 621679 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
192 | 621681 | C - Flat No 908 | NA | 0.0000 | 0.0000 | 177 | 621666 | 31 | 0 | [6 empty] | 0.0000
193 | 621682 | C -908 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 192 | 621681 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
194 | 621683 | C - Flat No 909 | NA | 0.0000 | 0.0000 | 177 | 621666 | 31 | 0 | [6 empty] | 0.0000
195 | 621684 | C -909 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 194 | 621683 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
196 | 621685 | C - Flat No 910 | NA | 0.0000 | 0.0000 | 177 | 621666 | 31 | 0 | [6 empty] | 0.0000
197 | 621686 | C -910 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 196 | 621685 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
198 | 621687 | C - Flat No 911 | NA | 0.0000 | 0.0000 | 177 | 621666 | 31 | 0 | [6 empty] | 0.0000
199 | 621688 | C -911 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 198 | 621687 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
200 | 621689 | C - Flat No 912 | NA | 0.0000 | 0.0000 | 177 | 621666 | 31 | 0 | [6 empty] | 0.0000
201 | 621690 | C -912 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 200 | 621689 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
202 | 621691 | C - Flat No 913 | NA | 0.0000 | 0.0000 | 177 | 621666 | 31 | 0 | [6 empty] | 0.0000
203 | 621692 | C -913 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 202 | 621691 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
204 | 621693 | C - Flat No 914 | NA | 0.0000 | 0.0000 | 177 | 621666 | 31 | 0 | [6 empty] | 0.0000
205 | 621694 | C -914 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 204 | 621693 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
206 | 621695 | C - 10th Floor | NA | 0.0000 | 0.0000 | 1 | 621433 | 31 | 0 | [6 empty] | 0.0000
207 | 621696 | C - Flat No 1001 | NA | 0.0000 | 0.0000 | 206 | 621695 | 31 | 0 | [6 empty] | 0.0000
208 | 621697 | C -1001 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 207 | 621696 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
209 | 621698 | C - Flat No 1002 | NA | 0.0000 | 0.0000 | 206 | 621695 | 31 | 0 | [6 empty] | 0.0000
210 | 621699 | C -1002 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 209 | 621698 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
211 | 621700 | C - Flat No 1003 | NA | 0.0000 | 0.0000 | 206 | 621695 | 31 | 0 | [6 empty] | 0.0000
212 | 621701 | C -1003 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 211 | 621700 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
213 | 621702 | C - Flat No 1004 | NA | 0.0000 | 0.0000 | 206 | 621695 | 31 | 0 | [6 empty] | 0.0000
214 | 621703 | C -1004 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 213 | 621702 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
215 | 621704 | C - Flat No 1005 | NA | 0.0000 | 0.0000 | 206 | 621695 | 31 | 0 | [6 empty] | 0.0000
216 | 621705 | C -1005 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 215 | 621704 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
217 | 621706 | C - Flat No 1006 | NA | 0.0000 | 0.0000 | 206 | 621695 | 31 | 0 | [6 empty] | 0.0000
218 | 621707 | C -1006 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 217 | 621706 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
219 | 621708 | C - Flat No 1007 | NA | 0.0000 | 0.0000 | 206 | 621695 | 31 | 0 | [6 empty] | 0.0000
220 | 621709 | C -1007 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 219 | 621708 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
221 | 621710 | C - Flat No 1008 | NA | 0.0000 | 0.0000 | 206 | 621695 | 31 | 0 | [6 empty] | 0.0000
222 | 621711 | C -1008 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 221 | 621710 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
223 | 621712 | C - Flat No 1009 | NA | 0.0000 | 0.0000 | 206 | 621695 | 31 | 0 | [6 empty] | 0.0000
224 | 621713 | C -1009 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 223 | 621712 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
225 | 621714 | C - Flat No 1010 | NA | 0.0000 | 0.0000 | 206 | 621695 | 31 | 0 | [6 empty] | 0.0000
226 | 621715 | C -1010 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 225 | 621714 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
227 | 621716 | C - Flat No 1011 | NA | 0.0000 | 0.0000 | 206 | 621695 | 31 | 0 | [6 empty] | 0.0000
228 | 621717 | C -1011 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 227 | 621716 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
229 | 621718 | C - Flat No 1012 | NA | 0.0000 | 0.0000 | 206 | 621695 | 31 | 0 | [6 empty] | 0.0000
230 | 621719 | C -1012 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 229 | 621718 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
231 | 621720 | C - Flat No 1013 | NA | 0.0000 | 0.0000 | 206 | 621695 | 31 | 0 | [6 empty] | 0.0000
232 | 621721 | C -1013 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 231 | 621720 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
233 | 621722 | C - Flat No 1014 | NA | 0.0000 | 0.0000 | 206 | 621695 | 31 | 0 | [6 empty] | 0.0000
234 | 621723 | C -1014 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 233 | 621722 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
235 | 621724 | C - 11th Floor | NA | 0.0000 | 0.0000 | 1 | 621433 | 31 | 0 | [6 empty] | 0.0000
236 | 621725 | C - Flat No 1101 | NA | 0.0000 | 0.0000 | 235 | 621724 | 31 | 0 | [6 empty] | 0.0000
237 | 621726 | C -1101 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 236 | 621725 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
238 | 621727 | C - Flat No 1102 | NA | 0.0000 | 0.0000 | 235 | 621724 | 31 | 0 | [6 empty] | 0.0000
239 | 621728 | C -1102 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 238 | 621727 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
240 | 621729 | C - Flat No 1103 | NA | 0.0000 | 0.0000 | 235 | 621724 | 31 | 0 | [6 empty] | 0.0000
241 | 621730 | C -1103 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 240 | 621729 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
242 | 621731 | C - Flat No 1104 | NA | 0.0000 | 0.0000 | 235 | 621724 | 31 | 0 | [6 empty] | 0.0000
243 | 621732 | C -1104 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 242 | 621731 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
244 | 621733 | C - Flat No 1105 | NA | 0.0000 | 0.0000 | 235 | 621724 | 31 | 0 | [6 empty] | 0.0000
245 | 621734 | C -1105 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 244 | 621733 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
246 | 621735 | C - Flat No 1106 | NA | 0.0000 | 0.0000 | 235 | 621724 | 31 | 0 | [6 empty] | 0.0000
247 | 621736 | C -1106 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 246 | 621735 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
248 | 621737 | C - Flat No 1107 | NA | 0.0000 | 0.0000 | 235 | 621724 | 31 | 0 | [6 empty] | 0.0000
249 | 621738 | C -1107 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 248 | 621737 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
250 | 621739 | C - Flat No 1108 | NA | 0.0000 | 0.0000 | 235 | 621724 | 31 | 0 | [6 empty] | 0.0000
251 | 621740 | C -1108 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 250 | 621739 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
252 | 621741 | C - Flat No 1109 | NA | 0.0000 | 0.0000 | 235 | 621724 | 31 | 0 | [6 empty] | 0.0000
253 | 621742 | C -1109 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 252 | 621741 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
254 | 621743 | C - Flat No 1110 | NA | 0.0000 | 0.0000 | 235 | 621724 | 31 | 0 | [6 empty] | 0.0000
255 | 621744 | C -1110 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 254 | 621743 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
256 | 621745 | C - Flat No 1111 | NA | 0.0000 | 0.0000 | 235 | 621724 | 31 | 0 | [6 empty] | 0.0000
257 | 621746 | C -1111 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 256 | 621745 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
258 | 621747 | C - Flat No 1112 | NA | 0.0000 | 0.0000 | 235 | 621724 | 31 | 0 | [6 empty] | 0.0000
259 | 621748 | C -1112 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 258 | 621747 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
260 | 621749 | C - Flat No 1113 | NA | 0.0000 | 0.0000 | 235 | 621724 | 31 | 0 | [6 empty] | 0.0000
261 | 621750 | C -1113 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 260 | 621749 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
262 | 621751 | C - Flat No 1114 | NA | 0.0000 | 0.0000 | 235 | 621724 | 31 | 0 | [6 empty] | 0.0000
263 | 621752 | C -1114 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 262 | 621751 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
264 | 621753 | C - 12th Floor | NA | 0.0000 | 0.0000 | 1 | 621433 | 31 | 0 | [6 empty] | 0.0000
265 | 621754 | C - Flat No 1201 | NA | 0.0000 | 0.0000 | 264 | 621753 | 31 | 0 | [6 empty] | 0.0000
266 | 621755 | C -1201 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 265 | 621754 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
267 | 621756 | C - Flat No 1202 | NA | 0.0000 | 0.0000 | 264 | 621753 | 31 | 0 | [6 empty] | 0.0000
268 | 621757 | C -1202 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 267 | 621756 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
269 | 621758 | C - Flat No 1203 | NA | 0.0000 | 0.0000 | 264 | 621753 | 31 | 0 | [6 empty] | 0.0000
270 | 621759 | C -1203 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 269 | 621758 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
271 | 621760 | C - Flat No 1204 | NA | 0.0000 | 0.0000 | 264 | 621753 | 31 | 0 | [6 empty] | 0.0000
272 | 621761 | C -1204 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 271 | 621760 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
273 | 621762 | C - Flat No 1205 | NA | 0.0000 | 0.0000 | 264 | 621753 | 31 | 0 | [6 empty] | 0.0000
274 | 621763 | C -1205 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 273 | 621762 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
275 | 621764 | C - Flat No 1206 | NA | 0.0000 | 0.0000 | 264 | 621753 | 31 | 0 | [6 empty] | 0.0000
276 | 621765 | C -1206 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 275 | 621764 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
277 | 621766 | C - Flat No 1207 | NA | 0.0000 | 0.0000 | 264 | 621753 | 31 | 0 | [6 empty] | 0.0000
278 | 621767 | C -1207 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 277 | 621766 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
279 | 621768 | C - Flat No 1208 | NA | 0.0000 | 0.0000 | 264 | 621753 | 31 | 0 | [6 empty] | 0.0000
280 | 621769 | C -1208 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 279 | 621768 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
281 | 621770 | C - Flat No 1209 | NA | 0.0000 | 0.0000 | 264 | 621753 | 31 | 0 | [6 empty] | 0.0000
282 | 621771 | C -1209 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 281 | 621770 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
283 | 621772 | C - Flat No 1210 | NA | 0.0000 | 0.0000 | 264 | 621753 | 31 | 0 | [6 empty] | 0.0000
284 | 621773 | C -1210 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 283 | 621772 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
285 | 621774 | C - Flat No 1211 | NA | 0.0000 | 0.0000 | 264 | 621753 | 31 | 0 | [6 empty] | 0.0000
286 | 621775 | C -1211 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 285 | 621774 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
287 | 621776 | C - Flat No 1212 | NA | 0.0000 | 0.0000 | 264 | 621753 | 31 | 0 | [6 empty] | 0.0000
288 | 621777 | C -1212 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 287 | 621776 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
289 | 621778 | C - Flat No 1213 | NA | 0.0000 | 0.0000 | 264 | 621753 | 31 | 0 | [6 empty] | 0.0000
290 | 621779 | C -1213 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 289 | 621778 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
291 | 621780 | C - Flat No 1214 | NA | 0.0000 | 0.0000 | 264 | 621753 | 31 | 0 | [6 empty] | 0.0000
292 | 621781 | C -1214 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 291 | 621780 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
293 | 621782 | C - 13th Floor | NA | 0.0000 | 0.0000 | 1 | 621433 | 31 | 0 | [6 empty] | 0.0000
294 | 621783 | C - Flat No 1301 | NA | 0.0000 | 0.0000 | 293 | 621782 | 31 | 0 | [6 empty] | 0.0000
295 | 621784 | C -1301 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 294 | 621783 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
296 | 621785 | C - Flat No 1302 | NA | 0.0000 | 0.0000 | 293 | 621782 | 31 | 0 | [6 empty] | 0.0000
297 | 621786 | C -1302 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 296 | 621785 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
298 | 621787 | C - Flat No 1303 | NA | 0.0000 | 0.0000 | 293 | 621782 | 31 | 0 | [6 empty] | 0.0000
299 | 621788 | C -1303 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 298 | 621787 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
300 | 621789 | C - Flat No 1304 | NA | 0.0000 | 0.0000 | 293 | 621782 | 31 | 0 | [6 empty] | 0.0000
301 | 621790 | C -1304 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 300 | 621789 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
302 | 621791 | C - Flat No 1305 | NA | 0.0000 | 0.0000 | 293 | 621782 | 31 | 0 | [6 empty] | 0.0000
303 | 621792 | C -1305 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 302 | 621791 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
304 | 621793 | C - Flat No 1306 | NA | 0.0000 | 0.0000 | 293 | 621782 | 31 | 0 | [6 empty] | 0.0000
305 | 621794 | C -1306 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 304 | 621793 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
306 | 621795 | C - Flat No 1307 | NA | 0.0000 | 0.0000 | 293 | 621782 | 31 | 0 | [6 empty] | 0.0000
307 | 621796 | C -1307 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 306 | 621795 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
308 | 621797 | C - Flat No 1308 | NA | 0.0000 | 0.0000 | 293 | 621782 | 31 | 0 | [6 empty] | 0.0000
309 | 621798 | C -1308 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 308 | 621797 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
310 | 621799 | C - Flat No 1309 | NA | 0.0000 | 0.0000 | 293 | 621782 | 31 | 0 | [6 empty] | 0.0000
311 | 621800 | C -1309 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 310 | 621799 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
312 | 621801 | C - Flat No 1310 | NA | 0.0000 | 0.0000 | 293 | 621782 | 31 | 0 | [6 empty] | 0.0000
313 | 621802 | C -1310 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 312 | 621801 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
314 | 621803 | C - Flat No 1311 | NA | 0.0000 | 0.0000 | 293 | 621782 | 31 | 0 | [6 empty] | 0.0000
315 | 621804 | C -1311 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 314 | 621803 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
316 | 621805 | C - Flat No 1312 | NA | 0.0000 | 0.0000 | 293 | 621782 | 31 | 0 | [6 empty] | 0.0000
317 | 621806 | C -1312 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 316 | 621805 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
318 | 621807 | C - Flat No 1313 | NA | 0.0000 | 0.0000 | 293 | 621782 | 31 | 0 | [6 empty] | 0.0000
319 | 621808 | C -1313 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 318 | 621807 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
320 | 621809 | C - Flat No 1314 | NA | 0.0000 | 0.0000 | 293 | 621782 | 31 | 0 | [6 empty] | 0.0000
321 | 621810 | C -1314 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 320 | 621809 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
322 | 621812 | C - 14th Floor | NA | 0.0000 | 0.0000 | 1 | 621433 | 31 | 0 | [6 empty] | 0.0000
323 | 621813 | C - Flat No 1401 | NA | 0.0000 | 0.0000 | 322 | 621812 | 31 | 0 | [6 empty] | 0.0000
324 | 621814 | C -1401 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 323 | 621813 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
325 | 621815 | C - Flat No 1402 | NA | 0.0000 | 0.0000 | 322 | 621812 | 31 | 0 | [6 empty] | 0.0000
326 | 621816 | C -1402 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 325 | 621815 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
327 | 621817 | C - Flat No 1403 | NA | 0.0000 | 0.0000 | 322 | 621812 | 31 | 0 | [6 empty] | 0.0000
328 | 621818 | C -1403 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 327 | 621817 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
329 | 621819 | C - Flat No 1404 | NA | 0.0000 | 0.0000 | 322 | 621812 | 31 | 0 | [6 empty] | 0.0000
330 | 621820 | C -1404 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 329 | 621819 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
331 | 621821 | C - Flat No 1405 | NA | 0.0000 | 0.0000 | 322 | 621812 | 31 | 0 | [6 empty] | 0.0000
332 | 621822 | C -1405 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 331 | 621821 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
333 | 621823 | C - Flat No 1406 | NA | 0.0000 | 0.0000 | 322 | 621812 | 31 | 0 | [6 empty] | 0.0000
334 | 621824 | C -1406 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 333 | 621823 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
335 | 621825 | C - Flat No 1407 | NA | 0.0000 | 0.0000 | 322 | 621812 | 31 | 0 | [6 empty] | 0.0000
336 | 621826 | C -1407 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 335 | 621825 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
337 | 621827 | C - Flat No 1408 | NA | 0.0000 | 0.0000 | 322 | 621812 | 31 | 0 | [6 empty] | 0.0000
338 | 621828 | C -1408 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 337 | 621827 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
339 | 621829 | C - Flat No 1409 | NA | 0.0000 | 0.0000 | 322 | 621812 | 31 | 0 | [6 empty] | 0.0000
340 | 621830 | C -1409 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 339 | 621829 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
341 | 621831 | C - Flat No 1410 | NA | 0.0000 | 0.0000 | 322 | 621812 | 31 | 0 | [6 empty] | 0.0000
342 | 621832 | C -1410 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 341 | 621831 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
343 | 621833 | C - Flat No 1411 | NA | 0.0000 | 0.0000 | 322 | 621812 | 31 | 0 | [6 empty] | 0.0000
344 | 621834 | C -1411 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 343 | 621833 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
345 | 621835 | C - Flat No 1412 | NA | 0.0000 | 0.0000 | 322 | 621812 | 31 | 0 | [6 empty] | 0.0000
346 | 621836 | C -1412 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 345 | 621835 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
347 | 621837 | C - Flat No 1413 | NA | 0.0000 | 0.0000 | 322 | 621812 | 31 | 0 | [6 empty] | 0.0000
348 | 621838 | C -1413 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 347 | 621837 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
349 | 621839 | C - Flat No 1414 | NA | 0.0000 | 0.0000 | 322 | 621812 | 31 | 0 | [6 empty] | 0.0000
350 | 621840 | C -1414 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 349 | 621839 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000