## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 622248 | C - Kitchen Otta | NA | 0.0000 | 0.0000 | 0 | 567586 | 31 | 0 | [6 empty] | 0.0000
2 | 622307 | C - 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 622248 | 31 | 0 | [6 empty] | 0.0000
3 | 622308 | C - Flat No 301 | NA | 0.0000 | 0.0000 | 2 | 622307 | 31 | 0 | [6 empty] | 0.0000
4 | 622309 | C -301 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 3 | 622308 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
5 | 622310 | C - Flat No 302 | NA | 0.0000 | 0.0000 | 2 | 622307 | 31 | 0 | [6 empty] | 0.0000
6 | 622311 | C -302 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 5 | 622310 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
7 | 622312 | C - Flat No 303 | NA | 0.0000 | 0.0000 | 2 | 622307 | 31 | 0 | [6 empty] | 0.0000
8 | 622313 | C -303 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 7 | 622312 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
9 | 622314 | C - Flat No 304 | NA | 0.0000 | 0.0000 | 2 | 622307 | 31 | 0 | [6 empty] | 0.0000
10 | 622315 | C -304 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 9 | 622314 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
11 | 622316 | C - Flat No 305 | NA | 0.0000 | 0.0000 | 2 | 622307 | 31 | 0 | [6 empty] | 0.0000
12 | 622317 | C -305 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 11 | 622316 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
13 | 622318 | C - Flat No 306 | NA | 0.0000 | 0.0000 | 2 | 622307 | 31 | 0 | [6 empty] | 0.0000
14 | 622319 | C -306 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 13 | 622318 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
15 | 622320 | C - Flat No 307 | NA | 0.0000 | 0.0000 | 2 | 622307 | 31 | 0 | [6 empty] | 0.0000
16 | 622321 | C -307 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 15 | 622320 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
17 | 622322 | C - Flat No 308 | NA | 0.0000 | 0.0000 | 2 | 622307 | 31 | 0 | [6 empty] | 0.0000
18 | 622323 | C -308 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 17 | 622322 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
19 | 622324 | C - Flat No 309 | NA | 0.0000 | 0.0000 | 2 | 622307 | 31 | 0 | [6 empty] | 0.0000
20 | 622325 | C -309 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 19 | 622324 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
21 | 622326 | C - Flat No 310 | NA | 0.0000 | 0.0000 | 2 | 622307 | 31 | 0 | [6 empty] | 0.0000
22 | 622327 | C -310 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 21 | 622326 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
23 | 622328 | C - Flat No 311 | NA | 0.0000 | 0.0000 | 2 | 622307 | 31 | 0 | [6 empty] | 0.0000
24 | 622329 | C -311 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 23 | 622328 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
25 | 622330 | C - Flat No 312 | NA | 0.0000 | 0.0000 | 2 | 622307 | 31 | 0 | [6 empty] | 0.0000
26 | 622331 | C -312 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 25 | 622330 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
27 | 622332 | C - Flat No 313 | NA | 0.0000 | 0.0000 | 2 | 622307 | 31 | 0 | [6 empty] | 0.0000
28 | 622333 | C -313 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 27 | 622332 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
29 | 622334 | C - Flat No 314 | NA | 0.0000 | 0.0000 | 2 | 622307 | 31 | 0 | [6 empty] | 0.0000
30 | 622335 | C -314 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 29 | 622334 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
31 | 622336 | C - 4th Floor | NA | 0.0000 | 0.0000 | 1 | 622248 | 31 | 0 | [6 empty] | 0.0000
32 | 622337 | C - Flat No 401 | NA | 0.0000 | 0.0000 | 31 | 622336 | 31 | 0 | [6 empty] | 0.0000
33 | 622338 | C -401 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 32 | 622337 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
34 | 622339 | C - Flat No 402 | NA | 0.0000 | 0.0000 | 31 | 622336 | 31 | 0 | [6 empty] | 0.0000
35 | 622340 | C -402 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 34 | 622339 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
36 | 622341 | C - Flat No 403 | NA | 0.0000 | 0.0000 | 31 | 622336 | 31 | 0 | [6 empty] | 0.0000
37 | 622342 | C -403 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 36 | 622341 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
38 | 622343 | C - Flat No 404 | NA | 0.0000 | 0.0000 | 31 | 622336 | 31 | 0 | [6 empty] | 0.0000
39 | 622344 | C -404 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 38 | 622343 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
40 | 622345 | C - Flat No 405 | NA | 0.0000 | 0.0000 | 31 | 622336 | 31 | 0 | [6 empty] | 0.0000
41 | 622346 | C -405 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 40 | 622345 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
42 | 622347 | C - Flat No 406 | NA | 0.0000 | 0.0000 | 31 | 622336 | 31 | 0 | [6 empty] | 0.0000
43 | 622348 | C -406 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 42 | 622347 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
44 | 622349 | C - Flat No 407 | NA | 0.0000 | 0.0000 | 31 | 622336 | 31 | 0 | [6 empty] | 0.0000
45 | 622350 | C -407 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 44 | 622349 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
46 | 622351 | C - Flat No 408 | NA | 0.0000 | 0.0000 | 31 | 622336 | 31 | 0 | [6 empty] | 0.0000
47 | 622352 | C -408 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 46 | 622351 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
48 | 622353 | C - Flat No 409 | NA | 0.0000 | 0.0000 | 31 | 622336 | 31 | 0 | [6 empty] | 0.0000
49 | 622354 | C -409 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 48 | 622353 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
50 | 622355 | C - Flat No 410 | NA | 0.0000 | 0.0000 | 31 | 622336 | 31 | 0 | [6 empty] | 0.0000
51 | 622356 | C -410 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 50 | 622355 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
52 | 622357 | C - Flat No 411 | NA | 0.0000 | 0.0000 | 31 | 622336 | 31 | 0 | [6 empty] | 0.0000
53 | 622358 | C -411 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 52 | 622357 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
54 | 622359 | C - Flat No 412 | NA | 0.0000 | 0.0000 | 31 | 622336 | 31 | 0 | [6 empty] | 0.0000
55 | 622360 | C -412 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 54 | 622359 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
56 | 622361 | C - Flat No 413 | NA | 0.0000 | 0.0000 | 31 | 622336 | 31 | 0 | [6 empty] | 0.0000
57 | 622362 | C -413 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 56 | 622361 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
58 | 622363 | C - Flat No 414 | NA | 0.0000 | 0.0000 | 31 | 622336 | 31 | 0 | [6 empty] | 0.0000
59 | 622364 | C -414 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 58 | 622363 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
60 | 622365 | C - 5th Floor | NA | 0.0000 | 0.0000 | 1 | 622248 | 31 | 0 | [6 empty] | 0.0000
61 | 622366 | C - Flat No 501 | NA | 0.0000 | 0.0000 | 60 | 622365 | 31 | 0 | [6 empty] | 0.0000
62 | 622367 | C -501 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 61 | 622366 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
63 | 622368 | C - Flat No 502 | NA | 0.0000 | 0.0000 | 60 | 622365 | 31 | 0 | [6 empty] | 0.0000
64 | 622369 | C -502 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 63 | 622368 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
65 | 622370 | C - Flat No 503 | NA | 0.0000 | 0.0000 | 60 | 622365 | 31 | 0 | [6 empty] | 0.0000
66 | 622371 | C -503 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 65 | 622370 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
67 | 622372 | C - Flat No 504 | NA | 0.0000 | 0.0000 | 60 | 622365 | 31 | 0 | [6 empty] | 0.0000
68 | 622373 | C -504 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 67 | 622372 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
69 | 622374 | C - Flat No 505 | NA | 0.0000 | 0.0000 | 60 | 622365 | 31 | 0 | [6 empty] | 0.0000
70 | 622375 | C -505 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 69 | 622374 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
71 | 622376 | C - Flat No 506 | NA | 0.0000 | 0.0000 | 60 | 622365 | 31 | 0 | [6 empty] | 0.0000
72 | 622377 | C -506 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 71 | 622376 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
73 | 622378 | C - Flat No 507 | NA | 0.0000 | 0.0000 | 60 | 622365 | 31 | 0 | [6 empty] | 0.0000
74 | 622379 | C -507 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 73 | 622378 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
75 | 622380 | C - Flat No 508 | NA | 0.0000 | 0.0000 | 60 | 622365 | 31 | 0 | [6 empty] | 0.0000
76 | 622381 | C -508 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 75 | 622380 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
77 | 622382 | C - Flat No 509 | NA | 0.0000 | 0.0000 | 60 | 622365 | 31 | 0 | [6 empty] | 0.0000
78 | 622383 | C -509 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 77 | 622382 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
79 | 622384 | C - Flat No 510 | NA | 0.0000 | 0.0000 | 60 | 622365 | 31 | 0 | [6 empty] | 0.0000
80 | 622385 | C -510 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 79 | 622384 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
81 | 622386 | C - Flat No 511 | NA | 0.0000 | 0.0000 | 60 | 622365 | 31 | 0 | [6 empty] | 0.0000
82 | 622387 | C -511 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 81 | 622386 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
83 | 622388 | C - Flat No 512 | NA | 0.0000 | 0.0000 | 60 | 622365 | 31 | 0 | [6 empty] | 0.0000
84 | 622389 | C -512 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 83 | 622388 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
85 | 622390 | C - Flat No 513 | NA | 0.0000 | 0.0000 | 60 | 622365 | 31 | 0 | [6 empty] | 0.0000
86 | 622391 | C -513 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 85 | 622390 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
87 | 622392 | C - Flat No 514 | NA | 0.0000 | 0.0000 | 60 | 622365 | 31 | 0 | [6 empty] | 0.0000
88 | 622393 | C -514 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 87 | 622392 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
89 | 622394 | C - 6th Floor | NA | 0.0000 | 0.0000 | 1 | 622248 | 31 | 0 | [6 empty] | 0.0000
90 | 622395 | C - Flat No 601 | NA | 0.0000 | 0.0000 | 89 | 622394 | 31 | 0 | [6 empty] | 0.0000
91 | 622396 | C -601 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 90 | 622395 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
92 | 622397 | C - Flat No 602 | NA | 0.0000 | 0.0000 | 89 | 622394 | 31 | 0 | [6 empty] | 0.0000
93 | 622398 | C -602 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 92 | 622397 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
94 | 622399 | C - Flat No 603 | NA | 0.0000 | 0.0000 | 89 | 622394 | 31 | 0 | [6 empty] | 0.0000
95 | 622400 | C -603 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 94 | 622399 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
96 | 622401 | C - Flat No 604 | NA | 0.0000 | 0.0000 | 89 | 622394 | 31 | 0 | [6 empty] | 0.0000
97 | 622402 | C -604 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 96 | 622401 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
98 | 622403 | C - Flat No 605 | NA | 0.0000 | 0.0000 | 89 | 622394 | 31 | 0 | [6 empty] | 0.0000
99 | 622404 | C -605 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 98 | 622403 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
100 | 622405 | C - Flat No 606 | NA | 0.0000 | 0.0000 | 89 | 622394 | 31 | 0 | [6 empty] | 0.0000
101 | 622406 | C -606 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 100 | 622405 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
102 | 622407 | C - Flat No 607 | NA | 0.0000 | 0.0000 | 89 | 622394 | 31 | 0 | [6 empty] | 0.0000
103 | 622408 | C -607 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 102 | 622407 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
104 | 622409 | C - Flat No 608 | NA | 0.0000 | 0.0000 | 89 | 622394 | 31 | 0 | [6 empty] | 0.0000
105 | 622410 | C -608 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 104 | 622409 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
106 | 622411 | C - Flat No 609 | NA | 0.0000 | 0.0000 | 89 | 622394 | 31 | 0 | [6 empty] | 0.0000
107 | 622412 | C -609 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 106 | 622411 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
108 | 622413 | C - Flat No 610 | NA | 0.0000 | 0.0000 | 89 | 622394 | 31 | 0 | [6 empty] | 0.0000
109 | 622414 | C -610 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 108 | 622413 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
110 | 622415 | C - Flat No 611 | NA | 0.0000 | 0.0000 | 89 | 622394 | 31 | 0 | [6 empty] | 0.0000
111 | 622416 | C -611 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 110 | 622415 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
112 | 622417 | C - Flat No 612 | NA | 0.0000 | 0.0000 | 89 | 622394 | 31 | 0 | [6 empty] | 0.0000
113 | 622418 | C -612 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 112 | 622417 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
114 | 622419 | C - Flat No 613 | NA | 0.0000 | 0.0000 | 89 | 622394 | 31 | 0 | [6 empty] | 0.0000
115 | 622420 | C -613 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 114 | 622419 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
116 | 622421 | C - Flat No 614 | NA | 0.0000 | 0.0000 | 89 | 622394 | 31 | 0 | [6 empty] | 0.0000
117 | 622422 | C -614 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 116 | 622421 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
118 | 622423 | C - 7th Floor | NA | 0.0000 | 0.0000 | 1 | 622248 | 31 | 0 | [6 empty] | 0.0000
119 | 622424 | C - Flat No 701 | NA | 0.0000 | 0.0000 | 118 | 622423 | 31 | 0 | [6 empty] | 0.0000
120 | 622425 | C -701 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 119 | 622424 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
121 | 622426 | C - Flat No 702 | NA | 0.0000 | 0.0000 | 118 | 622423 | 31 | 0 | [6 empty] | 0.0000
122 | 622427 | C -702 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 121 | 622426 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
123 | 622428 | C - Flat No 703 | NA | 0.0000 | 0.0000 | 118 | 622423 | 31 | 0 | [6 empty] | 0.0000
124 | 622429 | C -703 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 123 | 622428 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
125 | 622430 | C - Flat No 704 | NA | 0.0000 | 0.0000 | 118 | 622423 | 31 | 0 | [6 empty] | 0.0000
126 | 622431 | C -704 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 125 | 622430 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
127 | 622432 | C - Flat No 705 | NA | 0.0000 | 0.0000 | 118 | 622423 | 31 | 0 | [6 empty] | 0.0000
128 | 622433 | C -705 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 127 | 622432 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
129 | 622434 | C - Flat No 706 | NA | 0.0000 | 0.0000 | 118 | 622423 | 31 | 0 | [6 empty] | 0.0000
130 | 622435 | C -706 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 129 | 622434 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
131 | 622436 | C - Flat No 707 | NA | 0.0000 | 0.0000 | 118 | 622423 | 31 | 0 | [6 empty] | 0.0000
132 | 622437 | C -707 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 131 | 622436 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
133 | 622438 | C - Flat No 708 | NA | 0.0000 | 0.0000 | 118 | 622423 | 31 | 0 | [6 empty] | 0.0000
134 | 622439 | C -708 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 133 | 622438 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
135 | 622440 | C - Flat No 709 | NA | 0.0000 | 0.0000 | 118 | 622423 | 31 | 0 | [6 empty] | 0.0000
136 | 622441 | C -709 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 135 | 622440 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
137 | 622442 | C - Flat No 710 | NA | 0.0000 | 0.0000 | 118 | 622423 | 31 | 0 | [6 empty] | 0.0000
138 | 622443 | C -710 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 137 | 622442 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
139 | 622444 | C - Flat No 711 | NA | 0.0000 | 0.0000 | 118 | 622423 | 31 | 0 | [6 empty] | 0.0000
140 | 622445 | C -711 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 139 | 622444 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
141 | 622446 | C - Flat No 712 | NA | 0.0000 | 0.0000 | 118 | 622423 | 31 | 0 | [6 empty] | 0.0000
142 | 622447 | C -712 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 141 | 622446 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
143 | 622448 | C - Flat No 713 | NA | 0.0000 | 0.0000 | 118 | 622423 | 31 | 0 | [6 empty] | 0.0000
144 | 622449 | C -713 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 143 | 622448 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
145 | 622450 | C - Flat No 714 | NA | 0.0000 | 0.0000 | 118 | 622423 | 31 | 0 | [6 empty] | 0.0000
146 | 622451 | C -714 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 145 | 622450 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
147 | 622452 | C - 8th Floor | NA | 0.0000 | 0.0000 | 1 | 622248 | 31 | 0 | [6 empty] | 0.0000
148 | 622453 | C - Flat No 801 | NA | 0.0000 | 0.0000 | 147 | 622452 | 31 | 0 | [6 empty] | 0.0000
149 | 622454 | C -801 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 148 | 622453 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
150 | 622455 | C - Flat No 802 | NA | 0.0000 | 0.0000 | 147 | 622452 | 31 | 0 | [6 empty] | 0.0000
151 | 622456 | C -802 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 150 | 622455 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
152 | 622457 | C - Flat No 803 | NA | 0.0000 | 0.0000 | 147 | 622452 | 31 | 0 | [6 empty] | 0.0000
153 | 622458 | C -803 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 152 | 622457 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
154 | 622459 | C - Flat No 804 | NA | 0.0000 | 0.0000 | 147 | 622452 | 31 | 0 | [6 empty] | 0.0000
155 | 622460 | C -804 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 154 | 622459 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
156 | 622461 | C - Flat No 805 | NA | 0.0000 | 0.0000 | 147 | 622452 | 31 | 0 | [6 empty] | 0.0000
157 | 622462 | C -805 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 156 | 622461 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
158 | 622463 | C - Flat No 806 | NA | 0.0000 | 0.0000 | 147 | 622452 | 31 | 0 | [6 empty] | 0.0000
159 | 622464 | C -806 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 158 | 622463 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
160 | 622465 | C - Flat No 807 | NA | 0.0000 | 0.0000 | 147 | 622452 | 31 | 0 | [6 empty] | 0.0000
161 | 622466 | C -807 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 160 | 622465 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
162 | 622467 | C - Flat No 808 | NA | 0.0000 | 0.0000 | 147 | 622452 | 31 | 0 | [6 empty] | 0.0000
163 | 622468 | C -808 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 162 | 622467 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
164 | 622469 | C - Flat No 809 | NA | 0.0000 | 0.0000 | 147 | 622452 | 31 | 0 | [6 empty] | 0.0000
165 | 622470 | C -809 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 164 | 622469 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
166 | 622471 | C - Flat No 810 | NA | 0.0000 | 0.0000 | 147 | 622452 | 31 | 0 | [6 empty] | 0.0000
167 | 622472 | C -810 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 166 | 622471 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
168 | 622473 | C - Flat No 811 | NA | 0.0000 | 0.0000 | 147 | 622452 | 31 | 0 | [6 empty] | 0.0000
169 | 622474 | C -811 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 168 | 622473 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
170 | 622475 | C - Flat No 812 | NA | 0.0000 | 0.0000 | 147 | 622452 | 31 | 0 | [6 empty] | 0.0000
171 | 622476 | C -812 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 170 | 622475 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
172 | 622477 | C - Flat No 813 | NA | 0.0000 | 0.0000 | 147 | 622452 | 31 | 0 | [6 empty] | 0.0000
173 | 622478 | C -813 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 172 | 622477 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
174 | 622479 | C - Flat No 814 | NA | 0.0000 | 0.0000 | 147 | 622452 | 31 | 0 | [6 empty] | 0.0000
175 | 622480 | C -814 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 174 | 622479 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
176 | 622481 | C - 9th Floor | NA | 0.0000 | 0.0000 | 1 | 622248 | 31 | 0 | [6 empty] | 0.0000
177 | 622482 | C - Flat No 901 | NA | 0.0000 | 0.0000 | 176 | 622481 | 31 | 0 | [6 empty] | 0.0000
178 | 622483 | C -901 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 177 | 622482 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
179 | 622484 | C - Flat No 902 | NA | 0.0000 | 0.0000 | 176 | 622481 | 31 | 0 | [6 empty] | 0.0000
180 | 622485 | C -902 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 179 | 622484 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
181 | 622486 | C - Flat No 903 | NA | 0.0000 | 0.0000 | 176 | 622481 | 31 | 0 | [6 empty] | 0.0000
182 | 622487 | C -903 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 181 | 622486 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
183 | 622488 | C - Flat No 904 | NA | 0.0000 | 0.0000 | 176 | 622481 | 31 | 0 | [6 empty] | 0.0000
184 | 622489 | C -904 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 183 | 622488 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
185 | 622490 | C - Flat No 905 | NA | 0.0000 | 0.0000 | 176 | 622481 | 31 | 0 | [6 empty] | 0.0000
186 | 622491 | C -905 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 185 | 622490 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
187 | 622492 | C - Flat No 906 | NA | 0.0000 | 0.0000 | 176 | 622481 | 31 | 0 | [6 empty] | 0.0000
188 | 622493 | C -906 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 187 | 622492 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
189 | 622494 | C - Flat No 907 | NA | 0.0000 | 0.0000 | 176 | 622481 | 31 | 0 | [6 empty] | 0.0000
190 | 622495 | C -907 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 189 | 622494 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
191 | 622496 | C - Flat No 908 | NA | 0.0000 | 0.0000 | 176 | 622481 | 31 | 0 | [6 empty] | 0.0000
192 | 622497 | C -908 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 191 | 622496 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
193 | 622498 | C - Flat No 909 | NA | 0.0000 | 0.0000 | 176 | 622481 | 31 | 0 | [6 empty] | 0.0000
194 | 622499 | C -909 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 193 | 622498 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
195 | 622500 | C - Flat No 910 | NA | 0.0000 | 0.0000 | 176 | 622481 | 31 | 0 | [6 empty] | 0.0000
196 | 622501 | C -910 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 195 | 622500 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
197 | 622502 | C - Flat No 911 | NA | 0.0000 | 0.0000 | 176 | 622481 | 31 | 0 | [6 empty] | 0.0000
198 | 622503 | C -911 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 197 | 622502 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
199 | 622504 | C - Flat No 912 | NA | 0.0000 | 0.0000 | 176 | 622481 | 31 | 0 | [6 empty] | 0.0000
200 | 622505 | C -912 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 199 | 622504 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
201 | 622506 | C - Flat No 913 | NA | 0.0000 | 0.0000 | 176 | 622481 | 31 | 0 | [6 empty] | 0.0000
202 | 622507 | C -913 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 201 | 622506 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
203 | 622508 | C - Flat No 914 | NA | 0.0000 | 0.0000 | 176 | 622481 | 31 | 0 | [6 empty] | 0.0000
204 | 622509 | C -914 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 203 | 622508 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
205 | 622510 | C - 10th Floor | NA | 0.0000 | 0.0000 | 1 | 622248 | 31 | 0 | [6 empty] | 0.0000
206 | 622511 | C - Flat No 1001 | NA | 0.0000 | 0.0000 | 205 | 622510 | 31 | 0 | [6 empty] | 0.0000
207 | 622512 | C -1001 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 206 | 622511 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
208 | 622513 | C - Flat No 1002 | NA | 0.0000 | 0.0000 | 205 | 622510 | 31 | 0 | [6 empty] | 0.0000
209 | 622514 | C -1002 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 208 | 622513 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
210 | 622515 | C - Flat No 1003 | NA | 0.0000 | 0.0000 | 205 | 622510 | 31 | 0 | [6 empty] | 0.0000
211 | 622516 | C -1003 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 210 | 622515 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
212 | 622517 | C - Flat No 1004 | NA | 0.0000 | 0.0000 | 205 | 622510 | 31 | 0 | [6 empty] | 0.0000
213 | 622518 | C -1004 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 212 | 622517 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
214 | 622519 | C - Flat No 1005 | NA | 0.0000 | 0.0000 | 205 | 622510 | 31 | 0 | [6 empty] | 0.0000
215 | 622520 | C -1005 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 214 | 622519 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
216 | 622521 | C - Flat No 1006 | NA | 0.0000 | 0.0000 | 205 | 622510 | 31 | 0 | [6 empty] | 0.0000
217 | 622522 | C -1006 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 216 | 622521 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
218 | 622523 | C - Flat No 1007 | NA | 0.0000 | 0.0000 | 205 | 622510 | 31 | 0 | [6 empty] | 0.0000
219 | 622524 | C -1007 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 218 | 622523 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
220 | 622525 | C - Flat No 1008 | NA | 0.0000 | 0.0000 | 205 | 622510 | 31 | 0 | [6 empty] | 0.0000
221 | 622526 | C -1008 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 220 | 622525 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
222 | 622527 | C - Flat No 1009 | NA | 0.0000 | 0.0000 | 205 | 622510 | 31 | 0 | [6 empty] | 0.0000
223 | 622528 | C -1009 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 222 | 622527 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
224 | 622529 | C - Flat No 1010 | NA | 0.0000 | 0.0000 | 205 | 622510 | 31 | 0 | [6 empty] | 0.0000
225 | 622530 | C -1010 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 224 | 622529 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
226 | 622531 | C - Flat No 1011 | NA | 0.0000 | 0.0000 | 205 | 622510 | 31 | 0 | [6 empty] | 0.0000
227 | 622532 | C -1011 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 226 | 622531 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
228 | 622533 | C - Flat No 1012 | NA | 0.0000 | 0.0000 | 205 | 622510 | 31 | 0 | [6 empty] | 0.0000
229 | 622534 | C -1012 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 228 | 622533 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
230 | 622535 | C - Flat No 1013 | NA | 0.0000 | 0.0000 | 205 | 622510 | 31 | 0 | [6 empty] | 0.0000
231 | 622536 | C -1013 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 230 | 622535 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
232 | 622537 | C - Flat No 1014 | NA | 0.0000 | 0.0000 | 205 | 622510 | 31 | 0 | [6 empty] | 0.0000
233 | 622538 | C -1014 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 232 | 622537 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
234 | 622539 | C - 11th Floor | NA | 0.0000 | 0.0000 | 1 | 622248 | 31 | 0 | [6 empty] | 0.0000
235 | 622540 | C - Flat No 1101 | NA | 0.0000 | 0.0000 | 234 | 622539 | 31 | 0 | [6 empty] | 0.0000
236 | 622541 | C -1101 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 235 | 622540 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
237 | 622542 | C - Flat No 1102 | NA | 0.0000 | 0.0000 | 234 | 622539 | 31 | 0 | [6 empty] | 0.0000
238 | 622543 | C -1102 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 237 | 622542 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
239 | 622544 | C - Flat No 1103 | NA | 0.0000 | 0.0000 | 234 | 622539 | 31 | 0 | [6 empty] | 0.0000
240 | 622545 | C -1103 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 239 | 622544 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
241 | 622546 | C - Flat No 1104 | NA | 0.0000 | 0.0000 | 234 | 622539 | 31 | 0 | [6 empty] | 0.0000
242 | 622547 | C -1104 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 241 | 622546 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
243 | 622548 | C - Flat No 1105 | NA | 0.0000 | 0.0000 | 234 | 622539 | 31 | 0 | [6 empty] | 0.0000
244 | 622549 | C -1105 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 243 | 622548 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
245 | 622550 | C - Flat No 1106 | NA | 0.0000 | 0.0000 | 234 | 622539 | 31 | 0 | [6 empty] | 0.0000
246 | 622551 | C -1106 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 245 | 622550 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
247 | 622552 | C - Flat No 1107 | NA | 0.0000 | 0.0000 | 234 | 622539 | 31 | 0 | [6 empty] | 0.0000
248 | 622553 | C -1107 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 247 | 622552 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
249 | 622554 | C - Flat No 1108 | NA | 0.0000 | 0.0000 | 234 | 622539 | 31 | 0 | [6 empty] | 0.0000
250 | 622555 | C -1108 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 249 | 622554 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
251 | 622556 | C - Flat No 1109 | NA | 0.0000 | 0.0000 | 234 | 622539 | 31 | 0 | [6 empty] | 0.0000
252 | 622557 | C -1109 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 251 | 622556 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
253 | 622558 | C - Flat No 1110 | NA | 0.0000 | 0.0000 | 234 | 622539 | 31 | 0 | [6 empty] | 0.0000
254 | 622559 | C -1110 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 253 | 622558 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
255 | 622560 | C - Flat No 1111 | NA | 0.0000 | 0.0000 | 234 | 622539 | 31 | 0 | [6 empty] | 0.0000
256 | 622561 | C -1111 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 255 | 622560 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
257 | 622562 | C - Flat No 1112 | NA | 0.0000 | 0.0000 | 234 | 622539 | 31 | 0 | [6 empty] | 0.0000
258 | 622563 | C -1112 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 257 | 622562 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
259 | 622564 | C - Flat No 1113 | NA | 0.0000 | 0.0000 | 234 | 622539 | 31 | 0 | [6 empty] | 0.0000
260 | 622565 | C -1113 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 259 | 622564 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
261 | 622566 | C - Flat No 1114 | NA | 0.0000 | 0.0000 | 234 | 622539 | 31 | 0 | [6 empty] | 0.0000
262 | 622567 | C -1114 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 261 | 622566 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
263 | 622568 | C - 12th Floor | NA | 0.0000 | 0.0000 | 1 | 622248 | 31 | 0 | [6 empty] | 0.0000
264 | 622569 | C - Flat No 1201 | NA | 0.0000 | 0.0000 | 263 | 622568 | 31 | 0 | [6 empty] | 0.0000
265 | 622570 | C -1201 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 264 | 622569 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
266 | 622571 | C - Flat No 1202 | NA | 0.0000 | 0.0000 | 263 | 622568 | 31 | 0 | [6 empty] | 0.0000
267 | 622572 | C -1202 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 266 | 622571 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
268 | 622573 | C - Flat No 1203 | NA | 0.0000 | 0.0000 | 263 | 622568 | 31 | 0 | [6 empty] | 0.0000
269 | 622574 | C -1203 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 268 | 622573 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
270 | 622575 | C - Flat No 1204 | NA | 0.0000 | 0.0000 | 263 | 622568 | 31 | 0 | [6 empty] | 0.0000
271 | 622576 | C -1204 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 270 | 622575 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
272 | 622577 | C - Flat No 1205 | NA | 0.0000 | 0.0000 | 263 | 622568 | 31 | 0 | [6 empty] | 0.0000
273 | 622578 | C -1205 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 272 | 622577 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
274 | 622579 | C - Flat No 1206 | NA | 0.0000 | 0.0000 | 263 | 622568 | 31 | 0 | [6 empty] | 0.0000
275 | 622580 | C -1206 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 274 | 622579 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
276 | 622581 | C - Flat No 1207 | NA | 0.0000 | 0.0000 | 263 | 622568 | 31 | 0 | [6 empty] | 0.0000
277 | 622582 | C -1207 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 276 | 622581 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
278 | 622583 | C - Flat No 1208 | NA | 0.0000 | 0.0000 | 263 | 622568 | 31 | 0 | [6 empty] | 0.0000
279 | 622584 | C -1208 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 278 | 622583 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
280 | 622585 | C - Flat No 1209 | NA | 0.0000 | 0.0000 | 263 | 622568 | 31 | 0 | [6 empty] | 0.0000
281 | 622586 | C -1209 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 280 | 622585 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
282 | 622587 | C - Flat No 1210 | NA | 0.0000 | 0.0000 | 263 | 622568 | 31 | 0 | [6 empty] | 0.0000
283 | 622588 | C -1210 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 282 | 622587 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
284 | 622589 | C - Flat No 1211 | NA | 0.0000 | 0.0000 | 263 | 622568 | 31 | 0 | [6 empty] | 0.0000
285 | 622590 | C -1211 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 284 | 622589 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
286 | 622591 | C - Flat No 1212 | NA | 0.0000 | 0.0000 | 263 | 622568 | 31 | 0 | [6 empty] | 0.0000
287 | 622592 | C -1212 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 286 | 622591 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
288 | 622593 | C - Flat No 1213 | NA | 0.0000 | 0.0000 | 263 | 622568 | 31 | 0 | [6 empty] | 0.0000
289 | 622594 | C -1213 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 288 | 622593 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
290 | 622595 | C - Flat No 1214 | NA | 0.0000 | 0.0000 | 263 | 622568 | 31 | 0 | [6 empty] | 0.0000
291 | 622596 | C -1214 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 290 | 622595 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
292 | 622597 | C - 13th Floor | NA | 0.0000 | 0.0000 | 1 | 622248 | 31 | 0 | [6 empty] | 0.0000
293 | 622598 | C - Flat No 1301 | NA | 0.0000 | 0.0000 | 292 | 622597 | 31 | 0 | [6 empty] | 0.0000
294 | 622599 | C -1301 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 293 | 622598 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
295 | 622600 | C - Flat No 1302 | NA | 0.0000 | 0.0000 | 292 | 622597 | 31 | 0 | [6 empty] | 0.0000
296 | 622601 | C -1302 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 295 | 622600 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
297 | 622602 | C - Flat No 1303 | NA | 0.0000 | 0.0000 | 292 | 622597 | 31 | 0 | [6 empty] | 0.0000
298 | 622603 | C -1303 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 297 | 622602 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
299 | 622604 | C - Flat No 1304 | NA | 0.0000 | 0.0000 | 292 | 622597 | 31 | 0 | [6 empty] | 0.0000
300 | 622605 | C -1304 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 299 | 622604 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
301 | 622606 | C - Flat No 1305 | NA | 0.0000 | 0.0000 | 292 | 622597 | 31 | 0 | [6 empty] | 0.0000
302 | 622607 | C -1305 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 301 | 622606 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
303 | 622608 | C - Flat No 1306 | NA | 0.0000 | 0.0000 | 292 | 622597 | 31 | 0 | [6 empty] | 0.0000
304 | 622609 | C -1306 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 303 | 622608 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
305 | 622610 | C - Flat No 1307 | NA | 0.0000 | 0.0000 | 292 | 622597 | 31 | 0 | [6 empty] | 0.0000
306 | 622611 | C -1307 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 305 | 622610 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
307 | 622612 | C - Flat No 1308 | NA | 0.0000 | 0.0000 | 292 | 622597 | 31 | 0 | [6 empty] | 0.0000
308 | 622613 | C -1308 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 307 | 622612 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
309 | 622614 | C - Flat No 1309 | NA | 0.0000 | 0.0000 | 292 | 622597 | 31 | 0 | [6 empty] | 0.0000
310 | 622615 | C -1309 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 309 | 622614 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
311 | 622616 | C - Flat No 1310 | NA | 0.0000 | 0.0000 | 292 | 622597 | 31 | 0 | [6 empty] | 0.0000
312 | 622617 | C -1310 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 311 | 622616 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
313 | 622618 | C - Flat No 1311 | NA | 0.0000 | 0.0000 | 292 | 622597 | 31 | 0 | [6 empty] | 0.0000
314 | 622619 | C -1311 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 313 | 622618 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
315 | 622620 | C - Flat No 1312 | NA | 0.0000 | 0.0000 | 292 | 622597 | 31 | 0 | [6 empty] | 0.0000
316 | 622621 | C -1312 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 315 | 622620 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
317 | 622622 | C - Flat No 1313 | NA | 0.0000 | 0.0000 | 292 | 622597 | 31 | 0 | [6 empty] | 0.0000
318 | 622623 | C -1313 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 317 | 622622 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
319 | 622624 | C - Flat No 1314 | NA | 0.0000 | 0.0000 | 292 | 622597 | 31 | 0 | [6 empty] | 0.0000
320 | 622625 | C -1314 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 319 | 622624 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
321 | 622627 | C - 14th Floor | NA | 0.0000 | 0.0000 | 1 | 622248 | 31 | 0 | [6 empty] | 0.0000
322 | 622628 | C - Flat No 1401 | NA | 0.0000 | 0.0000 | 321 | 622627 | 31 | 0 | [6 empty] | 0.0000
323 | 622629 | C -1401 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 322 | 622628 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
324 | 622630 | C - Flat No 1402 | NA | 0.0000 | 0.0000 | 321 | 622627 | 31 | 0 | [6 empty] | 0.0000
325 | 622631 | C -1402 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 324 | 622630 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
326 | 622632 | C - Flat No 1403 | NA | 0.0000 | 0.0000 | 321 | 622627 | 31 | 0 | [6 empty] | 0.0000
327 | 622633 | C -1403 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 326 | 622632 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
328 | 622634 | C - Flat No 1404 | NA | 0.0000 | 0.0000 | 321 | 622627 | 31 | 0 | [6 empty] | 0.0000
329 | 622635 | C -1404 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 328 | 622634 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
330 | 622636 | C - Flat No 1405 | NA | 0.0000 | 0.0000 | 321 | 622627 | 31 | 0 | [6 empty] | 0.0000
331 | 622637 | C -1405 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 330 | 622636 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
332 | 622638 | C - Flat No 1406 | NA | 0.0000 | 0.0000 | 321 | 622627 | 31 | 0 | [6 empty] | 0.0000
333 | 622639 | C -1406 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 332 | 622638 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
334 | 622640 | C - Flat No 1407 | NA | 0.0000 | 0.0000 | 321 | 622627 | 31 | 0 | [6 empty] | 0.0000
335 | 622641 | C -1407 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 334 | 622640 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
336 | 622642 | C - Flat No 1408 | NA | 0.0000 | 0.0000 | 321 | 622627 | 31 | 0 | [6 empty] | 0.0000
337 | 622643 | C -1408 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 336 | 622642 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
338 | 622644 | C - Flat No 1409 | NA | 0.0000 | 0.0000 | 321 | 622627 | 31 | 0 | [6 empty] | 0.0000
339 | 622645 | C -1409 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 338 | 622644 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
340 | 622646 | C - Flat No 1410 | NA | 0.0000 | 0.0000 | 321 | 622627 | 31 | 0 | [6 empty] | 0.0000
341 | 622647 | C -1410 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 340 | 622646 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
342 | 622648 | C - Flat No 1411 | NA | 0.0000 | 0.0000 | 321 | 622627 | 31 | 0 | [6 empty] | 0.0000
343 | 622649 | C -1411 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 342 | 622648 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
344 | 622650 | C - Flat No 1412 | NA | 0.0000 | 0.0000 | 321 | 622627 | 31 | 0 | [6 empty] | 0.0000
345 | 622651 | C -1412 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 344 | 622650 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
346 | 622652 | C - Flat No 1413 | NA | 0.0000 | 0.0000 | 321 | 622627 | 31 | 0 | [6 empty] | 0.0000
347 | 622653 | C -1413 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 346 | 622652 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
348 | 622654 | C - Flat No 1414 | NA | 0.0000 | 0.0000 | 321 | 622627 | 31 | 0 | [6 empty] | 0.0000
349 | 622655 | C -1414 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 348 | 622654 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000