## Sheet1
Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT
Selected Group :- A - Super structure RCC Work (L) | Selected Group :- A - Super structure RCC Work (L) | Selected Group :- A - Super structure RCC Work (L) | Selected Group :- A - Super structure RCC Work (L) | Selected Group :- A - Super structure RCC Work (L) | Selected Group :- A - Super structure RCC Work (L) | Selected Group :- A - Super structure RCC Work (L) | Selected Group :- A - Super structure RCC Work (L) | Selected Group :- A - Super structure RCC Work (L) | Selected Group :- A - Super structure RCC Work (L) | Selected Group :- A - Super structure RCC Work (L) | Selected Group :- A - Super structure RCC Work (L) | Selected Group :- A - Super structure RCC Work (L) | Selected Group :- A - Super structure RCC Work (L) | Selected Group :- A - Super structure RCC Work (L) | Selected Group :- A - Super structure RCC Work (L) | Selected Group :- A - Super structure RCC Work (L)
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 623124 | B - Super structure RCC Work (L) | NA | 0.0000 | 0.0000 | 0 | 623123 | 31 | 0 | [6 empty] | 0.0000
2 | 623125 | B - 1st Slab RCC Work (L) | Sq.Ft | 8310.4800 | 8310.4800 | 1 | 623124 | 4 | 34336 | A - 1st Slab RCC Work (L) | [5 empty] | 0.0000
3 | 623126 | B - 2nd Slab RCC Work (L) | Sq.Ft | 8174.7300 | 8174.7300 | 1 | 623124 | 4 | 34336 | A - 1st Slab RCC Work (L) | [5 empty] | 0.0000
4 | 623127 | B - 3rd Slab RCC Work (L) | Sq.Ft | 8174.7300 | 8174.7300 | 1 | 623124 | 4 | 34336 | A - 1st Slab RCC Work (L) | [5 empty] | 0.0000
5 | 623128 | B - 4th Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34378 | A - 4th Slab RCC Work (L) | [5 empty] | 0.0000
6 | 623129 | B - 5th Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
7 | 623130 | B - 6th Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
8 | 623131 | B - 7th Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
9 | 623132 | B - 8th Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
10 | 623133 | B - 9th Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
11 | 623134 | B - 10th Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
12 | 623135 | B - 11th Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
13 | 623136 | B - 12th Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
14 | 623137 | B - 13th Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
15 | 623138 | B - 14th Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
16 | 623139 | B - 15th Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
17 | 623140 | B - 16th Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
18 | 623141 | B - 17th Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
19 | 623142 | B - 18th Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
20 | 623143 | B - 19th Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
21 | 623144 | B - 20th Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
22 | 623145 | B - 21st Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
23 | 623146 | B - 22nd Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
24 | 623147 | B - 23rd Slab RCC Work (L) | Sq.Ft | 5312.8700 | 5312.8700 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
25 | 623148 | B - 24th Slab RCC Work (L) | Sq.Ft | 5148.4029 | 5148.4029 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
26 | 623149 | B - LMR & OHWT RCC Work (L) | Sq.Ft | 2330.4000 | 2330.4000 | 1 | 623124 | 4 | 34379 | A - 5th Slab RCC Work (L) | [5 empty] | 0.0000
27 | 623150 | B - Super Structure Aluform Work | Sq.Ft | 1.0000 | 1.0000 | 1 | 623124 | 4 | 34381 | A - Super Structure Aluform | [5 empty] | 0.0000