## Sheet1
Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT | Project :-BHOSARI SRA PROJECT
Selected Group :- A - Super Structure RCC Work (M) | Selected Group :- A - Super Structure RCC Work (M) | Selected Group :- A - Super Structure RCC Work (M) | Selected Group :- A - Super Structure RCC Work (M) | Selected Group :- A - Super Structure RCC Work (M) | Selected Group :- A - Super Structure RCC Work (M) | Selected Group :- A - Super Structure RCC Work (M) | Selected Group :- A - Super Structure RCC Work (M) | Selected Group :- A - Super Structure RCC Work (M) | Selected Group :- A - Super Structure RCC Work (M) | Selected Group :- A - Super Structure RCC Work (M) | Selected Group :- A - Super Structure RCC Work (M) | Selected Group :- A - Super Structure RCC Work (M) | Selected Group :- A - Super Structure RCC Work (M) | Selected Group :- A - Super Structure RCC Work (M) | Selected Group :- A - Super Structure RCC Work (M) | Selected Group :- A - Super Structure RCC Work (M)
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 623212 | B - Super Structure RCC Work (M) | NA | 0.0000 | 0.0000 | 0 | 623123 | 31 | 0 | [6 empty] | 0.0000
2 | 623213 | B - 1st Slab RCC Work (M) | Sq.Ft | 8310.5000 | 8310.5000 | 1 | 623212 | 4 | 34382 | A - 1st Slab RCC Work (M) | [5 empty] | 0.0000
3 | 623214 | B - 2nd Slab RCC Work (M) | Sq.Ft | 8174.7000 | 8174.7000 | 1 | 623212 | 4 | 34382 | A - 1st Slab RCC Work (M) | [5 empty] | 0.0000
4 | 623215 | B - 3rd Slab RCC Work (M) | Sq.Ft | 8174.7000 | 8174.7000 | 1 | 623212 | 4 | 34382 | A - 1st Slab RCC Work (M) | [5 empty] | 0.0000
5 | 623216 | B - 4th Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34382 | A - 1st Slab RCC Work (M) | [5 empty] | 0.0000
6 | 623217 | B - 5th Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34384 | A - 5th Slab RCC Work (M) | [5 empty] | 0.0000
7 | 623218 | B - 6th Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34384 | A - 5th Slab RCC Work (M) | [5 empty] | 0.0000
8 | 623219 | B - 7th Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34384 | A - 5th Slab RCC Work (M) | [5 empty] | 0.0000
9 | 623220 | B - 8th Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34385 | A - 8th Slab RCC Work (M) | [5 empty] | 0.0000
10 | 623221 | B - 9th Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34385 | A - 8th Slab RCC Work (M) | [5 empty] | 0.0000
11 | 623222 | B - 10th Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
12 | 623223 | B - 11th Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
13 | 623224 | B - 12th Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
14 | 623225 | B - 13th Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
15 | 623226 | B - 14th Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34386 | A - 10th Slab RCC Work (M) | [5 empty] | 0.0000
16 | 623227 | B - 15th Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34387 | A - 15th Slab RCC Work (M) | [5 empty] | 0.0000
17 | 623228 | B - 16th Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34387 | A - 15th Slab RCC Work (M) | [5 empty] | 0.0000
18 | 623229 | B - 17th Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34387 | A - 15th Slab RCC Work (M) | [5 empty] | 0.0000
19 | 623230 | B - 18th Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34388 | A - 18th Slab RCC Work (M) | [5 empty] | 0.0000
20 | 623231 | B - 19th Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34389 | A - 19th Slab RCC Work (M) | [5 empty] | 0.0000
21 | 623232 | B - 20th Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
22 | 623233 | B - 21st Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
23 | 623234 | B - 22nd Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
24 | 623235 | B - 23rd Slab RCC Work (M) | Sq.Ft | 5312.9000 | 5312.9000 | 1 | 623212 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
25 | 623236 | B - 24th (Terrace) Slab RCC Work (M) | Sq.Ft | 5148.4000 | 5148.4000 | 1 | 623212 | 4 | 34390 | A - 20th Slab RCC Work (M) | [5 empty] | 0.0000
26 | 623237 | B - LMR & OHWT RCC Work (M) | Sq.Ft | 2330.4000 | 2330.4000 | 1 | 623212 | 4 | 34391 | A - LMR & OHWT RCC Work (M) | [5 empty] | 0.0000
27 | 623238 | B - Super Structure Aluform (M) | Sq.Ft | 35695.2650 | 35695.2650 | 1 | 623212 | 4 | 34381 | A - Super Structure Aluform | [5 empty] | 0.0000