## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work | Selected Group :- C - Umra Patti Work
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 625957 | F - Umra Patti Work | NA | 0.0000 | 0.0000 | 0 | 605104 | 31 | 0 | [6 empty] | 0.0000
2 | 625958 | F - 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 625957 | 31 | 0 | [6 empty] | 0.0000
3 | 625959 | F - Flat No 301 | NA | 0.0000 | 0.0000 | 2 | 625958 | 31 | 0 | [6 empty] | 0.0000
4 | 625960 | F -301 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 3 | 625959 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
5 | 625961 | F - Flat No 302 | NA | 0.0000 | 0.0000 | 2 | 625958 | 31 | 0 | [6 empty] | 0.0000
6 | 625962 | F -302 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 5 | 625961 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
7 | 625963 | F - Flat No 303 | NA | 0.0000 | 0.0000 | 2 | 625958 | 31 | 0 | [6 empty] | 0.0000
8 | 625964 | F -303 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 7 | 625963 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
9 | 625965 | F - Flat No 304 | NA | 0.0000 | 0.0000 | 2 | 625958 | 31 | 0 | [6 empty] | 0.0000
10 | 625966 | F -304 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 9 | 625965 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
11 | 625967 | F - Flat No 305 | NA | 0.0000 | 0.0000 | 2 | 625958 | 31 | 0 | [6 empty] | 0.0000
12 | 625968 | F -305 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 11 | 625967 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
13 | 625969 | F - Flat No 306 | NA | 0.0000 | 0.0000 | 2 | 625958 | 31 | 0 | [6 empty] | 0.0000
14 | 625970 | F -306 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 13 | 625969 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
15 | 625971 | F - Flat No 307 | NA | 0.0000 | 0.0000 | 2 | 625958 | 31 | 0 | [6 empty] | 0.0000
16 | 625972 | F -307 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 15 | 625971 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
17 | 625973 | F - Flat No 308 | NA | 0.0000 | 0.0000 | 2 | 625958 | 31 | 0 | [6 empty] | 0.0000
18 | 625974 | F -308 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 17 | 625973 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
19 | 625975 | F - Flat No 309 | NA | 0.0000 | 0.0000 | 2 | 625958 | 31 | 0 | [6 empty] | 0.0000
20 | 625976 | F -309 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 19 | 625975 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
21 | 625977 | F - Flat No 310 | NA | 0.0000 | 0.0000 | 2 | 625958 | 31 | 0 | [6 empty] | 0.0000
22 | 625978 | F -310 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 21 | 625977 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
23 | 625979 | F - Flat No 311 | NA | 0.0000 | 0.0000 | 2 | 625958 | 31 | 0 | [6 empty] | 0.0000
24 | 625980 | F -311 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 23 | 625979 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
25 | 625981 | F - Flat No 312 | NA | 0.0000 | 0.0000 | 2 | 625958 | 31 | 0 | [6 empty] | 0.0000
26 | 625982 | F -312 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 25 | 625981 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
27 | 625983 | F - Flat No 313 | NA | 0.0000 | 0.0000 | 2 | 625958 | 31 | 0 | [6 empty] | 0.0000
28 | 625984 | F -313 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 27 | 625983 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
29 | 625985 | F - Flat No 314 | NA | 0.0000 | 0.0000 | 2 | 625958 | 31 | 0 | [6 empty] | 0.0000
30 | 625986 | F -314 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 29 | 625985 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
31 | 625987 | F - 4th Floor | NA | 0.0000 | 0.0000 | 1 | 625957 | 31 | 0 | [6 empty] | 0.0000
32 | 625988 | F - Flat No 401 | NA | 0.0000 | 0.0000 | 31 | 625987 | 31 | 0 | [6 empty] | 0.0000
33 | 625989 | F -401 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 32 | 625988 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
34 | 625990 | F - Flat No 402 | NA | 0.0000 | 0.0000 | 31 | 625987 | 31 | 0 | [6 empty] | 0.0000
35 | 625991 | F -402 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 34 | 625990 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
36 | 625992 | F - Flat No 403 | NA | 0.0000 | 0.0000 | 31 | 625987 | 31 | 0 | [6 empty] | 0.0000
37 | 625993 | F -403 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 36 | 625992 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
38 | 625994 | F - Flat No 404 | NA | 0.0000 | 0.0000 | 31 | 625987 | 31 | 0 | [6 empty] | 0.0000
39 | 625995 | F -404 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 38 | 625994 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
40 | 625996 | F - Flat No 405 | NA | 0.0000 | 0.0000 | 31 | 625987 | 31 | 0 | [6 empty] | 0.0000
41 | 625997 | F -405 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 40 | 625996 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
42 | 625998 | F - Flat No 406 | NA | 0.0000 | 0.0000 | 31 | 625987 | 31 | 0 | [6 empty] | 0.0000
43 | 625999 | F -406 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 42 | 625998 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
44 | 626000 | F - Flat No 407 | NA | 0.0000 | 0.0000 | 31 | 625987 | 31 | 0 | [6 empty] | 0.0000
45 | 626001 | F -407 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 44 | 626000 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
46 | 626002 | F - Flat No 408 | NA | 0.0000 | 0.0000 | 31 | 625987 | 31 | 0 | [6 empty] | 0.0000
47 | 626003 | F -408 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 46 | 626002 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
48 | 626004 | F - Flat No 409 | NA | 0.0000 | 0.0000 | 31 | 625987 | 31 | 0 | [6 empty] | 0.0000
49 | 626005 | F -409 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 48 | 626004 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
50 | 626006 | F - Flat No 410 | NA | 0.0000 | 0.0000 | 31 | 625987 | 31 | 0 | [6 empty] | 0.0000
51 | 626007 | F -410 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 50 | 626006 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
52 | 626008 | F - Flat No 411 | NA | 0.0000 | 0.0000 | 31 | 625987 | 31 | 0 | [6 empty] | 0.0000
53 | 626009 | F -411 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 52 | 626008 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
54 | 626010 | F - Flat No 412 | NA | 0.0000 | 0.0000 | 31 | 625987 | 31 | 0 | [6 empty] | 0.0000
55 | 626011 | F -412 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 54 | 626010 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
56 | 626012 | F - Flat No 413 | NA | 0.0000 | 0.0000 | 31 | 625987 | 31 | 0 | [6 empty] | 0.0000
57 | 626013 | F -413 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 56 | 626012 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
58 | 626014 | F - Flat No 414 | NA | 0.0000 | 0.0000 | 31 | 625987 | 31 | 0 | [6 empty] | 0.0000
59 | 626015 | F -414 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 58 | 626014 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
60 | 626016 | F - 5th Floor | NA | 0.0000 | 0.0000 | 1 | 625957 | 31 | 0 | [6 empty] | 0.0000
61 | 626017 | F - Flat No 501 | NA | 0.0000 | 0.0000 | 60 | 626016 | 31 | 0 | [6 empty] | 0.0000
62 | 626018 | F -501 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 61 | 626017 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
63 | 626019 | F - Flat No 502 | NA | 0.0000 | 0.0000 | 60 | 626016 | 31 | 0 | [6 empty] | 0.0000
64 | 626020 | F -502 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 63 | 626019 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
65 | 626021 | F - Flat No 503 | NA | 0.0000 | 0.0000 | 60 | 626016 | 31 | 0 | [6 empty] | 0.0000
66 | 626022 | F -503 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 65 | 626021 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
67 | 626023 | F - Flat No 504 | NA | 0.0000 | 0.0000 | 60 | 626016 | 31 | 0 | [6 empty] | 0.0000
68 | 626024 | F -504 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 67 | 626023 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
69 | 626025 | F - Flat No 505 | NA | 0.0000 | 0.0000 | 60 | 626016 | 31 | 0 | [6 empty] | 0.0000
70 | 626026 | F -505 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 69 | 626025 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
71 | 626027 | F - Flat No 506 | NA | 0.0000 | 0.0000 | 60 | 626016 | 31 | 0 | [6 empty] | 0.0000
72 | 626028 | F -506 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 71 | 626027 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
73 | 626029 | F - Flat No 507 | NA | 0.0000 | 0.0000 | 60 | 626016 | 31 | 0 | [6 empty] | 0.0000
74 | 626030 | F -507 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 73 | 626029 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
75 | 626031 | F - Flat No 508 | NA | 0.0000 | 0.0000 | 60 | 626016 | 31 | 0 | [6 empty] | 0.0000
76 | 626032 | F -508 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 75 | 626031 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
77 | 626033 | F - Flat No 509 | NA | 0.0000 | 0.0000 | 60 | 626016 | 31 | 0 | [6 empty] | 0.0000
78 | 626034 | F -509 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 77 | 626033 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
79 | 626035 | F - Flat No 510 | NA | 0.0000 | 0.0000 | 60 | 626016 | 31 | 0 | [6 empty] | 0.0000
80 | 626036 | F -510 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 79 | 626035 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
81 | 626037 | F - Flat No 511 | NA | 0.0000 | 0.0000 | 60 | 626016 | 31 | 0 | [6 empty] | 0.0000
82 | 626038 | F -511 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 81 | 626037 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
83 | 626039 | F - Flat No 512 | NA | 0.0000 | 0.0000 | 60 | 626016 | 31 | 0 | [6 empty] | 0.0000
84 | 626040 | F -512 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 83 | 626039 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
85 | 626041 | F - Flat No 513 | NA | 0.0000 | 0.0000 | 60 | 626016 | 31 | 0 | [6 empty] | 0.0000
86 | 626042 | F -513 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 85 | 626041 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
87 | 626043 | F - Flat No 514 | NA | 0.0000 | 0.0000 | 60 | 626016 | 31 | 0 | [6 empty] | 0.0000
88 | 626044 | F -514 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 87 | 626043 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
89 | 626045 | F - 6th Floor | NA | 0.0000 | 0.0000 | 1 | 625957 | 31 | 0 | [6 empty] | 0.0000
90 | 626046 | F - Flat No 601 | NA | 0.0000 | 0.0000 | 89 | 626045 | 31 | 0 | [6 empty] | 0.0000
91 | 626047 | F -601 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 90 | 626046 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
92 | 626048 | F - Flat No 602 | NA | 0.0000 | 0.0000 | 89 | 626045 | 31 | 0 | [6 empty] | 0.0000
93 | 626049 | F -602 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 92 | 626048 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
94 | 626050 | F - Flat No 603 | NA | 0.0000 | 0.0000 | 89 | 626045 | 31 | 0 | [6 empty] | 0.0000
95 | 626051 | F -603 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 94 | 626050 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
96 | 626052 | F - Flat No 604 | NA | 0.0000 | 0.0000 | 89 | 626045 | 31 | 0 | [6 empty] | 0.0000
97 | 626053 | F -604 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 96 | 626052 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
98 | 626054 | F - Flat No 605 | NA | 0.0000 | 0.0000 | 89 | 626045 | 31 | 0 | [6 empty] | 0.0000
99 | 626055 | F -605 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 98 | 626054 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
100 | 626056 | F - Flat No 606 | NA | 0.0000 | 0.0000 | 89 | 626045 | 31 | 0 | [6 empty] | 0.0000
101 | 626057 | F -606 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 100 | 626056 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
102 | 626058 | F - Flat No 607 | NA | 0.0000 | 0.0000 | 89 | 626045 | 31 | 0 | [6 empty] | 0.0000
103 | 626059 | F -607 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 102 | 626058 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
104 | 626060 | F - Flat No 608 | NA | 0.0000 | 0.0000 | 89 | 626045 | 31 | 0 | [6 empty] | 0.0000
105 | 626061 | F -608 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 104 | 626060 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
106 | 626062 | F - Flat No 609 | NA | 0.0000 | 0.0000 | 89 | 626045 | 31 | 0 | [6 empty] | 0.0000
107 | 626063 | F -609 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 106 | 626062 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
108 | 626064 | F - Flat No 610 | NA | 0.0000 | 0.0000 | 89 | 626045 | 31 | 0 | [6 empty] | 0.0000
109 | 626065 | F -610 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 108 | 626064 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
110 | 626066 | F - Flat No 611 | NA | 0.0000 | 0.0000 | 89 | 626045 | 31 | 0 | [6 empty] | 0.0000
111 | 626067 | F -611 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 110 | 626066 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
112 | 626068 | F - Flat No 612 | NA | 0.0000 | 0.0000 | 89 | 626045 | 31 | 0 | [6 empty] | 0.0000
113 | 626069 | F -612 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 112 | 626068 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
114 | 626070 | F - Flat No 613 | NA | 0.0000 | 0.0000 | 89 | 626045 | 31 | 0 | [6 empty] | 0.0000
115 | 626071 | F -613 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 114 | 626070 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
116 | 626072 | F - Flat No 614 | NA | 0.0000 | 0.0000 | 89 | 626045 | 31 | 0 | [6 empty] | 0.0000
117 | 626073 | F -614 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 116 | 626072 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
118 | 626074 | F - 7th Floor | NA | 0.0000 | 0.0000 | 1 | 625957 | 31 | 0 | [6 empty] | 0.0000
119 | 626075 | F - Flat No 701 | NA | 0.0000 | 0.0000 | 118 | 626074 | 31 | 0 | [6 empty] | 0.0000
120 | 626076 | F -701 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 119 | 626075 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
121 | 626077 | F - Flat No 702 | NA | 0.0000 | 0.0000 | 118 | 626074 | 31 | 0 | [6 empty] | 0.0000
122 | 626078 | F -702 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 121 | 626077 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
123 | 626079 | F - Flat No 703 | NA | 0.0000 | 0.0000 | 118 | 626074 | 31 | 0 | [6 empty] | 0.0000
124 | 626080 | F -703 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 123 | 626079 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
125 | 626081 | F - Flat No 704 | NA | 0.0000 | 0.0000 | 118 | 626074 | 31 | 0 | [6 empty] | 0.0000
126 | 626082 | F -704 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 125 | 626081 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
127 | 626083 | F - Flat No 705 | NA | 0.0000 | 0.0000 | 118 | 626074 | 31 | 0 | [6 empty] | 0.0000
128 | 626084 | F -705 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 127 | 626083 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
129 | 626085 | F - Flat No 706 | NA | 0.0000 | 0.0000 | 118 | 626074 | 31 | 0 | [6 empty] | 0.0000
130 | 626086 | F -706 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 129 | 626085 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
131 | 626087 | F - Flat No 707 | NA | 0.0000 | 0.0000 | 118 | 626074 | 31 | 0 | [6 empty] | 0.0000
132 | 626088 | F -707 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 131 | 626087 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
133 | 626089 | F - Flat No 708 | NA | 0.0000 | 0.0000 | 118 | 626074 | 31 | 0 | [6 empty] | 0.0000
134 | 626090 | F -708 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 133 | 626089 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
135 | 626091 | F - Flat No 709 | NA | 0.0000 | 0.0000 | 118 | 626074 | 31 | 0 | [6 empty] | 0.0000
136 | 626092 | F -709 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 135 | 626091 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
137 | 626093 | F - Flat No 710 | NA | 0.0000 | 0.0000 | 118 | 626074 | 31 | 0 | [6 empty] | 0.0000
138 | 626094 | F -710 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 137 | 626093 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
139 | 626095 | F - Flat No 711 | NA | 0.0000 | 0.0000 | 118 | 626074 | 31 | 0 | [6 empty] | 0.0000
140 | 626096 | F -711 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 139 | 626095 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
141 | 626097 | F - Flat No 712 | NA | 0.0000 | 0.0000 | 118 | 626074 | 31 | 0 | [6 empty] | 0.0000
142 | 626098 | F -712 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 141 | 626097 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
143 | 626099 | F - Flat No 713 | NA | 0.0000 | 0.0000 | 118 | 626074 | 31 | 0 | [6 empty] | 0.0000
144 | 626100 | F -713 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 143 | 626099 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
145 | 626101 | F - Flat No 714 | NA | 0.0000 | 0.0000 | 118 | 626074 | 31 | 0 | [6 empty] | 0.0000
146 | 626102 | F -714 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 145 | 626101 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
147 | 626103 | F - 8th Floor | NA | 0.0000 | 0.0000 | 1 | 625957 | 31 | 0 | [6 empty] | 0.0000
148 | 626104 | F - Flat No 801 | NA | 0.0000 | 0.0000 | 147 | 626103 | 31 | 0 | [6 empty] | 0.0000
149 | 626105 | F -801 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 148 | 626104 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
150 | 626106 | F - Flat No 802 | NA | 0.0000 | 0.0000 | 147 | 626103 | 31 | 0 | [6 empty] | 0.0000
151 | 626107 | F -802 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 150 | 626106 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
152 | 626108 | F - Flat No 803 | NA | 0.0000 | 0.0000 | 147 | 626103 | 31 | 0 | [6 empty] | 0.0000
153 | 626109 | F -803 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 152 | 626108 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
154 | 626110 | F - Flat No 804 | NA | 0.0000 | 0.0000 | 147 | 626103 | 31 | 0 | [6 empty] | 0.0000
155 | 626111 | F -804 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 154 | 626110 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
156 | 626112 | F - Flat No 805 | NA | 0.0000 | 0.0000 | 147 | 626103 | 31 | 0 | [6 empty] | 0.0000
157 | 626113 | F -805 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 156 | 626112 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
158 | 626114 | F - Flat No 806 | NA | 0.0000 | 0.0000 | 147 | 626103 | 31 | 0 | [6 empty] | 0.0000
159 | 626115 | F -806 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 158 | 626114 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
160 | 626116 | F - Flat No 807 | NA | 0.0000 | 0.0000 | 147 | 626103 | 31 | 0 | [6 empty] | 0.0000
161 | 626117 | F -807 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 160 | 626116 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
162 | 626118 | F - Flat No 808 | NA | 0.0000 | 0.0000 | 147 | 626103 | 31 | 0 | [6 empty] | 0.0000
163 | 626119 | F -808 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 162 | 626118 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
164 | 626120 | F - Flat No 809 | NA | 0.0000 | 0.0000 | 147 | 626103 | 31 | 0 | [6 empty] | 0.0000
165 | 626121 | F -809 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 164 | 626120 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
166 | 626122 | F - Flat No 810 | NA | 0.0000 | 0.0000 | 147 | 626103 | 31 | 0 | [6 empty] | 0.0000
167 | 626123 | F -810 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 166 | 626122 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
168 | 626124 | F - Flat No 811 | NA | 0.0000 | 0.0000 | 147 | 626103 | 31 | 0 | [6 empty] | 0.0000
169 | 626125 | F -811 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 168 | 626124 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
170 | 626126 | F - Flat No 812 | NA | 0.0000 | 0.0000 | 147 | 626103 | 31 | 0 | [6 empty] | 0.0000
171 | 626127 | F -812 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 170 | 626126 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
172 | 626128 | F - Flat No 813 | NA | 0.0000 | 0.0000 | 147 | 626103 | 31 | 0 | [6 empty] | 0.0000
173 | 626129 | F -813 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 172 | 626128 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
174 | 626130 | F - Flat No 814 | NA | 0.0000 | 0.0000 | 147 | 626103 | 31 | 0 | [6 empty] | 0.0000
175 | 626131 | F -814 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 174 | 626130 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
176 | 626132 | F - 9th Floor | NA | 0.0000 | 0.0000 | 1 | 625957 | 31 | 0 | [6 empty] | 0.0000
177 | 626133 | F - Flat No 901 | NA | 0.0000 | 0.0000 | 176 | 626132 | 31 | 0 | [6 empty] | 0.0000
178 | 626134 | F -901 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 177 | 626133 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
179 | 626135 | F - Flat No 902 | NA | 0.0000 | 0.0000 | 176 | 626132 | 31 | 0 | [6 empty] | 0.0000
180 | 626136 | F -902 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 179 | 626135 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
181 | 626137 | F - Flat No 903 | NA | 0.0000 | 0.0000 | 176 | 626132 | 31 | 0 | [6 empty] | 0.0000
182 | 626138 | F -903 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 181 | 626137 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
183 | 626139 | F - Flat No 904 | NA | 0.0000 | 0.0000 | 176 | 626132 | 31 | 0 | [6 empty] | 0.0000
184 | 626140 | F -904 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 183 | 626139 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
185 | 626141 | F - Flat No 905 | NA | 0.0000 | 0.0000 | 176 | 626132 | 31 | 0 | [6 empty] | 0.0000
186 | 626142 | F -905 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 185 | 626141 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
187 | 626143 | F - Flat No 906 | NA | 0.0000 | 0.0000 | 176 | 626132 | 31 | 0 | [6 empty] | 0.0000
188 | 626144 | F -906 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 187 | 626143 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
189 | 626145 | F - Flat No 907 | NA | 0.0000 | 0.0000 | 176 | 626132 | 31 | 0 | [6 empty] | 0.0000
190 | 626146 | F -907 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 189 | 626145 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
191 | 626147 | F - Flat No 908 | NA | 0.0000 | 0.0000 | 176 | 626132 | 31 | 0 | [6 empty] | 0.0000
192 | 626148 | F -908 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 191 | 626147 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
193 | 626149 | F - Flat No 909 | NA | 0.0000 | 0.0000 | 176 | 626132 | 31 | 0 | [6 empty] | 0.0000
194 | 626150 | F -909 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 193 | 626149 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
195 | 626151 | F - Flat No 910 | NA | 0.0000 | 0.0000 | 176 | 626132 | 31 | 0 | [6 empty] | 0.0000
196 | 626152 | F -910 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 195 | 626151 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
197 | 626153 | F - Flat No 911 | NA | 0.0000 | 0.0000 | 176 | 626132 | 31 | 0 | [6 empty] | 0.0000
198 | 626154 | F -911 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 197 | 626153 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
199 | 626155 | F - Flat No 912 | NA | 0.0000 | 0.0000 | 176 | 626132 | 31 | 0 | [6 empty] | 0.0000
200 | 626156 | F -912 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 199 | 626155 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
201 | 626157 | F - Flat No 913 | NA | 0.0000 | 0.0000 | 176 | 626132 | 31 | 0 | [6 empty] | 0.0000
202 | 626158 | F -913 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 201 | 626157 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
203 | 626159 | F - Flat No 914 | NA | 0.0000 | 0.0000 | 176 | 626132 | 31 | 0 | [6 empty] | 0.0000
204 | 626160 | F -914 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 203 | 626159 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
205 | 626161 | F - 10th Floor | NA | 0.0000 | 0.0000 | 1 | 625957 | 31 | 0 | [6 empty] | 0.0000
206 | 626162 | F - Flat No 1001 | NA | 0.0000 | 0.0000 | 205 | 626161 | 31 | 0 | [6 empty] | 0.0000
207 | 626163 | F -1001 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 206 | 626162 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
208 | 626164 | F - Flat No 1002 | NA | 0.0000 | 0.0000 | 205 | 626161 | 31 | 0 | [6 empty] | 0.0000
209 | 626165 | F -1002 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 208 | 626164 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
210 | 626166 | F - Flat No 1003 | NA | 0.0000 | 0.0000 | 205 | 626161 | 31 | 0 | [6 empty] | 0.0000
211 | 626167 | F -1003 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 210 | 626166 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
212 | 626168 | F - Flat No 1004 | NA | 0.0000 | 0.0000 | 205 | 626161 | 31 | 0 | [6 empty] | 0.0000
213 | 626169 | F -1004 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 212 | 626168 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
214 | 626170 | F - Flat No 1005 | NA | 0.0000 | 0.0000 | 205 | 626161 | 31 | 0 | [6 empty] | 0.0000
215 | 626171 | F -1005 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 214 | 626170 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
216 | 626172 | F - Flat No 1006 | NA | 0.0000 | 0.0000 | 205 | 626161 | 31 | 0 | [6 empty] | 0.0000
217 | 626173 | F -1006 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 216 | 626172 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
218 | 626174 | F - Flat No 1007 | NA | 0.0000 | 0.0000 | 205 | 626161 | 31 | 0 | [6 empty] | 0.0000
219 | 626175 | F -1007 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 218 | 626174 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
220 | 626176 | F - Flat No 1008 | NA | 0.0000 | 0.0000 | 205 | 626161 | 31 | 0 | [6 empty] | 0.0000
221 | 626177 | F -1008 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 220 | 626176 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
222 | 626178 | F - Flat No 1009 | NA | 0.0000 | 0.0000 | 205 | 626161 | 31 | 0 | [6 empty] | 0.0000
223 | 626179 | F -1009 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 222 | 626178 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
224 | 626180 | F - Flat No 1010 | NA | 0.0000 | 0.0000 | 205 | 626161 | 31 | 0 | [6 empty] | 0.0000
225 | 626181 | F -1010 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 224 | 626180 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
226 | 626182 | F - Flat No 1011 | NA | 0.0000 | 0.0000 | 205 | 626161 | 31 | 0 | [6 empty] | 0.0000
227 | 626183 | F -1011 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 226 | 626182 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
228 | 626184 | F - Flat No 1012 | NA | 0.0000 | 0.0000 | 205 | 626161 | 31 | 0 | [6 empty] | 0.0000
229 | 626185 | F -1012 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 228 | 626184 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
230 | 626186 | F - Flat No 1013 | NA | 0.0000 | 0.0000 | 205 | 626161 | 31 | 0 | [6 empty] | 0.0000
231 | 626187 | F -1013 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 230 | 626186 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
232 | 626188 | F - Flat No 1014 | NA | 0.0000 | 0.0000 | 205 | 626161 | 31 | 0 | [6 empty] | 0.0000
233 | 626189 | F -1014 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 232 | 626188 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
234 | 626190 | F - 11th Floor | NA | 0.0000 | 0.0000 | 1 | 625957 | 31 | 0 | [6 empty] | 0.0000
235 | 626191 | F - Flat No 1101 | NA | 0.0000 | 0.0000 | 234 | 626190 | 31 | 0 | [6 empty] | 0.0000
236 | 626192 | F -1101 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 235 | 626191 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
237 | 626193 | F - Flat No 1102 | NA | 0.0000 | 0.0000 | 234 | 626190 | 31 | 0 | [6 empty] | 0.0000
238 | 626194 | F -1102 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 237 | 626193 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
239 | 626195 | F - Flat No 1103 | NA | 0.0000 | 0.0000 | 234 | 626190 | 31 | 0 | [6 empty] | 0.0000
240 | 626196 | F -1103 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 239 | 626195 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
241 | 626197 | F - Flat No 1104 | NA | 0.0000 | 0.0000 | 234 | 626190 | 31 | 0 | [6 empty] | 0.0000
242 | 626198 | F -1104 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 241 | 626197 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
243 | 626199 | F - Flat No 1105 | NA | 0.0000 | 0.0000 | 234 | 626190 | 31 | 0 | [6 empty] | 0.0000
244 | 626200 | F -1105 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 243 | 626199 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
245 | 626201 | F - Flat No 1106 | NA | 0.0000 | 0.0000 | 234 | 626190 | 31 | 0 | [6 empty] | 0.0000
246 | 626202 | F -1106 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 245 | 626201 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
247 | 626203 | F - Flat No 1107 | NA | 0.0000 | 0.0000 | 234 | 626190 | 31 | 0 | [6 empty] | 0.0000
248 | 626204 | F -1107 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 247 | 626203 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
249 | 626205 | F - Flat No 1108 | NA | 0.0000 | 0.0000 | 234 | 626190 | 31 | 0 | [6 empty] | 0.0000
250 | 626206 | F -1108 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 249 | 626205 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
251 | 626207 | F - Flat No 1109 | NA | 0.0000 | 0.0000 | 234 | 626190 | 31 | 0 | [6 empty] | 0.0000
252 | 626208 | F -1109 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 251 | 626207 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
253 | 626209 | F - Flat No 1110 | NA | 0.0000 | 0.0000 | 234 | 626190 | 31 | 0 | [6 empty] | 0.0000
254 | 626210 | F -1110 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 253 | 626209 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
255 | 626211 | F - Flat No 1111 | NA | 0.0000 | 0.0000 | 234 | 626190 | 31 | 0 | [6 empty] | 0.0000
256 | 626212 | F -1111 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 255 | 626211 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
257 | 626213 | F - Flat No 1112 | NA | 0.0000 | 0.0000 | 234 | 626190 | 31 | 0 | [6 empty] | 0.0000
258 | 626214 | F -1112 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 257 | 626213 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
259 | 626215 | F - Flat No 1113 | NA | 0.0000 | 0.0000 | 234 | 626190 | 31 | 0 | [6 empty] | 0.0000
260 | 626216 | F -1113 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 259 | 626215 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
261 | 626217 | F - Flat No 1114 | NA | 0.0000 | 0.0000 | 234 | 626190 | 31 | 0 | [6 empty] | 0.0000
262 | 626218 | F -1114 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 261 | 626217 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
263 | 626219 | F - 12th Floor | NA | 0.0000 | 0.0000 | 1 | 625957 | 31 | 0 | [6 empty] | 0.0000
264 | 626220 | F - Flat No 1201 | NA | 0.0000 | 0.0000 | 263 | 626219 | 31 | 0 | [6 empty] | 0.0000
265 | 626221 | F -1201 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 264 | 626220 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
266 | 626222 | F - Flat No 1202 | NA | 0.0000 | 0.0000 | 263 | 626219 | 31 | 0 | [6 empty] | 0.0000
267 | 626223 | F -1202 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 266 | 626222 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
268 | 626224 | F - Flat No 1203 | NA | 0.0000 | 0.0000 | 263 | 626219 | 31 | 0 | [6 empty] | 0.0000
269 | 626225 | F -1203 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 268 | 626224 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
270 | 626226 | F - Flat No 1204 | NA | 0.0000 | 0.0000 | 263 | 626219 | 31 | 0 | [6 empty] | 0.0000
271 | 626227 | F -1204 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 270 | 626226 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
272 | 626228 | F - Flat No 1205 | NA | 0.0000 | 0.0000 | 263 | 626219 | 31 | 0 | [6 empty] | 0.0000
273 | 626229 | F -1205 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 272 | 626228 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
274 | 626230 | F - Flat No 1206 | NA | 0.0000 | 0.0000 | 263 | 626219 | 31 | 0 | [6 empty] | 0.0000
275 | 626231 | F -1206 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 274 | 626230 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
276 | 626232 | F - Flat No 1207 | NA | 0.0000 | 0.0000 | 263 | 626219 | 31 | 0 | [6 empty] | 0.0000
277 | 626233 | F -1207 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 276 | 626232 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
278 | 626234 | F - Flat No 1208 | NA | 0.0000 | 0.0000 | 263 | 626219 | 31 | 0 | [6 empty] | 0.0000
279 | 626235 | F -1208 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 278 | 626234 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
280 | 626236 | F - Flat No 1209 | NA | 0.0000 | 0.0000 | 263 | 626219 | 31 | 0 | [6 empty] | 0.0000
281 | 626237 | F -1209 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 280 | 626236 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
282 | 626238 | F - Flat No 1210 | NA | 0.0000 | 0.0000 | 263 | 626219 | 31 | 0 | [6 empty] | 0.0000
283 | 626239 | F -1210 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 282 | 626238 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
284 | 626240 | F - Flat No 1211 | NA | 0.0000 | 0.0000 | 263 | 626219 | 31 | 0 | [6 empty] | 0.0000
285 | 626241 | F -1211 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 284 | 626240 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
286 | 626242 | F - Flat No 1212 | NA | 0.0000 | 0.0000 | 263 | 626219 | 31 | 0 | [6 empty] | 0.0000
287 | 626243 | F -1212 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 286 | 626242 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
288 | 626244 | F - Flat No 1213 | NA | 0.0000 | 0.0000 | 263 | 626219 | 31 | 0 | [6 empty] | 0.0000
289 | 626245 | F -1213 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 288 | 626244 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
290 | 626246 | F - Flat No 1214 | NA | 0.0000 | 0.0000 | 263 | 626219 | 31 | 0 | [6 empty] | 0.0000
291 | 626247 | F -1214 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 290 | 626246 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
292 | 626248 | F - 13th Floor | NA | 0.0000 | 0.0000 | 1 | 625957 | 31 | 0 | [6 empty] | 0.0000
293 | 626249 | F - Flat No 1301 | NA | 0.0000 | 0.0000 | 292 | 626248 | 31 | 0 | [6 empty] | 0.0000
294 | 626250 | F -1301 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 293 | 626249 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
295 | 626251 | F - Flat No 1302 | NA | 0.0000 | 0.0000 | 292 | 626248 | 31 | 0 | [6 empty] | 0.0000
296 | 626252 | F -1302 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 295 | 626251 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
297 | 626253 | F - Flat No 1303 | NA | 0.0000 | 0.0000 | 292 | 626248 | 31 | 0 | [6 empty] | 0.0000
298 | 626254 | F -1303 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 297 | 626253 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
299 | 626255 | F - Flat No 1304 | NA | 0.0000 | 0.0000 | 292 | 626248 | 31 | 0 | [6 empty] | 0.0000
300 | 626256 | F -1304 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 299 | 626255 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
301 | 626257 | F - Flat No 1305 | NA | 0.0000 | 0.0000 | 292 | 626248 | 31 | 0 | [6 empty] | 0.0000
302 | 626258 | F -1305 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 301 | 626257 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
303 | 626259 | F - Flat No 1306 | NA | 0.0000 | 0.0000 | 292 | 626248 | 31 | 0 | [6 empty] | 0.0000
304 | 626260 | F -1306 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 303 | 626259 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
305 | 626261 | F - Flat No 1307 | NA | 0.0000 | 0.0000 | 292 | 626248 | 31 | 0 | [6 empty] | 0.0000
306 | 626262 | F -1307 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 305 | 626261 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
307 | 626263 | F - Flat No 1308 | NA | 0.0000 | 0.0000 | 292 | 626248 | 31 | 0 | [6 empty] | 0.0000
308 | 626264 | F -1308 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 307 | 626263 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
309 | 626265 | F - Flat No 1309 | NA | 0.0000 | 0.0000 | 292 | 626248 | 31 | 0 | [6 empty] | 0.0000
310 | 626266 | F -1309 Umra Patti Work | R.Ft | 0.0000 | 0.0000 | 309 | 626265 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
311 | 626267 | F - Flat No 1310 | NA | 0.0000 | 0.0000 | 292 | 626248 | 31 | 0 | [6 empty] | 0.0000
312 | 626268 | F -1310 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 311 | 626267 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
313 | 626269 | F - Flat No 1311 | NA | 0.0000 | 0.0000 | 292 | 626248 | 31 | 0 | [6 empty] | 0.0000
314 | 626270 | F -1311 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 313 | 626269 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
315 | 626271 | F - Flat No 1312 | NA | 0.0000 | 0.0000 | 292 | 626248 | 31 | 0 | [6 empty] | 0.0000
316 | 626272 | F -1312 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 315 | 626271 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
317 | 626273 | F - Flat No 1313 | NA | 0.0000 | 0.0000 | 292 | 626248 | 31 | 0 | [6 empty] | 0.0000
318 | 626274 | F -1313 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 317 | 626273 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
319 | 626275 | F - Flat No 1314 | NA | 0.0000 | 0.0000 | 292 | 626248 | 31 | 0 | [6 empty] | 0.0000
320 | 626276 | F -1314 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 319 | 626275 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
321 | 626277 | F - 14th Floor | NA | 0.0000 | 0.0000 | 1 | 625957 | 31 | 0 | [6 empty] | 0.0000
322 | 626278 | F - Flat No 1401 | NA | 0.0000 | 0.0000 | 321 | 626277 | 31 | 0 | [6 empty] | 0.0000
323 | 626279 | F -1401 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 322 | 626278 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
324 | 626280 | F - Flat No 1402 | NA | 0.0000 | 0.0000 | 321 | 626277 | 31 | 0 | [6 empty] | 0.0000
325 | 626281 | F -1402 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 324 | 626280 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
326 | 626282 | F - Flat No 1403 | NA | 0.0000 | 0.0000 | 321 | 626277 | 31 | 0 | [6 empty] | 0.0000
327 | 626283 | F -1403 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 326 | 626282 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
328 | 626284 | F - Flat No 1404 | NA | 0.0000 | 0.0000 | 321 | 626277 | 31 | 0 | [6 empty] | 0.0000
329 | 626285 | F -1404 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 328 | 626284 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
330 | 626286 | F - Flat No 1405 | NA | 0.0000 | 0.0000 | 321 | 626277 | 31 | 0 | [6 empty] | 0.0000
331 | 626287 | F -1405 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 330 | 626286 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
332 | 626288 | F - Flat No 1406 | NA | 0.0000 | 0.0000 | 321 | 626277 | 31 | 0 | [6 empty] | 0.0000
333 | 626289 | F -1406 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 332 | 626288 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
334 | 626290 | F - Flat No 1407 | NA | 0.0000 | 0.0000 | 321 | 626277 | 31 | 0 | [6 empty] | 0.0000
335 | 626291 | F -1407 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 334 | 626290 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
336 | 626292 | F - Flat No 1408 | NA | 0.0000 | 0.0000 | 321 | 626277 | 31 | 0 | [6 empty] | 0.0000
337 | 626293 | F -1408 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 336 | 626292 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
338 | 626294 | F - Flat No 1409 | NA | 0.0000 | 0.0000 | 321 | 626277 | 31 | 0 | [6 empty] | 0.0000
339 | 626295 | F -1409 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 338 | 626294 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
340 | 626296 | F - Flat No 1410 | NA | 0.0000 | 0.0000 | 321 | 626277 | 31 | 0 | [6 empty] | 0.0000
341 | 626297 | F -1410 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 340 | 626296 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
342 | 626298 | F - Flat No 1411 | NA | 0.0000 | 0.0000 | 321 | 626277 | 31 | 0 | [6 empty] | 0.0000
343 | 626299 | F -1411 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 342 | 626298 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
344 | 626300 | F - Flat No 1412 | NA | 0.0000 | 0.0000 | 321 | 626277 | 31 | 0 | [6 empty] | 0.0000
345 | 626301 | F -1412 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 344 | 626300 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
346 | 626302 | F - Flat No 1413 | NA | 0.0000 | 0.0000 | 321 | 626277 | 31 | 0 | [6 empty] | 0.0000
347 | 626303 | F -1413 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 346 | 626302 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000
348 | 626304 | F - Flat No 1414 | NA | 0.0000 | 0.0000 | 321 | 626277 | 31 | 0 | [6 empty] | 0.0000
349 | 626305 | F -1414 Umra Patti Work | R.Ft | 12.1400 | 12.1400 | 348 | 626304 | 4 | 30706 | A-301 Umra Patti Work | [5 empty] | 0.0000