## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta | Selected Group :- C - Kitchen Otta
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 626655 | F - Kitchen Otta | NA | 0.0000 | 0.0000 | 0 | 605104 | 31 | 0 | [6 empty] | 0.0000
2 | 626656 | F - 3rd Floor | NA | 0.0000 | 0.0000 | 1 | 626655 | 31 | 0 | [6 empty] | 0.0000
3 | 626657 | F - Flat No 301 | NA | 0.0000 | 0.0000 | 2 | 626656 | 31 | 0 | [6 empty] | 0.0000
4 | 626658 | F -301 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 3 | 626657 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
5 | 626659 | F - Flat No 302 | NA | 0.0000 | 0.0000 | 2 | 626656 | 31 | 0 | [6 empty] | 0.0000
6 | 626660 | F -302 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 5 | 626659 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
7 | 626661 | F - Flat No 303 | NA | 0.0000 | 0.0000 | 2 | 626656 | 31 | 0 | [6 empty] | 0.0000
8 | 626662 | F -303 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 7 | 626661 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
9 | 626663 | F - Flat No 304 | NA | 0.0000 | 0.0000 | 2 | 626656 | 31 | 0 | [6 empty] | 0.0000
10 | 626664 | F -304 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 9 | 626663 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
11 | 626665 | F - Flat No 305 | NA | 0.0000 | 0.0000 | 2 | 626656 | 31 | 0 | [6 empty] | 0.0000
12 | 626666 | F -305 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 11 | 626665 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
13 | 626667 | F - Flat No 306 | NA | 0.0000 | 0.0000 | 2 | 626656 | 31 | 0 | [6 empty] | 0.0000
14 | 626668 | F -306 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 13 | 626667 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
15 | 626669 | F - Flat No 307 | NA | 0.0000 | 0.0000 | 2 | 626656 | 31 | 0 | [6 empty] | 0.0000
16 | 626670 | F -307 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 15 | 626669 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
17 | 626671 | F - Flat No 308 | NA | 0.0000 | 0.0000 | 2 | 626656 | 31 | 0 | [6 empty] | 0.0000
18 | 626672 | F -308 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 17 | 626671 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
19 | 626673 | F - Flat No 309 | NA | 0.0000 | 0.0000 | 2 | 626656 | 31 | 0 | [6 empty] | 0.0000
20 | 626674 | F -309 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 19 | 626673 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
21 | 626675 | F - Flat No 310 | NA | 0.0000 | 0.0000 | 2 | 626656 | 31 | 0 | [6 empty] | 0.0000
22 | 626676 | F -310 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 21 | 626675 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
23 | 626677 | F - Flat No 311 | NA | 0.0000 | 0.0000 | 2 | 626656 | 31 | 0 | [6 empty] | 0.0000
24 | 626678 | F -311 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 23 | 626677 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
25 | 626679 | F - Flat No 312 | NA | 0.0000 | 0.0000 | 2 | 626656 | 31 | 0 | [6 empty] | 0.0000
26 | 626680 | F -312 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 25 | 626679 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
27 | 626681 | F - Flat No 313 | NA | 0.0000 | 0.0000 | 2 | 626656 | 31 | 0 | [6 empty] | 0.0000
28 | 626682 | F -313 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 27 | 626681 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
29 | 626683 | F - Flat No 314 | NA | 0.0000 | 0.0000 | 2 | 626656 | 31 | 0 | [6 empty] | 0.0000
30 | 626684 | F -314 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 29 | 626683 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
31 | 626685 | F - 4th Floor | NA | 0.0000 | 0.0000 | 1 | 626655 | 31 | 0 | [6 empty] | 0.0000
32 | 626686 | F - Flat No 401 | NA | 0.0000 | 0.0000 | 31 | 626685 | 31 | 0 | [6 empty] | 0.0000
33 | 626687 | F -401 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 32 | 626686 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
34 | 626688 | F - Flat No 402 | NA | 0.0000 | 0.0000 | 31 | 626685 | 31 | 0 | [6 empty] | 0.0000
35 | 626689 | F -402 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 34 | 626688 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
36 | 626690 | F - Flat No 403 | NA | 0.0000 | 0.0000 | 31 | 626685 | 31 | 0 | [6 empty] | 0.0000
37 | 626691 | F -403 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 36 | 626690 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
38 | 626692 | F - Flat No 404 | NA | 0.0000 | 0.0000 | 31 | 626685 | 31 | 0 | [6 empty] | 0.0000
39 | 626693 | F -404 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 38 | 626692 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
40 | 626694 | F - Flat No 405 | NA | 0.0000 | 0.0000 | 31 | 626685 | 31 | 0 | [6 empty] | 0.0000
41 | 626695 | F -405 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 40 | 626694 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
42 | 626696 | F - Flat No 406 | NA | 0.0000 | 0.0000 | 31 | 626685 | 31 | 0 | [6 empty] | 0.0000
43 | 626697 | F -406 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 42 | 626696 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
44 | 626698 | F - Flat No 407 | NA | 0.0000 | 0.0000 | 31 | 626685 | 31 | 0 | [6 empty] | 0.0000
45 | 626699 | F -407 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 44 | 626698 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
46 | 626700 | F - Flat No 408 | NA | 0.0000 | 0.0000 | 31 | 626685 | 31 | 0 | [6 empty] | 0.0000
47 | 626701 | F -408 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 46 | 626700 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
48 | 626702 | F - Flat No 409 | NA | 0.0000 | 0.0000 | 31 | 626685 | 31 | 0 | [6 empty] | 0.0000
49 | 626703 | F -409 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 48 | 626702 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
50 | 626704 | F - Flat No 410 | NA | 0.0000 | 0.0000 | 31 | 626685 | 31 | 0 | [6 empty] | 0.0000
51 | 626705 | F -410 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 50 | 626704 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
52 | 626706 | F - Flat No 411 | NA | 0.0000 | 0.0000 | 31 | 626685 | 31 | 0 | [6 empty] | 0.0000
53 | 626707 | F -411 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 52 | 626706 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
54 | 626708 | F - Flat No 412 | NA | 0.0000 | 0.0000 | 31 | 626685 | 31 | 0 | [6 empty] | 0.0000
55 | 626709 | F -412 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 54 | 626708 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
56 | 626710 | F - Flat No 413 | NA | 0.0000 | 0.0000 | 31 | 626685 | 31 | 0 | [6 empty] | 0.0000
57 | 626711 | F -413 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 56 | 626710 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
58 | 626712 | F - Flat No 414 | NA | 0.0000 | 0.0000 | 31 | 626685 | 31 | 0 | [6 empty] | 0.0000
59 | 626713 | F -414 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 58 | 626712 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
60 | 626714 | F - 5th Floor | NA | 0.0000 | 0.0000 | 1 | 626655 | 31 | 0 | [6 empty] | 0.0000
61 | 626715 | F - Flat No 501 | NA | 0.0000 | 0.0000 | 60 | 626714 | 31 | 0 | [6 empty] | 0.0000
62 | 626716 | F -501 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 61 | 626715 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
63 | 626717 | F - Flat No 502 | NA | 0.0000 | 0.0000 | 60 | 626714 | 31 | 0 | [6 empty] | 0.0000
64 | 626718 | F -502 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 63 | 626717 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
65 | 626719 | F - Flat No 503 | NA | 0.0000 | 0.0000 | 60 | 626714 | 31 | 0 | [6 empty] | 0.0000
66 | 626720 | F -503 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 65 | 626719 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
67 | 626721 | F - Flat No 504 | NA | 0.0000 | 0.0000 | 60 | 626714 | 31 | 0 | [6 empty] | 0.0000
68 | 626722 | F -504 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 67 | 626721 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
69 | 626723 | F - Flat No 505 | NA | 0.0000 | 0.0000 | 60 | 626714 | 31 | 0 | [6 empty] | 0.0000
70 | 626724 | F -505 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 69 | 626723 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
71 | 626725 | F - Flat No 506 | NA | 0.0000 | 0.0000 | 60 | 626714 | 31 | 0 | [6 empty] | 0.0000
72 | 626726 | F -506 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 71 | 626725 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
73 | 626727 | F - Flat No 507 | NA | 0.0000 | 0.0000 | 60 | 626714 | 31 | 0 | [6 empty] | 0.0000
74 | 626728 | F -507 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 73 | 626727 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
75 | 626729 | F - Flat No 508 | NA | 0.0000 | 0.0000 | 60 | 626714 | 31 | 0 | [6 empty] | 0.0000
76 | 626730 | F -508 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 75 | 626729 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
77 | 626731 | F - Flat No 509 | NA | 0.0000 | 0.0000 | 60 | 626714 | 31 | 0 | [6 empty] | 0.0000
78 | 626732 | F -509 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 77 | 626731 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
79 | 626733 | F - Flat No 510 | NA | 0.0000 | 0.0000 | 60 | 626714 | 31 | 0 | [6 empty] | 0.0000
80 | 626734 | F -510 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 79 | 626733 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
81 | 626735 | F - Flat No 511 | NA | 0.0000 | 0.0000 | 60 | 626714 | 31 | 0 | [6 empty] | 0.0000
82 | 626736 | F -511 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 81 | 626735 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
83 | 626737 | F - Flat No 512 | NA | 0.0000 | 0.0000 | 60 | 626714 | 31 | 0 | [6 empty] | 0.0000
84 | 626738 | F -512 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 83 | 626737 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
85 | 626739 | F - Flat No 513 | NA | 0.0000 | 0.0000 | 60 | 626714 | 31 | 0 | [6 empty] | 0.0000
86 | 626740 | F -513 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 85 | 626739 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
87 | 626741 | F - Flat No 514 | NA | 0.0000 | 0.0000 | 60 | 626714 | 31 | 0 | [6 empty] | 0.0000
88 | 626742 | F -514 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 87 | 626741 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
89 | 626743 | F - 6th Floor | NA | 0.0000 | 0.0000 | 1 | 626655 | 31 | 0 | [6 empty] | 0.0000
90 | 626744 | F - Flat No 601 | NA | 0.0000 | 0.0000 | 89 | 626743 | 31 | 0 | [6 empty] | 0.0000
91 | 626745 | F -601 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 90 | 626744 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
92 | 626746 | F - Flat No 602 | NA | 0.0000 | 0.0000 | 89 | 626743 | 31 | 0 | [6 empty] | 0.0000
93 | 626747 | F -602 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 92 | 626746 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
94 | 626748 | F - Flat No 603 | NA | 0.0000 | 0.0000 | 89 | 626743 | 31 | 0 | [6 empty] | 0.0000
95 | 626749 | F -603 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 94 | 626748 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
96 | 626750 | F - Flat No 604 | NA | 0.0000 | 0.0000 | 89 | 626743 | 31 | 0 | [6 empty] | 0.0000
97 | 626751 | F -604 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 96 | 626750 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
98 | 626752 | F - Flat No 605 | NA | 0.0000 | 0.0000 | 89 | 626743 | 31 | 0 | [6 empty] | 0.0000
99 | 626753 | F -605 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 98 | 626752 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
100 | 626754 | F - Flat No 606 | NA | 0.0000 | 0.0000 | 89 | 626743 | 31 | 0 | [6 empty] | 0.0000
101 | 626755 | F -606 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 100 | 626754 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
102 | 626756 | F - Flat No 607 | NA | 0.0000 | 0.0000 | 89 | 626743 | 31 | 0 | [6 empty] | 0.0000
103 | 626757 | F -607 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 102 | 626756 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
104 | 626758 | F - Flat No 608 | NA | 0.0000 | 0.0000 | 89 | 626743 | 31 | 0 | [6 empty] | 0.0000
105 | 626759 | F -608 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 104 | 626758 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
106 | 626760 | F - Flat No 609 | NA | 0.0000 | 0.0000 | 89 | 626743 | 31 | 0 | [6 empty] | 0.0000
107 | 626761 | F -609 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 106 | 626760 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
108 | 626762 | F - Flat No 610 | NA | 0.0000 | 0.0000 | 89 | 626743 | 31 | 0 | [6 empty] | 0.0000
109 | 626763 | F -610 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 108 | 626762 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
110 | 626764 | F - Flat No 611 | NA | 0.0000 | 0.0000 | 89 | 626743 | 31 | 0 | [6 empty] | 0.0000
111 | 626765 | F -611 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 110 | 626764 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
112 | 626766 | F - Flat No 612 | NA | 0.0000 | 0.0000 | 89 | 626743 | 31 | 0 | [6 empty] | 0.0000
113 | 626767 | F -612 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 112 | 626766 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
114 | 626768 | F - Flat No 613 | NA | 0.0000 | 0.0000 | 89 | 626743 | 31 | 0 | [6 empty] | 0.0000
115 | 626769 | F -613 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 114 | 626768 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
116 | 626770 | F - Flat No 614 | NA | 0.0000 | 0.0000 | 89 | 626743 | 31 | 0 | [6 empty] | 0.0000
117 | 626771 | F -614 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 116 | 626770 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
118 | 626772 | F - 7th Floor | NA | 0.0000 | 0.0000 | 1 | 626655 | 31 | 0 | [6 empty] | 0.0000
119 | 626773 | F - Flat No 701 | NA | 0.0000 | 0.0000 | 118 | 626772 | 31 | 0 | [6 empty] | 0.0000
120 | 626774 | F -701 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 119 | 626773 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
121 | 626775 | F - Flat No 702 | NA | 0.0000 | 0.0000 | 118 | 626772 | 31 | 0 | [6 empty] | 0.0000
122 | 626776 | F -702 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 121 | 626775 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
123 | 626777 | F - Flat No 703 | NA | 0.0000 | 0.0000 | 118 | 626772 | 31 | 0 | [6 empty] | 0.0000
124 | 626778 | F -703 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 123 | 626777 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
125 | 626779 | F - Flat No 704 | NA | 0.0000 | 0.0000 | 118 | 626772 | 31 | 0 | [6 empty] | 0.0000
126 | 626780 | F -704 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 125 | 626779 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
127 | 626781 | F - Flat No 705 | NA | 0.0000 | 0.0000 | 118 | 626772 | 31 | 0 | [6 empty] | 0.0000
128 | 626782 | F -705 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 127 | 626781 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
129 | 626783 | F - Flat No 706 | NA | 0.0000 | 0.0000 | 118 | 626772 | 31 | 0 | [6 empty] | 0.0000
130 | 626784 | F -706 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 129 | 626783 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
131 | 626785 | F - Flat No 707 | NA | 0.0000 | 0.0000 | 118 | 626772 | 31 | 0 | [6 empty] | 0.0000
132 | 626786 | F -707 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 131 | 626785 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
133 | 626787 | F - Flat No 708 | NA | 0.0000 | 0.0000 | 118 | 626772 | 31 | 0 | [6 empty] | 0.0000
134 | 626788 | F -708 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 133 | 626787 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
135 | 626789 | F - Flat No 709 | NA | 0.0000 | 0.0000 | 118 | 626772 | 31 | 0 | [6 empty] | 0.0000
136 | 626790 | F -709 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 135 | 626789 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
137 | 626791 | F - Flat No 710 | NA | 0.0000 | 0.0000 | 118 | 626772 | 31 | 0 | [6 empty] | 0.0000
138 | 626792 | F -710 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 137 | 626791 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
139 | 626793 | F - Flat No 711 | NA | 0.0000 | 0.0000 | 118 | 626772 | 31 | 0 | [6 empty] | 0.0000
140 | 626794 | F -711 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 139 | 626793 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
141 | 626795 | F - Flat No 712 | NA | 0.0000 | 0.0000 | 118 | 626772 | 31 | 0 | [6 empty] | 0.0000
142 | 626796 | F -712 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 141 | 626795 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
143 | 626797 | F - Flat No 713 | NA | 0.0000 | 0.0000 | 118 | 626772 | 31 | 0 | [6 empty] | 0.0000
144 | 626798 | F -713 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 143 | 626797 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
145 | 626799 | F - Flat No 714 | NA | 0.0000 | 0.0000 | 118 | 626772 | 31 | 0 | [6 empty] | 0.0000
146 | 626800 | F -714 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 145 | 626799 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
147 | 626801 | F - 8th Floor | NA | 0.0000 | 0.0000 | 1 | 626655 | 31 | 0 | [6 empty] | 0.0000
148 | 626802 | F - Flat No 801 | NA | 0.0000 | 0.0000 | 147 | 626801 | 31 | 0 | [6 empty] | 0.0000
149 | 626803 | F -801 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 148 | 626802 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
150 | 626804 | F - Flat No 802 | NA | 0.0000 | 0.0000 | 147 | 626801 | 31 | 0 | [6 empty] | 0.0000
151 | 626805 | F -802 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 150 | 626804 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
152 | 626806 | F - Flat No 803 | NA | 0.0000 | 0.0000 | 147 | 626801 | 31 | 0 | [6 empty] | 0.0000
153 | 626807 | F -803 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 152 | 626806 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
154 | 626808 | F - Flat No 804 | NA | 0.0000 | 0.0000 | 147 | 626801 | 31 | 0 | [6 empty] | 0.0000
155 | 626809 | F -804 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 154 | 626808 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
156 | 626810 | F - Flat No 805 | NA | 0.0000 | 0.0000 | 147 | 626801 | 31 | 0 | [6 empty] | 0.0000
157 | 626811 | F -805 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 156 | 626810 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
158 | 626812 | F - Flat No 806 | NA | 0.0000 | 0.0000 | 147 | 626801 | 31 | 0 | [6 empty] | 0.0000
159 | 626813 | F -806 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 158 | 626812 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
160 | 626814 | F - Flat No 807 | NA | 0.0000 | 0.0000 | 147 | 626801 | 31 | 0 | [6 empty] | 0.0000
161 | 626815 | F -807 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 160 | 626814 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
162 | 626816 | F - Flat No 808 | NA | 0.0000 | 0.0000 | 147 | 626801 | 31 | 0 | [6 empty] | 0.0000
163 | 626817 | F -808 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 162 | 626816 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
164 | 626818 | F - Flat No 809 | NA | 0.0000 | 0.0000 | 147 | 626801 | 31 | 0 | [6 empty] | 0.0000
165 | 626819 | F -809 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 164 | 626818 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
166 | 626820 | F - Flat No 810 | NA | 0.0000 | 0.0000 | 147 | 626801 | 31 | 0 | [6 empty] | 0.0000
167 | 626821 | F -810 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 166 | 626820 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
168 | 626822 | F - Flat No 811 | NA | 0.0000 | 0.0000 | 147 | 626801 | 31 | 0 | [6 empty] | 0.0000
169 | 626823 | F -811 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 168 | 626822 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
170 | 626824 | F - Flat No 812 | NA | 0.0000 | 0.0000 | 147 | 626801 | 31 | 0 | [6 empty] | 0.0000
171 | 626825 | F -812 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 170 | 626824 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
172 | 626826 | F - Flat No 813 | NA | 0.0000 | 0.0000 | 147 | 626801 | 31 | 0 | [6 empty] | 0.0000
173 | 626827 | F -813 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 172 | 626826 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
174 | 626828 | F - Flat No 814 | NA | 0.0000 | 0.0000 | 147 | 626801 | 31 | 0 | [6 empty] | 0.0000
175 | 626829 | F -814 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 174 | 626828 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
176 | 626830 | F - 9th Floor | NA | 0.0000 | 0.0000 | 1 | 626655 | 31 | 0 | [6 empty] | 0.0000
177 | 626831 | F - Flat No 901 | NA | 0.0000 | 0.0000 | 176 | 626830 | 31 | 0 | [6 empty] | 0.0000
178 | 626832 | F -901 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 177 | 626831 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
179 | 626833 | F - Flat No 902 | NA | 0.0000 | 0.0000 | 176 | 626830 | 31 | 0 | [6 empty] | 0.0000
180 | 626834 | F -902 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 179 | 626833 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
181 | 626835 | F - Flat No 903 | NA | 0.0000 | 0.0000 | 176 | 626830 | 31 | 0 | [6 empty] | 0.0000
182 | 626836 | F -903 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 181 | 626835 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
183 | 626837 | F - Flat No 904 | NA | 0.0000 | 0.0000 | 176 | 626830 | 31 | 0 | [6 empty] | 0.0000
184 | 626838 | F -904 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 183 | 626837 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
185 | 626839 | F - Flat No 905 | NA | 0.0000 | 0.0000 | 176 | 626830 | 31 | 0 | [6 empty] | 0.0000
186 | 626840 | F -905 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 185 | 626839 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
187 | 626841 | F - Flat No 906 | NA | 0.0000 | 0.0000 | 176 | 626830 | 31 | 0 | [6 empty] | 0.0000
188 | 626842 | F -906 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 187 | 626841 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
189 | 626843 | F - Flat No 907 | NA | 0.0000 | 0.0000 | 176 | 626830 | 31 | 0 | [6 empty] | 0.0000
190 | 626844 | F -907 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 189 | 626843 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
191 | 626845 | F - Flat No 908 | NA | 0.0000 | 0.0000 | 176 | 626830 | 31 | 0 | [6 empty] | 0.0000
192 | 626846 | F -908 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 191 | 626845 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
193 | 626847 | F - Flat No 909 | NA | 0.0000 | 0.0000 | 176 | 626830 | 31 | 0 | [6 empty] | 0.0000
194 | 626848 | F -909 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 193 | 626847 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
195 | 626849 | F - Flat No 910 | NA | 0.0000 | 0.0000 | 176 | 626830 | 31 | 0 | [6 empty] | 0.0000
196 | 626850 | F -910 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 195 | 626849 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
197 | 626851 | F - Flat No 911 | NA | 0.0000 | 0.0000 | 176 | 626830 | 31 | 0 | [6 empty] | 0.0000
198 | 626852 | F -911 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 197 | 626851 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
199 | 626853 | F - Flat No 912 | NA | 0.0000 | 0.0000 | 176 | 626830 | 31 | 0 | [6 empty] | 0.0000
200 | 626854 | F -912 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 199 | 626853 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
201 | 626855 | F - Flat No 913 | NA | 0.0000 | 0.0000 | 176 | 626830 | 31 | 0 | [6 empty] | 0.0000
202 | 626856 | F -913 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 201 | 626855 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
203 | 626857 | F - Flat No 914 | NA | 0.0000 | 0.0000 | 176 | 626830 | 31 | 0 | [6 empty] | 0.0000
204 | 626858 | F -914 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 203 | 626857 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
205 | 626859 | F - 10th Floor | NA | 0.0000 | 0.0000 | 1 | 626655 | 31 | 0 | [6 empty] | 0.0000
206 | 626860 | F - Flat No 1001 | NA | 0.0000 | 0.0000 | 205 | 626859 | 31 | 0 | [6 empty] | 0.0000
207 | 626861 | F -1001 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 206 | 626860 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
208 | 626862 | F - Flat No 1002 | NA | 0.0000 | 0.0000 | 205 | 626859 | 31 | 0 | [6 empty] | 0.0000
209 | 626863 | F -1002 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 208 | 626862 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
210 | 626864 | F - Flat No 1003 | NA | 0.0000 | 0.0000 | 205 | 626859 | 31 | 0 | [6 empty] | 0.0000
211 | 626865 | F -1003 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 210 | 626864 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
212 | 626866 | F - Flat No 1004 | NA | 0.0000 | 0.0000 | 205 | 626859 | 31 | 0 | [6 empty] | 0.0000
213 | 626867 | F -1004 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 212 | 626866 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
214 | 626868 | F - Flat No 1005 | NA | 0.0000 | 0.0000 | 205 | 626859 | 31 | 0 | [6 empty] | 0.0000
215 | 626869 | F -1005 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 214 | 626868 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
216 | 626870 | F - Flat No 1006 | NA | 0.0000 | 0.0000 | 205 | 626859 | 31 | 0 | [6 empty] | 0.0000
217 | 626871 | F -1006 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 216 | 626870 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
218 | 626872 | F - Flat No 1007 | NA | 0.0000 | 0.0000 | 205 | 626859 | 31 | 0 | [6 empty] | 0.0000
219 | 626873 | F -1007 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 218 | 626872 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
220 | 626874 | F - Flat No 1008 | NA | 0.0000 | 0.0000 | 205 | 626859 | 31 | 0 | [6 empty] | 0.0000
221 | 626875 | F -1008 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 220 | 626874 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
222 | 626876 | F - Flat No 1009 | NA | 0.0000 | 0.0000 | 205 | 626859 | 31 | 0 | [6 empty] | 0.0000
223 | 626877 | F -1009 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 222 | 626876 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
224 | 626878 | F - Flat No 1010 | NA | 0.0000 | 0.0000 | 205 | 626859 | 31 | 0 | [6 empty] | 0.0000
225 | 626879 | F -1010 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 224 | 626878 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
226 | 626880 | F - Flat No 1011 | NA | 0.0000 | 0.0000 | 205 | 626859 | 31 | 0 | [6 empty] | 0.0000
227 | 626881 | F -1011 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 226 | 626880 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
228 | 626882 | F - Flat No 1012 | NA | 0.0000 | 0.0000 | 205 | 626859 | 31 | 0 | [6 empty] | 0.0000
229 | 626883 | F -1012 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 228 | 626882 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
230 | 626884 | F - Flat No 1013 | NA | 0.0000 | 0.0000 | 205 | 626859 | 31 | 0 | [6 empty] | 0.0000
231 | 626885 | F -1013 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 230 | 626884 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
232 | 626886 | F - Flat No 1014 | NA | 0.0000 | 0.0000 | 205 | 626859 | 31 | 0 | [6 empty] | 0.0000
233 | 626887 | F -1014 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 232 | 626886 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
234 | 626888 | F - 11th Floor | NA | 0.0000 | 0.0000 | 1 | 626655 | 31 | 0 | [6 empty] | 0.0000
235 | 626889 | F - Flat No 1101 | NA | 0.0000 | 0.0000 | 234 | 626888 | 31 | 0 | [6 empty] | 0.0000
236 | 626890 | F -1101 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 235 | 626889 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
237 | 626891 | F - Flat No 1102 | NA | 0.0000 | 0.0000 | 234 | 626888 | 31 | 0 | [6 empty] | 0.0000
238 | 626892 | F -1102 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 237 | 626891 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
239 | 626893 | F - Flat No 1103 | NA | 0.0000 | 0.0000 | 234 | 626888 | 31 | 0 | [6 empty] | 0.0000
240 | 626894 | F -1103 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 239 | 626893 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
241 | 626895 | F - Flat No 1104 | NA | 0.0000 | 0.0000 | 234 | 626888 | 31 | 0 | [6 empty] | 0.0000
242 | 626896 | F -1104 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 241 | 626895 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
243 | 626897 | F - Flat No 1105 | NA | 0.0000 | 0.0000 | 234 | 626888 | 31 | 0 | [6 empty] | 0.0000
244 | 626898 | F -1105 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 243 | 626897 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
245 | 626899 | F - Flat No 1106 | NA | 0.0000 | 0.0000 | 234 | 626888 | 31 | 0 | [6 empty] | 0.0000
246 | 626900 | F -1106 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 245 | 626899 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
247 | 626901 | F - Flat No 1107 | NA | 0.0000 | 0.0000 | 234 | 626888 | 31 | 0 | [6 empty] | 0.0000
248 | 626902 | F -1107 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 247 | 626901 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
249 | 626903 | F - Flat No 1108 | NA | 0.0000 | 0.0000 | 234 | 626888 | 31 | 0 | [6 empty] | 0.0000
250 | 626904 | F -1108 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 249 | 626903 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
251 | 626905 | F - Flat No 1109 | NA | 0.0000 | 0.0000 | 234 | 626888 | 31 | 0 | [6 empty] | 0.0000
252 | 626906 | F -1109 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 251 | 626905 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
253 | 626907 | F - Flat No 1110 | NA | 0.0000 | 0.0000 | 234 | 626888 | 31 | 0 | [6 empty] | 0.0000
254 | 626908 | F -1110 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 253 | 626907 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
255 | 626909 | F - Flat No 1111 | NA | 0.0000 | 0.0000 | 234 | 626888 | 31 | 0 | [6 empty] | 0.0000
256 | 626910 | F -1111 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 255 | 626909 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
257 | 626911 | F - Flat No 1112 | NA | 0.0000 | 0.0000 | 234 | 626888 | 31 | 0 | [6 empty] | 0.0000
258 | 626912 | F -1112 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 257 | 626911 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
259 | 626913 | F - Flat No 1113 | NA | 0.0000 | 0.0000 | 234 | 626888 | 31 | 0 | [6 empty] | 0.0000
260 | 626914 | F -1113 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 259 | 626913 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
261 | 626915 | F - Flat No 1114 | NA | 0.0000 | 0.0000 | 234 | 626888 | 31 | 0 | [6 empty] | 0.0000
262 | 626916 | F -1114 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 261 | 626915 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
263 | 626917 | F - 12th Floor | NA | 0.0000 | 0.0000 | 1 | 626655 | 31 | 0 | [6 empty] | 0.0000
264 | 626918 | F - Flat No 1201 | NA | 0.0000 | 0.0000 | 263 | 626917 | 31 | 0 | [6 empty] | 0.0000
265 | 626919 | F -1201 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 264 | 626918 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
266 | 626920 | F - Flat No 1202 | NA | 0.0000 | 0.0000 | 263 | 626917 | 31 | 0 | [6 empty] | 0.0000
267 | 626921 | F -1202 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 266 | 626920 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
268 | 626922 | F - Flat No 1203 | NA | 0.0000 | 0.0000 | 263 | 626917 | 31 | 0 | [6 empty] | 0.0000
269 | 626923 | F -1203 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 268 | 626922 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
270 | 626924 | F - Flat No 1204 | NA | 0.0000 | 0.0000 | 263 | 626917 | 31 | 0 | [6 empty] | 0.0000
271 | 626925 | F -1204 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 270 | 626924 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
272 | 626926 | F - Flat No 1205 | NA | 0.0000 | 0.0000 | 263 | 626917 | 31 | 0 | [6 empty] | 0.0000
273 | 626927 | F -1205 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 272 | 626926 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
274 | 626928 | F - Flat No 1206 | NA | 0.0000 | 0.0000 | 263 | 626917 | 31 | 0 | [6 empty] | 0.0000
275 | 626929 | F -1206 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 274 | 626928 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
276 | 626930 | F - Flat No 1207 | NA | 0.0000 | 0.0000 | 263 | 626917 | 31 | 0 | [6 empty] | 0.0000
277 | 626931 | F -1207 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 276 | 626930 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
278 | 626932 | F - Flat No 1208 | NA | 0.0000 | 0.0000 | 263 | 626917 | 31 | 0 | [6 empty] | 0.0000
279 | 626933 | F -1208 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 278 | 626932 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
280 | 626934 | F - Flat No 1209 | NA | 0.0000 | 0.0000 | 263 | 626917 | 31 | 0 | [6 empty] | 0.0000
281 | 626935 | F -1209 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 280 | 626934 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
282 | 626936 | F - Flat No 1210 | NA | 0.0000 | 0.0000 | 263 | 626917 | 31 | 0 | [6 empty] | 0.0000
283 | 626937 | F -1210 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 282 | 626936 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
284 | 626938 | F - Flat No 1211 | NA | 0.0000 | 0.0000 | 263 | 626917 | 31 | 0 | [6 empty] | 0.0000
285 | 626939 | F -1211 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 284 | 626938 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
286 | 626940 | F - Flat No 1212 | NA | 0.0000 | 0.0000 | 263 | 626917 | 31 | 0 | [6 empty] | 0.0000
287 | 626941 | F -1212 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 286 | 626940 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
288 | 626942 | F - Flat No 1213 | NA | 0.0000 | 0.0000 | 263 | 626917 | 31 | 0 | [6 empty] | 0.0000
289 | 626943 | F -1213 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 288 | 626942 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
290 | 626944 | F - Flat No 1214 | NA | 0.0000 | 0.0000 | 263 | 626917 | 31 | 0 | [6 empty] | 0.0000
291 | 626945 | F -1214 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 290 | 626944 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
292 | 626946 | F - 13th Floor | NA | 0.0000 | 0.0000 | 1 | 626655 | 31 | 0 | [6 empty] | 0.0000
293 | 626947 | F - Flat No 1301 | NA | 0.0000 | 0.0000 | 292 | 626946 | 31 | 0 | [6 empty] | 0.0000
294 | 626948 | F -1301 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 293 | 626947 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
295 | 626949 | F - Flat No 1302 | NA | 0.0000 | 0.0000 | 292 | 626946 | 31 | 0 | [6 empty] | 0.0000
296 | 626950 | F -1302 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 295 | 626949 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
297 | 626951 | F - Flat No 1303 | NA | 0.0000 | 0.0000 | 292 | 626946 | 31 | 0 | [6 empty] | 0.0000
298 | 626952 | F -1303 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 297 | 626951 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
299 | 626953 | F - Flat No 1304 | NA | 0.0000 | 0.0000 | 292 | 626946 | 31 | 0 | [6 empty] | 0.0000
300 | 626954 | F -1304 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 299 | 626953 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
301 | 626955 | F - Flat No 1305 | NA | 0.0000 | 0.0000 | 292 | 626946 | 31 | 0 | [6 empty] | 0.0000
302 | 626956 | F -1305 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 301 | 626955 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
303 | 626957 | F - Flat No 1306 | NA | 0.0000 | 0.0000 | 292 | 626946 | 31 | 0 | [6 empty] | 0.0000
304 | 626958 | F -1306 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 303 | 626957 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
305 | 626959 | F - Flat No 1307 | NA | 0.0000 | 0.0000 | 292 | 626946 | 31 | 0 | [6 empty] | 0.0000
306 | 626960 | F -1307 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 305 | 626959 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
307 | 626961 | F - Flat No 1308 | NA | 0.0000 | 0.0000 | 292 | 626946 | 31 | 0 | [6 empty] | 0.0000
308 | 626962 | F -1308 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 307 | 626961 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
309 | 626963 | F - Flat No 1309 | NA | 0.0000 | 0.0000 | 292 | 626946 | 31 | 0 | [6 empty] | 0.0000
310 | 626964 | F -1309 Kitchen Otta | R.Ft | 0.0000 | 0.0000 | 309 | 626963 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
311 | 626965 | F - Flat No 1310 | NA | 0.0000 | 0.0000 | 292 | 626946 | 31 | 0 | [6 empty] | 0.0000
312 | 626966 | F -1310 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 311 | 626965 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
313 | 626967 | F - Flat No 1311 | NA | 0.0000 | 0.0000 | 292 | 626946 | 31 | 0 | [6 empty] | 0.0000
314 | 626968 | F -1311 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 313 | 626967 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
315 | 626969 | F - Flat No 1312 | NA | 0.0000 | 0.0000 | 292 | 626946 | 31 | 0 | [6 empty] | 0.0000
316 | 626970 | F -1312 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 315 | 626969 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
317 | 626971 | F - Flat No 1313 | NA | 0.0000 | 0.0000 | 292 | 626946 | 31 | 0 | [6 empty] | 0.0000
318 | 626972 | F -1313 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 317 | 626971 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
319 | 626973 | F - Flat No 1314 | NA | 0.0000 | 0.0000 | 292 | 626946 | 31 | 0 | [6 empty] | 0.0000
320 | 626974 | F -1314 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 319 | 626973 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
321 | 626975 | F - 14th Floor | NA | 0.0000 | 0.0000 | 1 | 626655 | 31 | 0 | [6 empty] | 0.0000
322 | 626976 | F - Flat No 1401 | NA | 0.0000 | 0.0000 | 321 | 626975 | 31 | 0 | [6 empty] | 0.0000
323 | 626977 | F -1401 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 322 | 626976 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
324 | 626978 | F - Flat No 1402 | NA | 0.0000 | 0.0000 | 321 | 626975 | 31 | 0 | [6 empty] | 0.0000
325 | 626979 | F -1402 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 324 | 626978 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
326 | 626980 | F - Flat No 1403 | NA | 0.0000 | 0.0000 | 321 | 626975 | 31 | 0 | [6 empty] | 0.0000
327 | 626981 | F -1403 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 326 | 626980 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
328 | 626982 | F - Flat No 1404 | NA | 0.0000 | 0.0000 | 321 | 626975 | 31 | 0 | [6 empty] | 0.0000
329 | 626983 | F -1404 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 328 | 626982 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
330 | 626984 | F - Flat No 1405 | NA | 0.0000 | 0.0000 | 321 | 626975 | 31 | 0 | [6 empty] | 0.0000
331 | 626985 | F -1405 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 330 | 626984 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
332 | 626986 | F - Flat No 1406 | NA | 0.0000 | 0.0000 | 321 | 626975 | 31 | 0 | [6 empty] | 0.0000
333 | 626987 | F -1406 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 332 | 626986 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
334 | 626988 | F - Flat No 1407 | NA | 0.0000 | 0.0000 | 321 | 626975 | 31 | 0 | [6 empty] | 0.0000
335 | 626989 | F -1407 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 334 | 626988 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
336 | 626990 | F - Flat No 1408 | NA | 0.0000 | 0.0000 | 321 | 626975 | 31 | 0 | [6 empty] | 0.0000
337 | 626991 | F -1408 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 336 | 626990 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
338 | 626992 | F - Flat No 1409 | NA | 0.0000 | 0.0000 | 321 | 626975 | 31 | 0 | [6 empty] | 0.0000
339 | 626993 | F -1409 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 338 | 626992 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
340 | 626994 | F - Flat No 1410 | NA | 0.0000 | 0.0000 | 321 | 626975 | 31 | 0 | [6 empty] | 0.0000
341 | 626995 | F -1410 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 340 | 626994 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
342 | 626996 | F - Flat No 1411 | NA | 0.0000 | 0.0000 | 321 | 626975 | 31 | 0 | [6 empty] | 0.0000
343 | 626997 | F -1411 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 342 | 626996 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
344 | 626998 | F - Flat No 1412 | NA | 0.0000 | 0.0000 | 321 | 626975 | 31 | 0 | [6 empty] | 0.0000
345 | 626999 | F -1412 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 344 | 626998 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
346 | 627000 | F - Flat No 1413 | NA | 0.0000 | 0.0000 | 321 | 626975 | 31 | 0 | [6 empty] | 0.0000
347 | 627001 | F -1413 Kitchen Otta | R.Ft | 6.1008 | 6.1008 | 346 | 627000 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000
348 | 627002 | F - Flat No 1414 | NA | 0.0000 | 0.0000 | 321 | 626975 | 31 | 0 | [6 empty] | 0.0000
349 | 627003 | F -1414 Kitchen Otta | R.Ft | 6.1000 | 6.1000 | 348 | 627002 | 4 | 30708 | A-301 Kitchen Ota | [5 empty] | 0.0000