## Sheet1
Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW
Selected Group :- C -External Painting Work | Selected Group :- C -External Painting Work | Selected Group :- C -External Painting Work | Selected Group :- C -External Painting Work | Selected Group :- C -External Painting Work | Selected Group :- C -External Painting Work | Selected Group :- C -External Painting Work | Selected Group :- C -External Painting Work | Selected Group :- C -External Painting Work | Selected Group :- C -External Painting Work | Selected Group :- C -External Painting Work | Selected Group :- C -External Painting Work | Selected Group :- C -External Painting Work | Selected Group :- C -External Painting Work | Selected Group :- C -External Painting Work | Selected Group :- C -External Painting Work | Selected Group :- C -External Painting Work
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 627427 | A -External Painting Work | NA | 0.0000 | 0.0000 | 0 | 620784 | 31 | 0 | [6 empty] | 0.0000
2 | 627428 | A - West Side External painting Work | NA | 0.0000 | 0.0000 | 1 | 627427 | 31 | 0 | [6 empty] | 0.0000
3 | 627429 | A - West Side UG Floor External Painting Work | Sq.Ft | 339.9380 | 339.9380 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
4 | 627430 | A - West Side 1st Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
5 | 627431 | A - West Side 2nd Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
6 | 627432 | A - West Side 3rd Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
7 | 627433 | A - West Side 4th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
8 | 627434 | A - West Side 5th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
9 | 627435 | A - West Side 6th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
10 | 627436 | A - West Side 7th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
11 | 627437 | A - West Side 8th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
12 | 627438 | A - West Side 9th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
13 | 627439 | A - West Side 10th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
14 | 627440 | A - West Side 11th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
15 | 627441 | A - West Side 12th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
16 | 627442 | A - West Side 13th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
17 | 627443 | A - West Side 14th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
18 | 627496 | A - West Side 15th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
19 | 627497 | A - West Side 16th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
20 | 627498 | A - West Side 17th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
21 | 627499 | A - West Side 18th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
22 | 627444 | A - West Side Terrace Floor External Painting Work | Sq.Ft | 1633.4050 | 1633.4050 | 2 | 627428 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
23 | 627445 | A - East Side External painting Work | NA | 0.0000 | 0.0000 | 1 | 627427 | 31 | 0 | [6 empty] | 0.0000
24 | 627446 | A - East Side UG Floor External Painting Work | Sq.Ft | 413.6070 | 413.6070 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
25 | 627447 | A - East Side 1st Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
26 | 627448 | A - East Side 2nd Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
27 | 627449 | A - East Side 3rd Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
28 | 627450 | A - East Side 4th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
29 | 627451 | A - East Side 5th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
30 | 627452 | A - East Side 6th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
31 | 627453 | A - East Side 7th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
32 | 627454 | A - East Side 8th Floor External Painting Work | Sq.Ft | 638.5700 | 638.5700 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
33 | 627455 | A - East Side 9th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
34 | 627456 | A - East Side 10th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
35 | 627457 | A - East Side 11th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
36 | 627458 | A - East Side 12th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
37 | 627459 | A - East Side 13th Floor External Painting Work | Sq.Ft | 638.5700 | 638.5700 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
38 | 627460 | A - East Side 14th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
39 | 627500 | A - East Side 15th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
40 | 627501 | A - East Side 16th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
41 | 627502 | A - East Side 17th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
42 | 627503 | A - East Side 18th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
43 | 627461 | A - East Side Terrace Floor External Painting Work | Sq.Ft | 834.6620 | 834.6620 | 23 | 627445 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
44 | 627462 | A - North Side External painting Work | NA | 0.0000 | 0.0000 | 1 | 627427 | 31 | 0 | [6 empty] | 0.0000
45 | 627463 | A - North Side UG Floor External Painting Work | Sq.Ft | 353.0480 | 353.0480 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
46 | 627464 | A - North Side 1st Floor External Painting Work | Sq.Ft | 1529.0690 | 1529.0690 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
47 | 627465 | A - North Side 2nd Floor External Painting Work | Sq.Ft | 1529.0690 | 1529.0690 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
48 | 627466 | A - North Side 3rd Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
49 | 627467 | A - North Side 4th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
50 | 627468 | A - North Side 5th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
51 | 627469 | A - North Side 6th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
52 | 627470 | A - North Side 7th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
53 | 627471 | A - North Side 8th Floor External Painting Work | Sq.Ft | 2070.2730 | 2070.2730 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
54 | 627472 | A - North Side 9th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
55 | 627473 | A - North Side 10th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
56 | 627474 | A - North Side 11th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
57 | 627475 | A - North Side 12th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
58 | 627476 | A - North Side 13th Floor External Painting Work | Sq.Ft | 2070.2730 | 2070.2730 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
59 | 627477 | A - North Side 14th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
60 | 627504 | A - North Side 15th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
61 | 627505 | A - North Side 16th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
62 | 627506 | A - North Side 17th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
63 | 627507 | C . North Side 18th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
64 | 627478 | A - North Side Terrace Floor External Painting Work | Sq.Ft | 2100.5300 | 2100.5300 | 44 | 627462 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
65 | 627479 | A - South Side External painting Work | NA | 0.0000 | 0.0000 | 1 | 627427 | 31 | 0 | [6 empty] | 0.0000
66 | 627480 | A - South Side UG Floor External Painting Work | Sq.Ft | 462.6150 | 462.6150 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
67 | 627481 | A - South Side 1st Floor External Painting Work | Sq.Ft | 1498.1870 | 1498.1870 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
68 | 627482 | A - South Side 2nd Floor External Painting Work | Sq.Ft | 1517.5630 | 1517.5630 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
69 | 627483 | A - South Side 3rd Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
70 | 627484 | A - South Side 4th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
71 | 627485 | A - South Side 5th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
72 | 627486 | A - South Side 6th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
73 | 627487 | A - South Side 7th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
74 | 627488 | A - South Side 8th Floor External Painting Work | Sq.Ft | 1972.7840 | 1972.7840 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
75 | 627489 | A - South Side 9th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
76 | 627490 | A - South Side 10th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
77 | 627491 | A - South Side 11th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
78 | 627492 | A - South Side 12th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
79 | 627493 | A - South Side 13th Floor External Painting Work | Sq.Ft | 1972.7840 | 1972.7840 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
80 | 627494 | A - South Side 14th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
81 | 627508 | A - South Side 15th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
82 | 627509 | A - South Side 16th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
83 | 627510 | A - South Side 17th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
84 | 627511 | A - South Side 18th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
85 | 627495 | A - South Side Terrace Floor External Painting Work | Sq.Ft | 1996.4210 | 1996.4210 | 65 | 627479 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000