## Sheet1
Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW
Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting | Selected Group :- C - Plumbing Duct Painting
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 627512 | A - Plumbing Duct Painting | NA | 0.0000 | 0.0000 | 0 | 620784 | 31 | 0 | [6 empty] | 0.0000
2 | 627513 | A -Duct 6 External painting Work | NA | 0.0000 | 0.0000 | 1 | 627512 | 31 | 0 | [6 empty] | 0.0000
3 | 627514 | A -1st Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 627513 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
4 | 623083 | A-2nd Floor Lift 1 Duct Painting Work | Sq.Ft | 117.8900 | 117.8900 | 0 | 623082 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
5 | 623084 | A-3rd Floor Lift 1 Duct Painting Work | Sq.Ft | 101.8000 | 101.8000 | 4 | 623083 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
6 | 627515 | A -2nd Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 627513 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
7 | 627516 | A -3rd Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 627513 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
8 | 627517 | A -4th External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 627513 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
9 | 627518 | A -5th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 627513 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
10 | 627519 | A -6th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 627513 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
11 | 627520 | A -7th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 627513 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
12 | 627521 | A -8th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 627513 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
13 | 627522 | A -9th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 627513 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
14 | 627523 | A -10th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 627513 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
15 | 627524 | A -11th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 627513 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
16 | 627525 | A -12th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 627513 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
17 | 627526 | A -13th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 627513 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
18 | 627527 | A -14th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 2 | 627513 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
19 | 627528 | A - Terrace Floor External Duct Painting Work | Sq.Ft | 2004.1710 | 2004.1710 | 2 | 627513 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000