## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - Common Lobby Tiling (M) | Selected Group :- C - Common Lobby Tiling (M) | Selected Group :- C - Common Lobby Tiling (M) | Selected Group :- C - Common Lobby Tiling (M) | Selected Group :- C - Common Lobby Tiling (M) | Selected Group :- C - Common Lobby Tiling (M) | Selected Group :- C - Common Lobby Tiling (M) | Selected Group :- C - Common Lobby Tiling (M) | Selected Group :- C - Common Lobby Tiling (M) | Selected Group :- C - Common Lobby Tiling (M) | Selected Group :- C - Common Lobby Tiling (M) | Selected Group :- C - Common Lobby Tiling (M) | Selected Group :- C - Common Lobby Tiling (M) | Selected Group :- C - Common Lobby Tiling (M) | Selected Group :- C - Common Lobby Tiling (M) | Selected Group :- C - Common Lobby Tiling (M) | Selected Group :- C - Common Lobby Tiling (M)
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 627654 | F - Common Lobby Tiling (M) | NA | 0.0000 | 0.0000 | 0 | 512330 | 31 | 0 | [6 empty] | 0.0000
2 | 627655 | F - Staircase Landing Flooring work | NA | 0.0000 | 0.0000 | 1 | 627654 | 31 | 0 | [6 empty] | 0.0000
3 | 627656 | F - Staircase 1 | NA | 0.0000 | 0.0000 | 2 | 627655 | 31 | 0 | [6 empty] | 0.0000
4 | 627657 | F - Ground Floor | NA | 0.0000 | 0.0000 | 3 | 627656 | 31 | 0 | [6 empty] | 0.0000
5 | 627658 | F - G.F Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 4 | 627657 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
6 | 627659 | F - G.F Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 4 | 627657 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
7 | 627660 | F - 1st Floor | NA | 0.0000 | 0.0000 | 3 | 627656 | 31 | 0 | [6 empty] | 0.0000
8 | 627661 | F - 1st Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 7 | 627660 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
9 | 627662 | F - 1st Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 7 | 627660 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
10 | 627663 | F - 2nd Floor | NA | 0.0000 | 0.0000 | 3 | 627656 | 31 | 0 | [6 empty] | 0.0000
11 | 627664 | F - 2nd Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 10 | 627663 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
12 | 627665 | F - 2nd Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 627663 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
13 | 627666 | F - 3rd Floor | NA | 0.0000 | 0.0000 | 3 | 627656 | 31 | 0 | [6 empty] | 0.0000
14 | 627667 | F - 3rd Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 13 | 627666 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
15 | 627668 | F - 3rd Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 13 | 627666 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
16 | 627669 | F - 4th Floor | NA | 0.0000 | 0.0000 | 3 | 627656 | 31 | 0 | [6 empty] | 0.0000
17 | 627670 | F - 4th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 16 | 627669 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
18 | 627671 | F - 4th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 16 | 627669 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
19 | 627672 | F - 5th Floor | NA | 0.0000 | 0.0000 | 3 | 627656 | 31 | 0 | [6 empty] | 0.0000
20 | 627673 | F - 5th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 19 | 627672 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
21 | 627674 | F - 5th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 19 | 627672 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
22 | 627733 | F - 6th Floor | NA | 0.0000 | 0.0000 | 3 | 627656 | 31 | 0 | [6 empty] | 0.0000
23 | 627734 | F - 6th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 22 | 627733 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
24 | 627735 | F - 6th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 627733 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
25 | 627736 | F - 7th Floor | NA | 0.0000 | 0.0000 | 3 | 627656 | 31 | 0 | [6 empty] | 0.0000
26 | 627737 | F - 7th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 25 | 627736 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
27 | 627738 | F - 7th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 25 | 627736 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
28 | 627739 | F - 8th Floor | NA | 0.0000 | 0.0000 | 3 | 627656 | 31 | 0 | [6 empty] | 0.0000
29 | 627740 | F - 8th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 28 | 627739 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
30 | 627741 | F - 8th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 28 | 627739 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
31 | 627742 | F - 9th Floor | NA | 0.0000 | 0.0000 | 3 | 627656 | 31 | 0 | [6 empty] | 0.0000
32 | 627743 | F - 9th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 31 | 627742 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
33 | 627744 | F - 9th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 31 | 627742 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
34 | 627745 | F - 10th Floor | NA | 0.0000 | 0.0000 | 3 | 627656 | 31 | 0 | [6 empty] | 0.0000
35 | 627746 | F - 10th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 34 | 627745 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
36 | 627747 | F - 10th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 627745 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
37 | 627748 | F - 11th Floor | NA | 0.0000 | 0.0000 | 3 | 627656 | 31 | 0 | [6 empty] | 0.0000
38 | 627749 | F - 11th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 37 | 627748 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
39 | 627750 | F - 11th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 37 | 627748 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
40 | 627751 | F - 12th Floor | NA | 0.0000 | 0.0000 | 3 | 627656 | 31 | 0 | [6 empty] | 0.0000
41 | 627752 | F - 12th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 40 | 627751 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
42 | 627753 | F - 12th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 40 | 627751 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
43 | 627754 | F - 13th Floor | NA | 0.0000 | 0.0000 | 3 | 627656 | 31 | 0 | [6 empty] | 0.0000
44 | 627755 | F - 13th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 43 | 627754 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
45 | 627756 | F - 13th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 43 | 627754 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
46 | 627757 | F - 14th Floor | NA | 0.0000 | 0.0000 | 3 | 627656 | 31 | 0 | [6 empty] | 0.0000
47 | 627758 | F - 14th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 46 | 627757 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
48 | 627759 | F - 14th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 627757 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
49 | 627675 | F - Staircase 2 | NA | 0.0000 | 0.0000 | 2 | 627655 | 31 | 0 | [6 empty] | 0.0000
50 | 627676 | F - Ground Floor | NA | 0.0000 | 0.0000 | 49 | 627675 | 31 | 0 | [6 empty] | 0.0000
51 | 627677 | F - G.F Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 50 | 627676 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
52 | 627678 | F - G.F Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 627676 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
53 | 627679 | F - 1st Floor | NA | 0.0000 | 0.0000 | 49 | 627675 | 31 | 0 | [6 empty] | 0.0000
54 | 627680 | F - 1st Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 53 | 627679 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
55 | 627681 | F - 1st Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 53 | 627679 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
56 | 627682 | F - 2nd Floor | NA | 0.0000 | 0.0000 | 49 | 627675 | 31 | 0 | [6 empty] | 0.0000
57 | 627683 | F - 2nd Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 56 | 627682 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
58 | 627684 | F - 2nd Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 56 | 627682 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
59 | 627685 | F - 3rd Floor | NA | 0.0000 | 0.0000 | 49 | 627675 | 31 | 0 | [6 empty] | 0.0000
60 | 627686 | F - 3rd Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 59 | 627685 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
61 | 627687 | F - 3rd Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 59 | 627685 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
62 | 627688 | F - 4th Floor | NA | 0.0000 | 0.0000 | 49 | 627675 | 31 | 0 | [6 empty] | 0.0000
63 | 627689 | F - 4th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 62 | 627688 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
64 | 627690 | F - 4th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 62 | 627688 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
65 | 627691 | F - 5th Floor | NA | 0.0000 | 0.0000 | 49 | 627675 | 31 | 0 | [6 empty] | 0.0000
66 | 627692 | F - 5th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 65 | 627691 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
67 | 627693 | F - 5th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 65 | 627691 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
68 | 627760 | F - 6th Floor | NA | 0.0000 | 0.0000 | 49 | 627675 | 31 | 0 | [6 empty] | 0.0000
69 | 627761 | F - 6th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 68 | 627760 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
70 | 627762 | F - 6th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 68 | 627760 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
71 | 627763 | F - 7th Floor | NA | 0.0000 | 0.0000 | 49 | 627675 | 31 | 0 | [6 empty] | 0.0000
72 | 627764 | F - 7th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 71 | 627763 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
73 | 627765 | F - 7th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 71 | 627763 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
74 | 627766 | F - 8th Floor | NA | 0.0000 | 0.0000 | 49 | 627675 | 31 | 0 | [6 empty] | 0.0000
75 | 627767 | F - 8th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 74 | 627766 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
76 | 627768 | F - 8th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 74 | 627766 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
77 | 627769 | F - 9th Floor | NA | 0.0000 | 0.0000 | 49 | 627675 | 31 | 0 | [6 empty] | 0.0000
78 | 627770 | F - 9th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 77 | 627769 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
79 | 627771 | F - 9th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 77 | 627769 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
80 | 627772 | F - 10th Floor | NA | 0.0000 | 0.0000 | 49 | 627675 | 31 | 0 | [6 empty] | 0.0000
81 | 627773 | F - 10th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 80 | 627772 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
82 | 627774 | F - 10th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 80 | 627772 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
83 | 627775 | F - 11th Floor | NA | 0.0000 | 0.0000 | 49 | 627675 | 31 | 0 | [6 empty] | 0.0000
84 | 627776 | F - 11th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 83 | 627775 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
85 | 627777 | F - 11th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 83 | 627775 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
86 | 627778 | F - 12th Floor | NA | 0.0000 | 0.0000 | 49 | 627675 | 31 | 0 | [6 empty] | 0.0000
87 | 627779 | F - 12th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 86 | 627778 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
88 | 627780 | F - 12th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 86 | 627778 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
89 | 627781 | F - 13th Floor | NA | 0.0000 | 0.0000 | 49 | 627675 | 31 | 0 | [6 empty] | 0.0000
90 | 627782 | F - 13th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 89 | 627781 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
91 | 627783 | F - 13th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 89 | 627781 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
92 | 627784 | F - 14th Floor | NA | 0.0000 | 0.0000 | 49 | 627675 | 31 | 0 | [6 empty] | 0.0000
93 | 627785 | F - 14th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 92 | 627784 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
94 | 627786 | F - 14th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 92 | 627784 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
95 | 627694 | F - Common Lobby Flooring Work | NA | 0.0000 | 0.0000 | 1 | 627654 | 31 | 0 | [6 empty] | 0.0000
96 | 627696 | F - 3rd Floor Lobby Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 95 | 627694 | 4 | 33949 | C - 1st Floor Lobby Flooring Work | [5 empty] | 0.0000
97 | 627698 | F - 4th Floor Lobby Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 95 | 627694 | 4 | 33949 | C - 1st Floor Lobby Flooring Work | [5 empty] | 0.0000
98 | 627699 | F - 5th Floor Lobby Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 95 | 627694 | 4 | 33949 | C - 1st Floor Lobby Flooring Work | [5 empty] | 0.0000
99 | 627700 | F - 6th Floor Lobby Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 95 | 627694 | 4 | 33949 | C - 1st Floor Lobby Flooring Work | [5 empty] | 0.0000
100 | 627701 | F - 7th Floor Lobby Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 95 | 627694 | 4 | 33949 | C - 1st Floor Lobby Flooring Work | [5 empty] | 0.0000
101 | 627702 | F - 8th Floor Lobby Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 95 | 627694 | 4 | 33949 | C - 1st Floor Lobby Flooring Work | [5 empty] | 0.0000
102 | 627721 | F - 9th Floor Lobby Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 95 | 627694 | 4 | 33949 | C - 1st Floor Lobby Flooring Work | [5 empty] | 0.0000
103 | 627722 | F - 10th Floor Lobby Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 95 | 627694 | 4 | 33949 | C - 1st Floor Lobby Flooring Work | [5 empty] | 0.0000
104 | 627723 | F - 11th Floor Lobby Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 95 | 627694 | 4 | 33949 | C - 1st Floor Lobby Flooring Work | [5 empty] | 0.0000
105 | 627724 | F - 12th Floor Lobby Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 95 | 627694 | 4 | 33949 | C - 1st Floor Lobby Flooring Work | [5 empty] | 0.0000
106 | 627725 | F - 13th Floor Lobby Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 95 | 627694 | 4 | 33949 | C - 1st Floor Lobby Flooring Work | [5 empty] | 0.0000
107 | 627726 | F - 14th Floor Lobby Flooring Work | Sq.Ft | 1.0000 | 1.0000 | 95 | 627694 | 4 | 33949 | C - 1st Floor Lobby Flooring Work | [5 empty] | 0.0000
108 | 627695 | F - Common Lobby Skirting Work | NA | 0.0000 | 0.0000 | 1 | 627654 | 31 | 0 | [6 empty] | 0.0000
109 | 627697 | F - 3rd Floor Lobby Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 627695 | 4 | 33950 | C - 1st Floor Lobby Skirting Work | [5 empty] | 0.0000
110 | 627703 | F - 4th Floor Lobby Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 627695 | 4 | 33950 | C - 1st Floor Lobby Skirting Work | [5 empty] | 0.0000
111 | 627704 | F - 5th Floor Lobby Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 627695 | 4 | 33950 | C - 1st Floor Lobby Skirting Work | [5 empty] | 0.0000
112 | 627705 | F - 6th Floor Lobby Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 627695 | 4 | 33950 | C - 1st Floor Lobby Skirting Work | [5 empty] | 0.0000
113 | 627706 | F - 7th Floor Lobby Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 627695 | 4 | 33950 | C - 1st Floor Lobby Skirting Work | [5 empty] | 0.0000
114 | 627707 | F - 8th Floor Lobby Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 627695 | 4 | 33950 | C - 1st Floor Lobby Skirting Work | [5 empty] | 0.0000
115 | 627727 | F - 9th Floor Lobby Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 627695 | 4 | 33950 | C - 1st Floor Lobby Skirting Work | [5 empty] | 0.0000
116 | 627728 | F - 10th Floor Lobby Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 627695 | 4 | 33950 | C - 1st Floor Lobby Skirting Work | [5 empty] | 0.0000
117 | 627729 | F - 11th Floor Lobby Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 627695 | 4 | 33950 | C - 1st Floor Lobby Skirting Work | [5 empty] | 0.0000
118 | 627730 | F - 12th Floor Lobby Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 627695 | 4 | 33950 | C - 1st Floor Lobby Skirting Work | [5 empty] | 0.0000
119 | 627731 | F - 13th Floor Lobby Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 627695 | 4 | 33950 | C - 1st Floor Lobby Skirting Work | [5 empty] | 0.0000
120 | 627732 | F - 14th Floor Lobby Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 108 | 627695 | 4 | 33950 | C - 1st Floor Lobby Skirting Work | [5 empty] | 0.0000
121 | 627708 | F -Common Lobby Tiling Bedding Material | NA | 0.0000 | 0.0000 | 1 | 627654 | 31 | 0 | [6 empty] | 0.0000
122 | 627709 | F -3rd Floor common Lobby Tiling Bedding Material | Sq.Ft | 1251.2100 | 1251.2100 | 121 | 627708 | 4 | 34045 | C-3rd Floor Common Lobby Tiling Bedding | [5 empty] | 0.0000
123 | 627710 | F -4th Floor common Lobby Tiling Bedding Material | Sq.Ft | 1251.2100 | 1251.2100 | 121 | 627708 | 4 | 34045 | C-3rd Floor Common Lobby Tiling Bedding | [5 empty] | 0.0000
124 | 627711 | F -5th Floor common Lobby Tiling Bedding Material | Sq.Ft | 1251.2100 | 1251.2100 | 121 | 627708 | 4 | 34045 | C-3rd Floor Common Lobby Tiling Bedding | [5 empty] | 0.0000
125 | 627712 | F -6th Floor common Lobby Tiling Bedding Material | Sq.Ft | 1251.2100 | 1251.2100 | 121 | 627708 | 4 | 34045 | C-3rd Floor Common Lobby Tiling Bedding | [5 empty] | 0.0000
126 | 627713 | F -7th Floor common Lobby Tiling Bedding Material | Sq.Ft | 1251.2100 | 1251.2100 | 121 | 627708 | 4 | 34045 | C-3rd Floor Common Lobby Tiling Bedding | [5 empty] | 0.0000
127 | 627714 | F -8th Floor common Lobby Tiling Bedding Material | Sq.Ft | 1034.9600 | 1034.9600 | 121 | 627708 | 4 | 34045 | C-3rd Floor Common Lobby Tiling Bedding | [5 empty] | 0.0000
128 | 627715 | F -9th Floor common Lobby Tiling Bedding Material | Sq.Ft | 1251.2100 | 1251.2100 | 121 | 627708 | 4 | 34045 | C-3rd Floor Common Lobby Tiling Bedding | [5 empty] | 0.0000
129 | 627716 | F -10th Floor common Lobby Tiling Bedding Material | Sq.Ft | 1251.2100 | 1251.2100 | 121 | 627708 | 4 | 34045 | C-3rd Floor Common Lobby Tiling Bedding | [5 empty] | 0.0000
130 | 627717 | F -11th Floor common Lobby Tiling Bedding Material | Sq.Ft | 1251.2100 | 1251.2100 | 121 | 627708 | 4 | 34045 | C-3rd Floor Common Lobby Tiling Bedding | [5 empty] | 0.0000
131 | 627718 | F -12th Floor common Lobby Tiling Bedding Material | Sq.Ft | 1251.2100 | 1251.2100 | 121 | 627708 | 4 | 34045 | C-3rd Floor Common Lobby Tiling Bedding | [5 empty] | 0.0000
132 | 627719 | F -13th Floor common Lobby Tiling Bedding Material | Sq.Ft | 1034.9600 | 1034.9600 | 121 | 627708 | 4 | 34045 | C-3rd Floor Common Lobby Tiling Bedding | [5 empty] | 0.0000
133 | 627720 | F -14th Floor common Lobby Tiling Bedding Material | Sq.Ft | 1251.2100 | 1251.2100 | 121 | 627708 | 4 | 34045 | C-3rd Floor Common Lobby Tiling Bedding | [5 empty] | 0.0000