## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 628574 | G - Lift Cladding Work | NA | 0.0000 | 0.0000 | 0 | 538613 | 31 | 0 | [6 empty] | 0.0000
2 | 628575 | G - Lift 1 | NA | 0.0000 | 0.0000 | 1 | 628574 | 31 | 0 | [6 empty] | 0.0000
3 | 628576 | G -GF Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628575 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
4 | 628577 | G -1st Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628575 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
5 | 628578 | G -2nd Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628575 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
6 | 628579 | G -3rd Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628575 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
7 | 628580 | G -4th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628575 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
8 | 628581 | G -5th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628575 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
9 | 628582 | G -6th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628575 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
10 | 628583 | G -7th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628575 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
11 | 628584 | G -8th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628575 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
12 | 628585 | G -9th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628575 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
13 | 628586 | G -10th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628575 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
14 | 628587 | G -11th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628575 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
15 | 628588 | G -12th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628575 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
16 | 628589 | G -13th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628575 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
17 | 628590 | G -14th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628575 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
18 | 628591 | G - Lift 2 | NA | 0.0000 | 0.0000 | 1 | 628574 | 31 | 0 | [6 empty] | 0.0000
19 | 628592 | G -GF Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628591 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
20 | 628593 | G -1st Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628591 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
21 | 628594 | G -2nd Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628591 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
22 | 628595 | G -3rd Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628591 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
23 | 628596 | G -4th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628591 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
24 | 628597 | G -5th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628591 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
25 | 628598 | G -6th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628591 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
26 | 628599 | G -7th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628591 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
27 | 628600 | G -8th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628591 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
28 | 628601 | G -9th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628591 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
29 | 628602 | G -10th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628591 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
30 | 628603 | G -11th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628591 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
31 | 628604 | G -12th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628591 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
32 | 628605 | G -13th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628591 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
33 | 628606 | G -14th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628591 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
34 | 628607 | G Lift 1 - 20mm Hole Making For Lift Button | No. | 1.0000 | 1.0000 | 1 | 628574 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
35 | 628608 | G Lift 2 - 20mm Hole Making For Lift Button | No. | 1.0000 | 1.0000 | 1 | 628574 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000