## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work | Selected Group :- G - Lift Cladding Work
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 628638 | C - Lift Cladding Work | NA | 0.0000 | 0.0000 | 0 | 570227 | 31 | 0 | [6 empty] | 0.0000
2 | 628639 | C - Lift 1 | NA | 0.0000 | 0.0000 | 1 | 628638 | 31 | 0 | [6 empty] | 0.0000
3 | 628642 | C - G.F. Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628639 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
4 | 628643 | C - 1st Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628639 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
5 | 628644 | C - 2nd Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628639 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
6 | 628645 | C - 3rd Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628639 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
7 | 628646 | C - 4th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628639 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
8 | 628647 | C - 5th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628639 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
9 | 628648 | C - 6th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628639 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
10 | 628649 | C - 7th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628639 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
11 | 628650 | C - 8th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628639 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
12 | 628651 | C - 9th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628639 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
13 | 628652 | C - 10th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628639 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
14 | 628653 | C - 11th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628639 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
15 | 628654 | C - 12th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628639 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
16 | 628655 | C - 13th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628639 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
17 | 628671 | C - 14th Floor Lift 1 Cladding Work | No. | 1.0000 | 1.0000 | 2 | 628639 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
18 | 628656 | C - Lift 2 | NA | 0.0000 | 0.0000 | 1 | 628638 | 31 | 0 | [6 empty] | 0.0000
19 | 628657 | C - G.F. Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628656 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
20 | 628658 | C - 1st Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628656 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
21 | 628659 | C - 2nd Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628656 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
22 | 628660 | C - 3rd Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628656 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
23 | 628661 | C - 4th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628656 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
24 | 628662 | C - 5th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628656 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
25 | 628663 | C - 6th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628656 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
26 | 628664 | C - 7th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628656 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
27 | 628665 | C - 8th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628656 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
28 | 628666 | C - 9th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628656 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
29 | 628667 | C - 10th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628656 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
30 | 628668 | C - 11th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628656 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
31 | 628669 | C - 12th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628656 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
32 | 628670 | C - 13th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628656 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
33 | 628672 | C - 14th Floor Lift 2 Cladding Work | No. | 1.0000 | 1.0000 | 18 | 628656 | 4 | 34458 | G - Lift Cladding Work | [5 empty] | 0.0000
34 | 628640 | C Lift 1 - 20mm Hole Making For Lift Button | No. | 1.0000 | 1.0000 | 1 | 628638 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000
35 | 628641 | C Lift 2 - 20mm Hole Making For Lift Button | No. | 1.0000 | 1.0000 | 1 | 628638 | 4 | 32145 | B-Lift Cladding Work | [5 empty] | 0.0000