## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work | Selected Group :- C - Common Painting Work
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 636200 | F - Common Painting Work | NA | 0.0000 | 0.0000 | 0 | 512330 | 31 | 0 | [6 empty] | 0.0000
2 | 636201 | F -Lift Duct Painting | NA | 0.0000 | 0.0000 | 1 | 636200 | 31 | 0 | [6 empty] | 0.0000
3 | 636202 | F - Lift 1 Duct Painting Work | NA | 0.0000 | 0.0000 | 2 | 636201 | 31 | 0 | [6 empty] | 0.0000
4 | 636203 | F -GF Lift 1 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 3 | 636202 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
5 | 636204 | F -1st Floor Lift 1 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 3 | 636202 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
6 | 636205 | F -2nd Floor Lift 1 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 3 | 636202 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
7 | 636206 | F -3rd Floor Lift 1 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 3 | 636202 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
8 | 636207 | F -4th Floor Lift 1 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 3 | 636202 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
9 | 636208 | F -5th Floor Lift 1 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 3 | 636202 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
10 | 636209 | F -6th Floor Lift 1 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 3 | 636202 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
11 | 636210 | F -7th Floor Lift 1 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 3 | 636202 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
12 | 636211 | F -8th Floor Lift 1 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 3 | 636202 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
13 | 636212 | F -9th Floor Lift 1 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 3 | 636202 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
14 | 636213 | F -10th Floor Lift 1 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 3 | 636202 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
15 | 636214 | F -11th Floor Lift 1 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 3 | 636202 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
16 | 636215 | F -12th Floor Lift 1 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 3 | 636202 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
17 | 636216 | F -13th Floor Lift 1 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 3 | 636202 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
18 | 636217 | F -14th Floor Lift 1 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 3 | 636202 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
19 | 636218 | F -Terrace Lift 1 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 3 | 636202 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
20 | 636219 | F - Lift 2 Duct Painting Work | NA | 0.0000 | 0.0000 | 2 | 636201 | 31 | 0 | [6 empty] | 0.0000
21 | 636220 | F -GF Lift 2 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 20 | 636219 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
22 | 636221 | F -1st Floor Lift 2 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 20 | 636219 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
23 | 636222 | F -2nd Floor Lift 2 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 20 | 636219 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
24 | 636223 | F -3rd Floor Lift 2 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 20 | 636219 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
25 | 636224 | F -4th Floor Lift 2 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 20 | 636219 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
26 | 636225 | F -5th Floor Lift 2 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 20 | 636219 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
27 | 636226 | F -6th Floor Lift 2 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 20 | 636219 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
28 | 636227 | F -7th Floor Lift 2 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 20 | 636219 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
29 | 636228 | F -8th Floor Lift 2 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 20 | 636219 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
30 | 636229 | F -9th Floor Lift 2 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 20 | 636219 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
31 | 636230 | F -10th Floor Lift 2 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 20 | 636219 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
32 | 636231 | F -11th Floor Lift 2 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 20 | 636219 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
33 | 636232 | F -12th Floor Lift 2 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 20 | 636219 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
34 | 636233 | F -13th Floor Lift 2 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 20 | 636219 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
35 | 636234 | F -14th Floor Lift 2 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 20 | 636219 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
36 | 636235 | F -Terrace Lift 2 Duct Painting Work | Sq.Ft | 240.7153 | 240.7153 | 20 | 636219 | 4 | 31254 | A-GF Lift Duct Painting Work | [5 empty] | 0.0000
37 | 636236 | F -External Painting Work | NA | 0.0000 | 0.0000 | 1 | 636200 | 31 | 0 | [6 empty] | 0.0000
38 | 636237 | F - West Side External painting Work | NA | 0.0000 | 0.0000 | 37 | 636236 | 31 | 0 | [6 empty] | 0.0000
39 | 636238 | F - West Side GF External Painting Work | Sq.Ft | 339.9380 | 339.9380 | 38 | 636237 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
40 | 636239 | F - West Side 1st Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 38 | 636237 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
41 | 636240 | F - West Side 2nd Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 38 | 636237 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
42 | 636241 | F - West Side 3rd Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 38 | 636237 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
43 | 636242 | F - West Side 4th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 38 | 636237 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
44 | 636243 | F - West Side 5th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 38 | 636237 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
45 | 636244 | F - West Side 6th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 38 | 636237 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
46 | 636245 | F - West Side 7th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 38 | 636237 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
47 | 636246 | F - West Side 8th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 38 | 636237 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
48 | 636247 | F - West Side 9th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 38 | 636237 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
49 | 636248 | F - West Side 10th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 38 | 636237 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
50 | 636249 | F - West Side 11th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 38 | 636237 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
51 | 636250 | F - West Side 12th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 38 | 636237 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
52 | 636251 | F - West Side 13th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 38 | 636237 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
53 | 636252 | F - West Side 14th Floor External Painting Work | Sq.Ft | 437.2620 | 437.2620 | 38 | 636237 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
54 | 636253 | F - West Side Terrace Floor External Painting Work | Sq.Ft | 1633.4050 | 1633.4050 | 38 | 636237 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
55 | 636254 | F - East Side External painting Work | NA | 0.0000 | 0.0000 | 37 | 636236 | 31 | 0 | [6 empty] | 0.0000
56 | 636255 | F - East Side GF External Painting Work | Sq.Ft | 413.6070 | 413.6070 | 55 | 636254 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
57 | 636256 | F - East Side 1st Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 55 | 636254 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
58 | 636257 | F - East Side 2nd Floor External Painting Work | Sq.Ft | 467.1150 | 467.1150 | 55 | 636254 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
59 | 636258 | F - East Side 3rd Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 55 | 636254 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
60 | 636259 | F - East Side 4th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 55 | 636254 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
61 | 636260 | F - East Side 5th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 55 | 636254 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
62 | 636261 | F - East Side 6th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 55 | 636254 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
63 | 636262 | F - East Side 7th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 55 | 636254 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
64 | 636263 | F - East Side 8th Floor External Painting Work | Sq.Ft | 638.5700 | 638.5700 | 55 | 636254 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
65 | 636264 | F - East Side 9th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 55 | 636254 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
66 | 636265 | F - East Side 10th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 55 | 636254 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
67 | 636266 | F - East Side 11th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 55 | 636254 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
68 | 636267 | F - East Side 12th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 55 | 636254 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
69 | 636268 | F - East Side 13th Floor External Painting Work | Sq.Ft | 638.5700 | 638.5700 | 55 | 636254 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
70 | 636269 | F - East Side 14th Floor External Painting Work | Sq.Ft | 649.5160 | 649.5160 | 55 | 636254 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
71 | 636270 | F - East Side Terrace Floor External Painting Work | Sq.Ft | 834.6620 | 834.6620 | 55 | 636254 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
72 | 636271 | F - North Side External painting Work | NA | 0.0000 | 0.0000 | 37 | 636236 | 31 | 0 | [6 empty] | 0.0000
73 | 636272 | F - North Side GF External Painting Work | Sq.Ft | 353.0480 | 353.0480 | 72 | 636271 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
74 | 636273 | F - North Side 1st Floor External Painting Work | Sq.Ft | 1529.0690 | 1529.0690 | 72 | 636271 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
75 | 636274 | F - North Side 2nd Floor External Painting Work | Sq.Ft | 1529.0690 | 1529.0690 | 72 | 636271 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
76 | 636275 | F - North Side 3rd Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 72 | 636271 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
77 | 636276 | F - North Side 4th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 72 | 636271 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
78 | 636277 | F - North Side 5th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 72 | 636271 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
79 | 636278 | F - North Side 6th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 72 | 636271 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
80 | 636279 | F - North Side 7th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 72 | 636271 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
81 | 636280 | F - North Side 8th Floor External Painting Work | Sq.Ft | 2070.2730 | 2070.2730 | 72 | 636271 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
82 | 636281 | F - North Side 9th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 72 | 636271 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
83 | 636282 | F - North Side 10th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 72 | 636271 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
84 | 636283 | F - North Side 11th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 72 | 636271 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
85 | 636284 | F - North Side 12th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 72 | 636271 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
86 | 636285 | F - North Side 13th Floor External Painting Work | Sq.Ft | 2070.2730 | 2070.2730 | 72 | 636271 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
87 | 636286 | F - North Side 14th Floor External Painting Work | Sq.Ft | 2020.0240 | 2020.0240 | 72 | 636271 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
88 | 636287 | F - North Side Terrace Floor External Painting Work | Sq.Ft | 2100.5300 | 2100.5300 | 72 | 636271 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
89 | 636288 | F - South Side External painting Work | NA | 0.0000 | 0.0000 | 37 | 636236 | 31 | 0 | [6 empty] | 0.0000
90 | 636289 | F - South Side GF External Painting Work | Sq.Ft | 462.6150 | 462.6150 | 89 | 636288 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
91 | 636290 | F - South Side 1st Floor External Painting Work | Sq.Ft | 1498.1870 | 1498.1870 | 89 | 636288 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
92 | 636291 | F - South Side 2nd Floor External Painting Work | Sq.Ft | 1517.5630 | 1517.5630 | 89 | 636288 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
93 | 636292 | F - South Side 3rd Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 89 | 636288 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
94 | 636293 | F - South Side 4th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 89 | 636288 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
95 | 636294 | F - South Side 5th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 89 | 636288 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
96 | 636295 | F - South Side 6th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 89 | 636288 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
97 | 636296 | F - South Side 7th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 89 | 636288 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
98 | 636297 | F - South Side 8th Floor External Painting Work | Sq.Ft | 1972.7840 | 1972.7840 | 89 | 636288 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
99 | 636298 | F - South Side 9th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 89 | 636288 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
100 | 636299 | F - South Side 10th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 89 | 636288 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
101 | 636300 | F - South Side 11th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 89 | 636288 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
102 | 636301 | F - South Side 12th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 89 | 636288 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
103 | 636302 | F - South Side 13th Floor External Painting Work | Sq.Ft | 1972.7840 | 1972.7840 | 89 | 636288 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
104 | 636303 | F - South Side 14th Floor External Painting Work | Sq.Ft | 1922.6310 | 1922.6310 | 89 | 636288 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
105 | 636304 | F - South Side Terrace Floor External Painting Work | Sq.Ft | 1996.4210 | 1996.4210 | 89 | 636288 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
106 | 636305 | F - Plumbing Duct Painting | NA | 0.0000 | 0.0000 | 1 | 636200 | 31 | 0 | [6 empty] | 0.0000
107 | 636306 | F -Duct 6 External painting Work | NA | 0.0000 | 0.0000 | 106 | 636305 | 31 | 0 | [6 empty] | 0.0000
108 | 636307 | F -1st Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 107 | 636306 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
109 | 636308 | F -2nd Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 107 | 636306 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
110 | 636309 | F -3rd Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 107 | 636306 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
111 | 636310 | F -4th External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 107 | 636306 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
112 | 636311 | F -5th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 107 | 636306 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
113 | 636312 | F -6th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 107 | 636306 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
114 | 636313 | F -7th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 107 | 636306 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
115 | 636314 | F -8th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 107 | 636306 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
116 | 636315 | F -9th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 107 | 636306 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
117 | 636316 | F -10th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 107 | 636306 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
118 | 636317 | F -11th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 107 | 636306 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
119 | 636318 | F -12th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 107 | 636306 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
120 | 636319 | F -13th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 107 | 636306 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
121 | 636320 | F -14th Floor External Duct Painting Work | Sq.Ft | 2106.9240 | 2106.9240 | 107 | 636306 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
122 | 636321 | F - Terrace Floor External Duct Painting Work | Sq.Ft | 2004.1710 | 2004.1710 | 107 | 636306 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000
123 | 636322 | F - Electrical Duct Painting | NA | 0.0000 | 0.0000 | 1 | 636200 | 31 | 0 | [6 empty] | 0.0000
124 | 636323 | F - Electrical Duct 1 Painting Work | NA | 0.0000 | 0.0000 | 123 | 636322 | 31 | 0 | [6 empty] | 0.0000
125 | 636324 | F -GF Electrical Duct 1 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 124 | 636323 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
126 | 636325 | F -1st Floor Electrical Duct 1 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 124 | 636323 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
127 | 636326 | F -2nd Floor Electrical Duct 1 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 124 | 636323 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
128 | 636327 | F -3rd Floor Electrical Duct 1 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 124 | 636323 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
129 | 636328 | F -4th Floor Electrical Duct 1 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 124 | 636323 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
130 | 636329 | F -5th Floor Electrical Duct 1 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 124 | 636323 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
131 | 636330 | F -6th Floor Electrical Duct 1 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 124 | 636323 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
132 | 636331 | F -7th Floor Electrical Duct 1 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 124 | 636323 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
133 | 636332 | F -8th Floor Electrical Duct 1 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 124 | 636323 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
134 | 636333 | F -9th Floor Electrical Duct 1 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 124 | 636323 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
135 | 636334 | F -10th Floor Electrical Duct 1 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 124 | 636323 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
136 | 636335 | F -11th Floor Electrical Duct 1 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 124 | 636323 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
137 | 636336 | F -12th Floor Electrical Duct 1 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 124 | 636323 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
138 | 636337 | F -13th Floor Electrical Duct 1 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 124 | 636323 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
139 | 636338 | F -14th Floor Electrical Duct 1 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 124 | 636323 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
140 | 636355 | F - Terrace Floor Electrical Duct 1 Painting Work | Sq.Ft | 211.5771 | 211.5771 | 124 | 636323 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
141 | 636339 | F - Electrical Duct 2 Painting Work | NA | 0.0000 | 0.0000 | 123 | 636322 | 31 | 0 | [6 empty] | 0.0000
142 | 636340 | F -GF Electrical Duct 2 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 141 | 636339 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
143 | 636341 | F -1st Floor Electrical Duct 2 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 141 | 636339 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
144 | 636342 | F -2nd Floor Electrical Duct 2 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 141 | 636339 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
145 | 636343 | F -3rd Floor Electrical Duct 2 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 141 | 636339 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
146 | 636344 | F -4th Floor Electrical Duct 2 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 141 | 636339 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
147 | 636345 | F -5th Floor Electrical Duct 2 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 141 | 636339 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
148 | 636346 | F -6th Floor Electrical Duct 2 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 141 | 636339 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
149 | 636347 | F -7th Floor Electrical Duct 2 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 141 | 636339 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
150 | 636348 | F -8th Floor Electrical Duct 2 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 141 | 636339 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
151 | 636349 | F -9th Floor Electrical Duct 2 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 141 | 636339 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
152 | 636350 | F -10th Floor Electrical Duct 2 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 141 | 636339 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
153 | 636351 | F -11th Floor Electrical Duct 2 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 141 | 636339 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
154 | 636352 | F -12th Floor Electrical Duct 2 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 141 | 636339 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
155 | 636353 | F -13th Floor Electrical Duct 2 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 141 | 636339 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
156 | 636354 | F -14th Floor Electrical Duct 2 Painting Work | Sq.Ft | 219.4564 | 219.4564 | 141 | 636339 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
157 | 636356 | F - Terrace Floor Electrical Duct 2 Painting Work | Sq.Ft | 211.5771 | 211.5771 | 141 | 636339 | 4 | 31253 | A-GF Electrical Duct Painting Work | [5 empty] | 0.0000
158 | 636357 | F - Fire Duct Painting | NA | 0.0000 | 0.0000 | 1 | 636200 | 31 | 0 | [6 empty] | 0.0000
159 | 636358 | F -Fire Duct 1 Painting Work | NA | 0.0000 | 0.0000 | 158 | 636357 | 31 | 0 | [6 empty] | 0.0000
160 | 636359 | F -GF Fire Duct 1 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 159 | 636358 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
161 | 636360 | F -1st Floor Fire Duct 1 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 159 | 636358 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
162 | 636361 | F -2nd Floor Fire Duct 1 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 159 | 636358 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
163 | 636362 | F -3rd Floor Fire Duct 1 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 159 | 636358 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
164 | 636363 | F -4th Floor Fire Duct 1 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 159 | 636358 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
165 | 636364 | F -5th Floor Fire Duct 1 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 159 | 636358 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
166 | 636365 | F -6th Floor Fire Duct 1 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 159 | 636358 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
167 | 636366 | F -7th Floor Fire Duct 1 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 159 | 636358 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
168 | 636367 | F -8th Floor Fire Duct 1 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 159 | 636358 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
169 | 636368 | F -9th Floor Fire Duct 1 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 159 | 636358 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
170 | 636369 | F -10th Floor Fire Duct 1 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 159 | 636358 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
171 | 636370 | F -11th Floor Fire Duct 1 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 159 | 636358 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
172 | 636371 | F -12th Floor Fire Duct 1 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 159 | 636358 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
173 | 636372 | F -13th Floor Fire Duct 1 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 159 | 636358 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
174 | 636373 | F -14th Floor Fire Duct 1 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 159 | 636358 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
175 | 636374 | F -Terrace Floor Fire Duct 1 Painting Work | Sq.Ft | 81.5857 | 81.5857 | 159 | 636358 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
176 | 636375 | F -Fire Duct 2 Painting Work | NA | 0.0000 | 0.0000 | 158 | 636357 | 31 | 0 | [6 empty] | 0.0000
177 | 636376 | F -GF Fire Duct 2 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 176 | 636375 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
178 | 636377 | F -1st Floor Fire Duct 2 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 176 | 636375 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
179 | 636378 | F -2nd Floor Fire Duct 2 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 176 | 636375 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
180 | 636379 | F -3rd Floor Fire Duct 2 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 176 | 636375 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
181 | 636380 | F -4th Floor Fire Duct 2 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 176 | 636375 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
182 | 636381 | F -5th Floor Fire Duct 2 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 176 | 636375 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
183 | 636382 | F -6th Floor Fire Duct 2 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 176 | 636375 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
184 | 636383 | F -7th Floor Fire Duct 2 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 176 | 636375 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
185 | 636384 | F -8th Floor Fire Duct 2 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 176 | 636375 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
186 | 636385 | F -9th Floor Fire Duct 2 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 176 | 636375 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
187 | 636386 | F -10th Floor Fire Duct 2 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 176 | 636375 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
188 | 636387 | F -11th Floor Fire Duct 2 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 176 | 636375 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
189 | 636388 | F -12th Floor Fire Duct 2 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 176 | 636375 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
190 | 636389 | F -13th Floor Fire Duct 2 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 176 | 636375 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
191 | 636390 | F -14th Floor Fire Duct 2 Painting Work | Sq.Ft | 85.6975 | 85.6975 | 176 | 636375 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
192 | 636391 | F -Terrace Floor Fire Duct 2 Painting Work | Sq.Ft | 81.5857 | 81.5857 | 176 | 636375 | 4 | 31255 | A-GF Fire Duct Painting Work | [5 empty] | 0.0000
193 | 636392 | F - LMR & OHWT Painting | NA | 0.0000 | 0.0000 | 1 | 636200 | 31 | 0 | [6 empty] | 0.0000
194 | 636393 | F - LMR & OHWT External Painting Work | Sq.Ft | 2622.9180 | 2622.9180 | 193 | 636392 | 4 | 32117 | A-GF External Painting Work | [5 empty] | 0.0000