## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- D - Common Tilling Work (M) | Selected Group :- D - Common Tilling Work (M) | Selected Group :- D - Common Tilling Work (M) | Selected Group :- D - Common Tilling Work (M) | Selected Group :- D - Common Tilling Work (M) | Selected Group :- D - Common Tilling Work (M) | Selected Group :- D - Common Tilling Work (M) | Selected Group :- D - Common Tilling Work (M) | Selected Group :- D - Common Tilling Work (M) | Selected Group :- D - Common Tilling Work (M) | Selected Group :- D - Common Tilling Work (M) | Selected Group :- D - Common Tilling Work (M) | Selected Group :- D - Common Tilling Work (M) | Selected Group :- D - Common Tilling Work (M) | Selected Group :- D - Common Tilling Work (M) | Selected Group :- D - Common Tilling Work (M) | Selected Group :- D - Common Tilling Work (M)
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 650985 | E - Common Tilling Work (M) | NA | 0.0000 | 0.0000 | 0 | 512344 | 31 | 0 | [6 empty] | 0.0000
2 | 650986 | E - Staircase Landing Flooring work | NA | 0.0000 | 0.0000 | 1 | 650985 | 31 | 0 | [6 empty] | 0.0000
3 | 650987 | E - Staircase 1 | NA | 0.0000 | 0.0000 | 2 | 650986 | 31 | 0 | [6 empty] | 0.0000
4 | 650988 | E - Ground Floor | NA | 0.0000 | 0.0000 | 3 | 650987 | 31 | 0 | [6 empty] | 0.0000
5 | 650989 | E - G.F Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 4 | 650988 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
6 | 650990 | E - G.F Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 4 | 650988 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
7 | 650991 | E - 1st Floor | NA | 0.0000 | 0.0000 | 3 | 650987 | 31 | 0 | [6 empty] | 0.0000
8 | 650992 | E - 1st Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 7 | 650991 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
9 | 650993 | E - 1st Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 7 | 650991 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
10 | 650994 | E - 2nd Floor | NA | 0.0000 | 0.0000 | 3 | 650987 | 31 | 0 | [6 empty] | 0.0000
11 | 650995 | E - 2nd Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 10 | 650994 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
12 | 650996 | E - 2nd Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 650994 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
13 | 650997 | E - 3rd Floor | NA | 0.0000 | 0.0000 | 3 | 650987 | 31 | 0 | [6 empty] | 0.0000
14 | 650998 | E - 3rd Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 13 | 650997 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
15 | 650999 | E - 3rd Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 13 | 650997 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
16 | 651000 | E - 4th Floor | NA | 0.0000 | 0.0000 | 3 | 650987 | 31 | 0 | [6 empty] | 0.0000
17 | 651001 | E - 4th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 16 | 651000 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
18 | 651002 | E - 4th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 16 | 651000 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
19 | 651003 | E - 5th Floor | NA | 0.0000 | 0.0000 | 3 | 650987 | 31 | 0 | [6 empty] | 0.0000
20 | 651004 | E - 5th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 19 | 651003 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
21 | 651005 | E - 5th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 19 | 651003 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
22 | 651025 | E - 6th Floor | NA | 0.0000 | 0.0000 | 3 | 650987 | 31 | 0 | [6 empty] | 0.0000
23 | 651026 | E - 6th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 22 | 651025 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
24 | 651027 | E - 6th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 651025 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
25 | 651028 | E - 7th Floor | NA | 0.0000 | 0.0000 | 3 | 650987 | 31 | 0 | [6 empty] | 0.0000
26 | 651029 | E - 7th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 25 | 651028 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
27 | 651030 | E - 7th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 25 | 651028 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
28 | 651031 | E - 8th Floor | NA | 0.0000 | 0.0000 | 3 | 650987 | 31 | 0 | [6 empty] | 0.0000
29 | 651032 | E - 8th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 28 | 651031 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
30 | 651033 | E - 8th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 28 | 651031 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
31 | 651034 | E - 9th Floor | NA | 0.0000 | 0.0000 | 3 | 650987 | 31 | 0 | [6 empty] | 0.0000
32 | 651035 | E - 9th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 31 | 651034 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
33 | 651036 | E - 9th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 31 | 651034 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
34 | 651037 | E - 10th Floor | NA | 0.0000 | 0.0000 | 3 | 650987 | 31 | 0 | [6 empty] | 0.0000
35 | 651038 | E - 10th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 34 | 651037 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
36 | 651039 | E - 10th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 651037 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
37 | 651040 | E - 11th Floor | NA | 0.0000 | 0.0000 | 3 | 650987 | 31 | 0 | [6 empty] | 0.0000
38 | 651041 | E - 11th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 37 | 651040 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
39 | 651042 | E - 11th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 37 | 651040 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
40 | 651043 | E - 12th Floor | NA | 0.0000 | 0.0000 | 3 | 650987 | 31 | 0 | [6 empty] | 0.0000
41 | 651044 | E - 12th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 40 | 651043 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
42 | 651045 | E - 12th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 40 | 651043 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
43 | 651046 | E - 13th Floor | NA | 0.0000 | 0.0000 | 3 | 650987 | 31 | 0 | [6 empty] | 0.0000
44 | 651047 | E - 13th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 43 | 651046 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
45 | 651048 | E - 13th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 43 | 651046 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
46 | 651049 | E - 14th Floor | NA | 0.0000 | 0.0000 | 3 | 650987 | 31 | 0 | [6 empty] | 0.0000
47 | 651050 | E - 14th Floor Staircase 1 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 46 | 651049 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
48 | 651051 | E - 14th Floor Staircase 1 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 651049 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
49 | 651006 | E - Staircase 2 | NA | 0.0000 | 0.0000 | 2 | 650986 | 31 | 0 | [6 empty] | 0.0000
50 | 651007 | E - Ground Floor | NA | 0.0000 | 0.0000 | 49 | 651006 | 31 | 0 | [6 empty] | 0.0000
51 | 651008 | E - G.F Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 50 | 651007 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
52 | 651009 | E - G.F Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 651007 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
53 | 651010 | E - 1st Floor | NA | 0.0000 | 0.0000 | 49 | 651006 | 31 | 0 | [6 empty] | 0.0000
54 | 651011 | E - 1st Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 53 | 651010 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
55 | 651012 | E - 1st Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 53 | 651010 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
56 | 651013 | E - 2nd Floor | NA | 0.0000 | 0.0000 | 49 | 651006 | 31 | 0 | [6 empty] | 0.0000
57 | 651014 | E - 2nd Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 56 | 651013 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
58 | 651015 | E - 2nd Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 56 | 651013 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
59 | 651016 | E - 3rd Floor | NA | 0.0000 | 0.0000 | 49 | 651006 | 31 | 0 | [6 empty] | 0.0000
60 | 651017 | E - 3rd Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 59 | 651016 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
61 | 651018 | E - 3rd Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 59 | 651016 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
62 | 651019 | E - 4th Floor | NA | 0.0000 | 0.0000 | 49 | 651006 | 31 | 0 | [6 empty] | 0.0000
63 | 651020 | E - 4th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 62 | 651019 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
64 | 651021 | E - 4th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 62 | 651019 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
65 | 651022 | E - 5th Floor | NA | 0.0000 | 0.0000 | 49 | 651006 | 31 | 0 | [6 empty] | 0.0000
66 | 651023 | E - 5th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 65 | 651022 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
67 | 651024 | E - 5th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 65 | 651022 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
68 | 651052 | E - 6th Floor | NA | 0.0000 | 0.0000 | 49 | 651006 | 31 | 0 | [6 empty] | 0.0000
69 | 651053 | E - 6th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 68 | 651052 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
70 | 651054 | E - 6th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 68 | 651052 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
71 | 651055 | E - 7th Floor | NA | 0.0000 | 0.0000 | 49 | 651006 | 31 | 0 | [6 empty] | 0.0000
72 | 651056 | E - 7th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 71 | 651055 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
73 | 651057 | E - 7th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 71 | 651055 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
74 | 651058 | E - 8th Floor | NA | 0.0000 | 0.0000 | 49 | 651006 | 31 | 0 | [6 empty] | 0.0000
75 | 651059 | E - 8th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 74 | 651058 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
76 | 651060 | E - 8th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 74 | 651058 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
77 | 651061 | E - 9th Floor | NA | 0.0000 | 0.0000 | 49 | 651006 | 31 | 0 | [6 empty] | 0.0000
78 | 651062 | E - 9th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 77 | 651061 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
79 | 651063 | E - 9th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 77 | 651061 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
80 | 651064 | E - 10th Floor | NA | 0.0000 | 0.0000 | 49 | 651006 | 31 | 0 | [6 empty] | 0.0000
81 | 651065 | E - 10th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 80 | 651064 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
82 | 651066 | E - 10th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 80 | 651064 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
83 | 651067 | E - 11th Floor | NA | 0.0000 | 0.0000 | 49 | 651006 | 31 | 0 | [6 empty] | 0.0000
84 | 651068 | E - 11th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 83 | 651067 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
85 | 651069 | E - 11th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 83 | 651067 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
86 | 651070 | E - 12th Floor | NA | 0.0000 | 0.0000 | 49 | 651006 | 31 | 0 | [6 empty] | 0.0000
87 | 651071 | E - 12th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 86 | 651070 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
88 | 651072 | E - 12th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 86 | 651070 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
89 | 651073 | E - 13th Floor | NA | 0.0000 | 0.0000 | 49 | 651006 | 31 | 0 | [6 empty] | 0.0000
90 | 651074 | E - 13th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 89 | 651073 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
91 | 651075 | E - 13th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 89 | 651073 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000
92 | 651076 | E - 14th Floor | NA | 0.0000 | 0.0000 | 49 | 651006 | 31 | 0 | [6 empty] | 0.0000
93 | 651077 | E - 14th Floor Staircase 2 Flooring work | Sq.Ft | 1.0000 | 1.0000 | 92 | 651076 | 4 | 33960 | C - G.F Staircase 1 Flooring work | [5 empty] | 0.0000
94 | 651078 | E - 14th Floor Staircase 2 Skirting Work | Sq.Ft | 1.0000 | 1.0000 | 92 | 651076 | 4 | 33961 | C - G.F Staircase 1 Skirting Work | [5 empty] | 0.0000