## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- D - 9th Floor | Selected Group :- D - 9th Floor | Selected Group :- D - 9th Floor | Selected Group :- D - 9th Floor | Selected Group :- D - 9th Floor | Selected Group :- D - 9th Floor | Selected Group :- D - 9th Floor | Selected Group :- D - 9th Floor | Selected Group :- D - 9th Floor | Selected Group :- D - 9th Floor | Selected Group :- D - 9th Floor | Selected Group :- D - 9th Floor | Selected Group :- D - 9th Floor | Selected Group :- D - 9th Floor | Selected Group :- D - 9th Floor | Selected Group :- D - 9th Floor | Selected Group :- D - 9th Floor
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 651571 | D - 9th Floor | NA | 0.0000 | 0.0000 | 0 | 571442 | 31 | 0 | [6 empty] | 0.0000
2 | 651572 | D - Flat No 901 | NA | 0.0000 | 0.0000 | 1 | 651571 | 31 | 0 | [6 empty] | 0.0000
3 | 651573 | D - 901 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 651572 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
4 | 651574 | D - 901 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 651572 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
5 | 651575 | D - 901 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 651572 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
6 | 651576 | D - Flat No 902 | NA | 0.0000 | 0.0000 | 1 | 651571 | 31 | 0 | [6 empty] | 0.0000
7 | 651577 | D . 902 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 651576 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
8 | 651578 | D . 902 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 651576 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
9 | 651579 | D . 902 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 651576 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
10 | 651580 | D - Flat No 903 | NA | 0.0000 | 0.0000 | 1 | 651571 | 31 | 0 | [6 empty] | 0.0000
11 | 651581 | D . 903 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 651580 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
12 | 651582 | D . 903 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 651580 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
13 | 651583 | D . 903 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 651580 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
14 | 651584 | D - Flat No 904 | NA | 0.0000 | 0.0000 | 1 | 651571 | 31 | 0 | [6 empty] | 0.0000
15 | 651585 | D . 904 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 651584 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
16 | 651586 | D . 904 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 651584 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
17 | 651587 | D . 904 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 651584 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
18 | 651588 | D - Flat No 905 | NA | 0.0000 | 0.0000 | 1 | 651571 | 31 | 0 | [6 empty] | 0.0000
19 | 651589 | D . 905 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 651588 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
20 | 651590 | D . 905 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 651588 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
21 | 651591 | D . 905 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 651588 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
22 | 651592 | D - Flat No 906 | NA | 0.0000 | 0.0000 | 1 | 651571 | 31 | 0 | [6 empty] | 0.0000
23 | 651593 | D . 906 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 651592 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
24 | 651594 | D . 906 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 651592 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
25 | 651595 | D . 906 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 651592 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
26 | 651596 | D - Flat No 907 | NA | 0.0000 | 0.0000 | 1 | 651571 | 31 | 0 | [6 empty] | 0.0000
27 | 651597 | D . 907 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 651596 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
28 | 651598 | D . 907 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 651596 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
29 | 651599 | D . 907 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 651596 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
30 | 651600 | D - Flat No 908 | NA | 0.0000 | 0.0000 | 1 | 651571 | 31 | 0 | [6 empty] | 0.0000
31 | 651601 | D . 908 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 651600 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
32 | 651602 | D . 908 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 651600 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
33 | 651603 | D . 908 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 651600 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
34 | 651604 | D - Flat No 909 | NA | 0.0000 | 0.0000 | 1 | 651571 | 31 | 0 | [6 empty] | 0.0000
35 | 651605 | D . 909 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 651604 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
36 | 651606 | D . 909 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 651604 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
37 | 651607 | D . 909 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 651604 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
38 | 651608 | D - Flat No 910 | NA | 0.0000 | 0.0000 | 1 | 651571 | 31 | 0 | [6 empty] | 0.0000
39 | 651609 | D . 910 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 651608 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
40 | 651610 | D . 910 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 651608 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
41 | 651611 | D . 910 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 651608 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
42 | 651612 | D - Flat No 911 | NA | 0.0000 | 0.0000 | 1 | 651571 | 31 | 0 | [6 empty] | 0.0000
43 | 651613 | D . 911 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 42 | 651612 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
44 | 651614 | D . 911 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 42 | 651612 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
45 | 651615 | D . 911 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 42 | 651612 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
46 | 651616 | D - Flat No 912 | NA | 0.0000 | 0.0000 | 1 | 651571 | 31 | 0 | [6 empty] | 0.0000
47 | 651617 | D . 912 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 651616 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
48 | 651618 | D . 912 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 651616 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
49 | 651619 | D . 912 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 651616 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
50 | 651620 | D - Flat No 913 | NA | 0.0000 | 0.0000 | 1 | 651571 | 31 | 0 | [6 empty] | 0.0000
51 | 651621 | D . 913 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 651620 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
52 | 651622 | D . 913 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 651620 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
53 | 651623 | D . 913 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 651620 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
54 | 651624 | D - Flat No 914 | NA | 0.0000 | 0.0000 | 1 | 651571 | 31 | 0 | [6 empty] | 0.0000
55 | 651625 | D . 914 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 54 | 651624 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
56 | 651626 | D . 914 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 54 | 651624 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
57 | 651627 | D . 914 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 54 | 651624 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000