## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- D - 11th Floor | Selected Group :- D - 11th Floor | Selected Group :- D - 11th Floor | Selected Group :- D - 11th Floor | Selected Group :- D - 11th Floor | Selected Group :- D - 11th Floor | Selected Group :- D - 11th Floor | Selected Group :- D - 11th Floor | Selected Group :- D - 11th Floor | Selected Group :- D - 11th Floor | Selected Group :- D - 11th Floor | Selected Group :- D - 11th Floor | Selected Group :- D - 11th Floor | Selected Group :- D - 11th Floor | Selected Group :- D - 11th Floor | Selected Group :- D - 11th Floor | Selected Group :- D - 11th Floor
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 651685 | D - 11th Floor | NA | 0.0000 | 0.0000 | 0 | 571442 | 31 | 0 | [6 empty] | 0.0000
2 | 651686 | D - Flat No 1101 | NA | 0.0000 | 0.0000 | 1 | 651685 | 31 | 0 | [6 empty] | 0.0000
3 | 651687 | D - 1101 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 651686 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
4 | 651688 | D - 1101 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 651686 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
5 | 651689 | D - 1101 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 651686 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
6 | 651690 | D - Flat No 1102 | NA | 0.0000 | 0.0000 | 1 | 651685 | 31 | 0 | [6 empty] | 0.0000
7 | 651691 | D . 1102 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 651690 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
8 | 651692 | D . 1102 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 651690 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
9 | 651693 | D . 1102 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 651690 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
10 | 651694 | D - Flat No 1103 | NA | 0.0000 | 0.0000 | 1 | 651685 | 31 | 0 | [6 empty] | 0.0000
11 | 651695 | D . 1103 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 651694 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
12 | 651696 | D . 1103 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 651694 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
13 | 651697 | D . 1103 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 651694 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
14 | 651698 | D - Flat No 1104 | NA | 0.0000 | 0.0000 | 1 | 651685 | 31 | 0 | [6 empty] | 0.0000
15 | 651699 | D . 1104 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 651698 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
16 | 651700 | D . 1104 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 651698 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
17 | 651701 | D . 1104 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 651698 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
18 | 651702 | D - Flat No 1105 | NA | 0.0000 | 0.0000 | 1 | 651685 | 31 | 0 | [6 empty] | 0.0000
19 | 651703 | D . 1105 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 651702 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
20 | 651704 | D . 1105 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 651702 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
21 | 651705 | D . 1105 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 651702 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
22 | 651706 | D - Flat No 1106 | NA | 0.0000 | 0.0000 | 1 | 651685 | 31 | 0 | [6 empty] | 0.0000
23 | 651707 | D . 1106 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 651706 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
24 | 651708 | D . 1106 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 651706 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
25 | 651709 | D . 1106 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 651706 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
26 | 651710 | D - Flat No 1107 | NA | 0.0000 | 0.0000 | 1 | 651685 | 31 | 0 | [6 empty] | 0.0000
27 | 651711 | D . 1107 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 651710 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
28 | 651712 | D . 1107 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 651710 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
29 | 651713 | D . 1107 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 651710 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
30 | 651714 | D - Flat No 1108 | NA | 0.0000 | 0.0000 | 1 | 651685 | 31 | 0 | [6 empty] | 0.0000
31 | 651715 | D . 1108 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 651714 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
32 | 651716 | D . 1108 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 651714 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
33 | 651717 | D . 1108 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 651714 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
34 | 651718 | D - Flat No 1109 | NA | 0.0000 | 0.0000 | 1 | 651685 | 31 | 0 | [6 empty] | 0.0000
35 | 651719 | D . 1109 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 651718 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
36 | 651720 | D . 1109 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 651718 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
37 | 651721 | D . 1109 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 651718 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
38 | 651722 | D - Flat No 1110 | NA | 0.0000 | 0.0000 | 1 | 651685 | 31 | 0 | [6 empty] | 0.0000
39 | 651723 | D . 1110 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 651722 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
40 | 651724 | D . 1110 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 651722 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
41 | 651725 | D . 1110 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 651722 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
42 | 651726 | D - Flat No 1111 | NA | 0.0000 | 0.0000 | 1 | 651685 | 31 | 0 | [6 empty] | 0.0000
43 | 651727 | D . 1111 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 42 | 651726 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
44 | 651728 | D . 1111 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 42 | 651726 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
45 | 651729 | D . 1111 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 42 | 651726 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
46 | 651730 | D - Flat No 1112 | NA | 0.0000 | 0.0000 | 1 | 651685 | 31 | 0 | [6 empty] | 0.0000
47 | 651731 | D . 1112 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 651730 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
48 | 651732 | D . 1112 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 651730 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
49 | 651733 | D . 1112 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 651730 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
50 | 651734 | D - Flat No 1113 | NA | 0.0000 | 0.0000 | 1 | 651685 | 31 | 0 | [6 empty] | 0.0000
51 | 651735 | D . 1113 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 651734 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
52 | 651736 | D . 1113 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 651734 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
53 | 651737 | D . 1113 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 651734 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
54 | 651738 | D - Flat No 1114 | NA | 0.0000 | 0.0000 | 1 | 651685 | 31 | 0 | [6 empty] | 0.0000
55 | 651739 | D . 1114 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 54 | 651738 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
56 | 651740 | D . 1114 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 54 | 651738 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
57 | 651741 | D . 1114 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 54 | 651738 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000