## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- E - 9th Floor | Selected Group :- E - 9th Floor | Selected Group :- E - 9th Floor | Selected Group :- E - 9th Floor | Selected Group :- E - 9th Floor | Selected Group :- E - 9th Floor | Selected Group :- E - 9th Floor | Selected Group :- E - 9th Floor | Selected Group :- E - 9th Floor | Selected Group :- E - 9th Floor | Selected Group :- E - 9th Floor | Selected Group :- E - 9th Floor | Selected Group :- E - 9th Floor | Selected Group :- E - 9th Floor | Selected Group :- E - 9th Floor | Selected Group :- E - 9th Floor | Selected Group :- E - 9th Floor
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 651996 | E - 9th Floor | NA | 0.0000 | 0.0000 | 0 | 588355 | 31 | 0 | [6 empty] | 0.0000
2 | 651997 | E - Flat No 901 | NA | 0.0000 | 0.0000 | 1 | 651996 | 31 | 0 | [6 empty] | 0.0000
3 | 651998 | E - 901 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 651997 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
4 | 651999 | E - 901 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 651997 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
5 | 652000 | E - 901 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 651997 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
6 | 652001 | E - Flat No 902 | NA | 0.0000 | 0.0000 | 1 | 651996 | 31 | 0 | [6 empty] | 0.0000
7 | 652002 | E . 902 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 652001 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
8 | 652003 | E . 902 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 652001 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
9 | 652004 | E . 902 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 652001 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
10 | 652005 | E - Flat No 903 | NA | 0.0000 | 0.0000 | 1 | 651996 | 31 | 0 | [6 empty] | 0.0000
11 | 652006 | E . 903 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 652005 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
12 | 652007 | E . 903 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 652005 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
13 | 652008 | E . 903 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 652005 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
14 | 652009 | E - Flat No 904 | NA | 0.0000 | 0.0000 | 1 | 651996 | 31 | 0 | [6 empty] | 0.0000
15 | 652010 | E . 904 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 652009 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
16 | 652011 | E . 904 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 652009 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
17 | 652012 | E . 904 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 652009 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
18 | 652013 | E - Flat No 905 | NA | 0.0000 | 0.0000 | 1 | 651996 | 31 | 0 | [6 empty] | 0.0000
19 | 652014 | E . 905 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 652013 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
20 | 652015 | E . 905 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 652013 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
21 | 652016 | E . 905 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 652013 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
22 | 652017 | E - Flat No 906 | NA | 0.0000 | 0.0000 | 1 | 651996 | 31 | 0 | [6 empty] | 0.0000
23 | 652018 | E . 906 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 652017 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
24 | 652019 | E . 906 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 652017 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
25 | 652020 | E . 906 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 652017 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
26 | 652021 | E - Flat No 907 | NA | 0.0000 | 0.0000 | 1 | 651996 | 31 | 0 | [6 empty] | 0.0000
27 | 652022 | E . 907 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 652021 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
28 | 652023 | E . 907 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 652021 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
29 | 652024 | E . 907 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 652021 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
30 | 652025 | E - Flat No 908 | NA | 0.0000 | 0.0000 | 1 | 651996 | 31 | 0 | [6 empty] | 0.0000
31 | 652026 | E . 908 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 652025 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
32 | 652027 | E . 908 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 652025 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
33 | 652028 | E . 908 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 652025 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
34 | 652029 | E - Flat No 909 | NA | 0.0000 | 0.0000 | 1 | 651996 | 31 | 0 | [6 empty] | 0.0000
35 | 652030 | E . 909 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 652029 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
36 | 652031 | E . 909 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 652029 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
37 | 652032 | E . 909 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 652029 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
38 | 652033 | E - Flat No 910 | NA | 0.0000 | 0.0000 | 1 | 651996 | 31 | 0 | [6 empty] | 0.0000
39 | 652034 | E . 910 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 652033 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
40 | 652035 | E . 910 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 652033 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
41 | 652036 | E . 910 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 652033 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
42 | 652037 | E - Flat No 911 | NA | 0.0000 | 0.0000 | 1 | 651996 | 31 | 0 | [6 empty] | 0.0000
43 | 652038 | E . 911 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 42 | 652037 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
44 | 652039 | E . 911 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 42 | 652037 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
45 | 652040 | E . 911 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 42 | 652037 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
46 | 652041 | E - Flat No 912 | NA | 0.0000 | 0.0000 | 1 | 651996 | 31 | 0 | [6 empty] | 0.0000
47 | 652042 | E . 912 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 652041 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
48 | 652043 | E . 912 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 652041 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
49 | 652044 | E . 912 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 652041 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
50 | 652045 | E - Flat No 913 | NA | 0.0000 | 0.0000 | 1 | 651996 | 31 | 0 | [6 empty] | 0.0000
51 | 652046 | E . 913 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 652045 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
52 | 652047 | E . 913 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 652045 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
53 | 652048 | E . 913 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 652045 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
54 | 652049 | E - Flat No 914 | NA | 0.0000 | 0.0000 | 1 | 651996 | 31 | 0 | [6 empty] | 0.0000
55 | 652050 | E . 914 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 54 | 652049 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
56 | 652051 | E . 914 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 54 | 652049 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
57 | 652052 | E . 914 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 54 | 652049 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000