## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- E - 13th Floor | Selected Group :- E - 13th Floor | Selected Group :- E - 13th Floor | Selected Group :- E - 13th Floor | Selected Group :- E - 13th Floor | Selected Group :- E - 13th Floor | Selected Group :- E - 13th Floor | Selected Group :- E - 13th Floor | Selected Group :- E - 13th Floor | Selected Group :- E - 13th Floor | Selected Group :- E - 13th Floor | Selected Group :- E - 13th Floor | Selected Group :- E - 13th Floor | Selected Group :- E - 13th Floor | Selected Group :- E - 13th Floor | Selected Group :- E - 13th Floor | Selected Group :- E - 13th Floor
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 652094 | E - 13th Floor | NA | 0.0000 | 0.0000 | 0 | 588355 | 31 | 0 | [6 empty] | 0.0000
2 | 652095 | E - Flat No 1301 | NA | 0.0000 | 0.0000 | 1 | 652094 | 31 | 0 | [6 empty] | 0.0000
3 | 652096 | E - 1301 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 652095 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
4 | 652097 | E - 1301 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 652095 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
5 | 652098 | E - 1301 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 652095 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
6 | 652099 | E - Flat No 1302 | NA | 0.0000 | 0.0000 | 1 | 652094 | 31 | 0 | [6 empty] | 0.0000
7 | 652100 | E . 1302 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 652099 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
8 | 652101 | E . 1302 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 652099 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
9 | 652102 | E . 1302 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 652099 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
10 | 652103 | E - Flat No 1303 | NA | 0.0000 | 0.0000 | 1 | 652094 | 31 | 0 | [6 empty] | 0.0000
11 | 652104 | E . 1303 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 652103 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
12 | 652105 | E . 1303 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 652103 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
13 | 652106 | E . 1303 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 652103 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
14 | 652107 | E - Flat No 1304 | NA | 0.0000 | 0.0000 | 1 | 652094 | 31 | 0 | [6 empty] | 0.0000
15 | 652108 | E . 1304 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 652107 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
16 | 652109 | E . 1304 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 652107 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
17 | 652110 | E . 1304 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 652107 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
18 | 652111 | E - Flat No 1305 | NA | 0.0000 | 0.0000 | 1 | 652094 | 31 | 0 | [6 empty] | 0.0000
19 | 652112 | E . 1305 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 652111 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
20 | 652113 | E . 1305 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 652111 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
21 | 652114 | E . 1305 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 652111 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
22 | 652115 | E - Flat No 1310 | NA | 0.0000 | 0.0000 | 1 | 652094 | 31 | 0 | [6 empty] | 0.0000
23 | 652116 | E . 1310 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 652115 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
24 | 652117 | E . 1310 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 652115 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
25 | 652118 | E . 1310 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 652115 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
26 | 652119 | E - Flat No 1311 | NA | 0.0000 | 0.0000 | 1 | 652094 | 31 | 0 | [6 empty] | 0.0000
27 | 652120 | E . 1311 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 652119 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
28 | 652121 | E . 1311 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 652119 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
29 | 652122 | E . 1311 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 652119 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
30 | 652123 | E - Flat No 1312 | NA | 0.0000 | 0.0000 | 1 | 652094 | 31 | 0 | [6 empty] | 0.0000
31 | 652124 | E . 1312 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 652123 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
32 | 652125 | E . 1312 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 652123 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
33 | 652126 | E . 1312 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 652123 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
34 | 652127 | E - Flat No 1313 | NA | 0.0000 | 0.0000 | 1 | 652094 | 31 | 0 | [6 empty] | 0.0000
35 | 652128 | E . 1313 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 652127 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
36 | 652129 | E . 1313 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 652127 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
37 | 652130 | E . 1313 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 652127 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
38 | 652131 | E - Flat No 1314 | NA | 0.0000 | 0.0000 | 1 | 652094 | 31 | 0 | [6 empty] | 0.0000
39 | 652132 | E . 1314 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 652131 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
40 | 652133 | E . 1314 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 652131 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
41 | 652134 | E . 1314 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 652131 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000