## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- E - 14th Floor | Selected Group :- E - 14th Floor | Selected Group :- E - 14th Floor | Selected Group :- E - 14th Floor | Selected Group :- E - 14th Floor | Selected Group :- E - 14th Floor | Selected Group :- E - 14th Floor | Selected Group :- E - 14th Floor | Selected Group :- E - 14th Floor | Selected Group :- E - 14th Floor | Selected Group :- E - 14th Floor | Selected Group :- E - 14th Floor | Selected Group :- E - 14th Floor | Selected Group :- E - 14th Floor | Selected Group :- E - 14th Floor | Selected Group :- E - 14th Floor | Selected Group :- E - 14th Floor
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 652566 | E - 14th Floor | NA | 0.0000 | 0.0000 | 0 | 588355 | 31 | 0 | [6 empty] | 0.0000
2 | 652567 | E - Flat No 1401 | NA | 0.0000 | 0.0000 | 1 | 652566 | 31 | 0 | [6 empty] | 0.0000
3 | 652568 | E - 1401 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 652567 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
4 | 652569 | E - 1401 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 652567 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
5 | 652570 | E - 1401 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 2 | 652567 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
6 | 652571 | E - Flat No 1402 | NA | 0.0000 | 0.0000 | 1 | 652566 | 31 | 0 | [6 empty] | 0.0000
7 | 652572 | E . 1402 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 652571 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
8 | 652573 | E . 1402 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 652571 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
9 | 652574 | E . 1402 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 6 | 652571 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
10 | 652575 | E - Flat No 1403 | NA | 0.0000 | 0.0000 | 1 | 652566 | 31 | 0 | [6 empty] | 0.0000
11 | 652576 | E . 1403 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 652575 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
12 | 652577 | E . 1403 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 652575 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
13 | 652578 | E . 1403 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 10 | 652575 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
14 | 652579 | E - Flat No 1404 | NA | 0.0000 | 0.0000 | 1 | 652566 | 31 | 0 | [6 empty] | 0.0000
15 | 652580 | E . 1404 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 652579 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
16 | 652581 | E . 1404 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 652579 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
17 | 652582 | E . 1404 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 14 | 652579 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
18 | 652583 | E - Flat No 1405 | NA | 0.0000 | 0.0000 | 1 | 652566 | 31 | 0 | [6 empty] | 0.0000
19 | 652584 | E . 1405 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 652583 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
20 | 652585 | E . 1405 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 652583 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
21 | 652586 | E . 1405 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 18 | 652583 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
22 | 652587 | E - Flat No 1406 | NA | 0.0000 | 0.0000 | 1 | 652566 | 31 | 0 | [6 empty] | 0.0000
23 | 652588 | E . 1406 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 652587 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
24 | 652589 | E . 1406 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 652587 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
25 | 652590 | E . 1406 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 22 | 652587 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
26 | 652591 | E - Flat No 1407 | NA | 0.0000 | 0.0000 | 1 | 652566 | 31 | 0 | [6 empty] | 0.0000
27 | 652592 | E . 1407 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 652591 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
28 | 652593 | E . 1407 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 652591 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
29 | 652594 | E . 1407 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 26 | 652591 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
30 | 652595 | E - Flat No 1408 | NA | 0.0000 | 0.0000 | 1 | 652566 | 31 | 0 | [6 empty] | 0.0000
31 | 652596 | E . 1408 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 652595 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
32 | 652597 | E . 1408 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 652595 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
33 | 652598 | E . 1408 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 30 | 652595 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
34 | 652599 | E - Flat No 1409 | NA | 0.0000 | 0.0000 | 1 | 652566 | 31 | 0 | [6 empty] | 0.0000
35 | 652600 | E . 1409 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 652599 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
36 | 652601 | E . 1409 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 652599 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
37 | 652602 | E . 1409 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 34 | 652599 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
38 | 652603 | E - Flat No 1410 | NA | 0.0000 | 0.0000 | 1 | 652566 | 31 | 0 | [6 empty] | 0.0000
39 | 652604 | E . 1410 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 652603 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
40 | 652605 | E . 1410 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 652603 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
41 | 652606 | E . 1410 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 38 | 652603 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
42 | 652607 | E - Flat No 1411 | NA | 0.0000 | 0.0000 | 1 | 652566 | 31 | 0 | [6 empty] | 0.0000
43 | 652608 | E . 1411 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 42 | 652607 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
44 | 652609 | E . 1411 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 42 | 652607 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
45 | 652610 | E . 1411 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 42 | 652607 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
46 | 652611 | E - Flat No 1412 | NA | 0.0000 | 0.0000 | 1 | 652566 | 31 | 0 | [6 empty] | 0.0000
47 | 652612 | E . 1412 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 652611 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
48 | 652613 | E . 1412 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 652611 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
49 | 652614 | E . 1412 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 46 | 652611 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
50 | 652615 | E - Flat No 1413 | NA | 0.0000 | 0.0000 | 1 | 652566 | 31 | 0 | [6 empty] | 0.0000
51 | 652616 | E . 1413 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 652615 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
52 | 652617 | E . 1413 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 652615 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
53 | 652618 | E . 1413 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 50 | 652615 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000
54 | 652619 | E - Flat No 1414 | NA | 0.0000 | 0.0000 | 1 | 652566 | 31 | 0 | [6 empty] | 0.0000
55 | 652620 | E . 1414 Balcony Waterproofing Work | Sq.Ft | 1.0000 | 1.0000 | 54 | 652619 | 4 | 33981 | D - 401 Balcony Waterproofing Work | [5 empty] | 0.0000
56 | 652621 | E . 1414 Bath & WC W/P Work | Sq.Ft | 1.0000 | 1.0000 | 54 | 652619 | 4 | 33982 | D - 401 Bath & WC W/P Work | [5 empty] | 0.0000
57 | 652622 | E . 1414 Internal Flat Floor Grouting Work | Sq.Ft | 1.0000 | 1.0000 | 54 | 652619 | 4 | 33983 | D - 401 Internal Flat Floor Grouting Wor | [5 empty] | 0.0000