## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L) | Selected Group :- D - Staircase Riser Plaster (L)
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 664262 | F - Staircase Riser Plaster (L) | NA | 0.0000 | 0.0000 | 0 | 601575 | 31 | 0 | [6 empty] | 0.0000
2 | 664263 | F -Staircase 1 | NA | 0.0000 | 0.0000 | 1 | 664262 | 31 | 0 | [6 empty] | 0.0000
3 | 664264 | F - 1st Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 664263 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
4 | 664265 | F - 2nd Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 664263 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
5 | 664266 | F - 3rd Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 664263 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
6 | 664267 | F - 4th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 664263 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
7 | 664268 | F - 5th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 664263 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
8 | 664269 | F - 6th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 664263 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
9 | 664270 | F - 7th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 664263 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
10 | 664271 | F - 8th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 664263 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
11 | 664272 | F - 9th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 664263 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
12 | 664273 | F - 10th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 664263 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
13 | 664274 | F - 11th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 664263 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
14 | 664287 | F - 12th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 664263 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
15 | 664288 | F - 13th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 664263 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
16 | 664289 | F - 14th Floor Staircase 1 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 2 | 664263 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
17 | 664275 | F -Staircase 2 | NA | 0.0000 | 0.0000 | 1 | 664262 | 31 | 0 | [6 empty] | 0.0000
18 | 664276 | F - 1st Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 17 | 664275 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
19 | 664277 | F - 2nd Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 17 | 664275 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
20 | 664278 | F - 3rd Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 17 | 664275 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
21 | 664279 | F - 4th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 17 | 664275 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
22 | 664280 | F - 5th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 17 | 664275 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
23 | 664281 | F - 6th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 17 | 664275 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
24 | 664282 | F - 7th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 17 | 664275 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
25 | 664283 | F - 8th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 17 | 664275 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
26 | 664284 | F - 9th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 17 | 664275 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
27 | 664285 | F - 10th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 17 | 664275 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
28 | 664286 | F - 11th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 17 | 664275 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
29 | 664290 | F - 12th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 17 | 664275 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
30 | 664291 | F - 13th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 17 | 664275 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000
31 | 664292 | F - 14th Floor Staircase 2 Riser Plaster (L) | No. | 1.0000 | 1.0000 | 17 | 664275 | 4 | 33883 | G - 1st Floor Staircase 1 Riser Plaster | [5 empty] | 0.0000