## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- A-Staircase 1 Painting Work | Selected Group :- A-Staircase 1 Painting Work | Selected Group :- A-Staircase 1 Painting Work | Selected Group :- A-Staircase 1 Painting Work | Selected Group :- A-Staircase 1 Painting Work | Selected Group :- A-Staircase 1 Painting Work | Selected Group :- A-Staircase 1 Painting Work | Selected Group :- A-Staircase 1 Painting Work | Selected Group :- A-Staircase 1 Painting Work | Selected Group :- A-Staircase 1 Painting Work | Selected Group :- A-Staircase 1 Painting Work | Selected Group :- A-Staircase 1 Painting Work | Selected Group :- A-Staircase 1 Painting Work | Selected Group :- A-Staircase 1 Painting Work | Selected Group :- A-Staircase 1 Painting Work | Selected Group :- A-Staircase 1 Painting Work | Selected Group :- A-Staircase 1 Painting Work
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 664420 | G -Staircase 1 Painting Work | NA | 0.0000 | 0.0000 | 0 | 664418 | 31 | 0 | [6 empty] | 0.0000
2 | 664419 | G -GF Staircase 1 Painting Work | Sq.Ft | 564.1000 | 564.1000 | 1 | 664420 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
3 | 664421 | G -1st Floor Staircase 1 Painting Work | Sq.Ft | 575.5600 | 575.5600 | 1 | 664420 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
4 | 664422 | G -2nd Floor Staircase 1 Painting Work | Sq.Ft | 575.5600 | 575.5600 | 1 | 664420 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
5 | 664423 | G -3rd Floor Staircase 1 Painting Work | Sq.Ft | 575.5600 | 575.5600 | 1 | 664420 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
6 | 664424 | G -4th Floor Staircase 1 Painting Work | Sq.Ft | 575.5600 | 575.5600 | 1 | 664420 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
7 | 664425 | G -5th Floor Staircase 1 Painting Work | Sq.Ft | 575.5600 | 575.5600 | 1 | 664420 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
8 | 664426 | G -6th Floor Staircase 1 Painting Work | Sq.Ft | 575.5600 | 575.5600 | 1 | 664420 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
9 | 664427 | G -7th Floor Staircase 1 Painting Work | Sq.Ft | 575.5600 | 575.5600 | 1 | 664420 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
10 | 664428 | G -8th Floor Staircase 1 Painting Work | Sq.Ft | 575.5600 | 575.5600 | 1 | 664420 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
11 | 664429 | G -9th Floor Staircase 1 Painting Work | Sq.Ft | 575.5600 | 575.5600 | 1 | 664420 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
12 | 664430 | G -10th Floor Staircase 1 Painting Work | Sq.Ft | 575.5600 | 575.5600 | 1 | 664420 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
13 | 664431 | G -11th Floor Staircase 1 Painting Work | Sq.Ft | 575.5600 | 575.5600 | 1 | 664420 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
14 | 664432 | G -12th Floor Staircase 1 Painting Work | Sq.Ft | 575.5600 | 575.5600 | 1 | 664420 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
15 | 664433 | G -13th Floor Staircase 1 Painting Work | Sq.Ft | 575.5600 | 575.5600 | 1 | 664420 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
16 | 664434 | G -14th Floor Staircase 1 Painting Work | Sq.Ft | 575.5600 | 575.5600 | 1 | 664420 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000