## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- G - 13th Floor | Selected Group :- G - 13th Floor | Selected Group :- G - 13th Floor | Selected Group :- G - 13th Floor | Selected Group :- G - 13th Floor | Selected Group :- G - 13th Floor | Selected Group :- G - 13th Floor | Selected Group :- G - 13th Floor | Selected Group :- G - 13th Floor | Selected Group :- G - 13th Floor | Selected Group :- G - 13th Floor | Selected Group :- G - 13th Floor | Selected Group :- G - 13th Floor | Selected Group :- G - 13th Floor | Selected Group :- G - 13th Floor | Selected Group :- G - 13th Floor | Selected Group :- G - 13th Floor
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 666430 | G - 13th Floor | NA | 0.0000 | 0.0000 | 0 | 666180 | 31 | 0 | [6 empty] | 0.0000
2 | 666431 | G - 1301 Kitchen & Balcony Flooring Qty Diff. (M) | Sq.Ft | 1.0000 | 1.0000 | 1 | 666430 | 4 | 34700 | G - Kitchen & Balcony Flooring Qty Diff. (M) | [5 empty] | 0.0000
3 | 666432 | G - 1302 Kitchen & Balcony Flooring Qty Diff. (M) | Sq.Ft | 1.0000 | 1.0000 | 1 | 666430 | 4 | 34700 | G - Kitchen & Balcony Flooring Qty Diff. (M) | [5 empty] | 0.0000
4 | 666433 | G - 1303 Kitchen & Balcony Flooring Qty Diff. (M) | Sq.Ft | 1.0000 | 1.0000 | 1 | 666430 | 4 | 34700 | G - Kitchen & Balcony Flooring Qty Diff. (M) | [5 empty] | 0.0000
5 | 666434 | G - 1304 Kitchen & Balcony Flooring Qty Diff. (M) | Sq.Ft | 1.0000 | 1.0000 | 1 | 666430 | 4 | 34700 | G - Kitchen & Balcony Flooring Qty Diff. (M) | [5 empty] | 0.0000
6 | 666435 | G - 1305 Kitchen & Balcony Flooring Qty Diff. (M) | Sq.Ft | 1.0000 | 1.0000 | 1 | 666430 | 4 | 34700 | G - Kitchen & Balcony Flooring Qty Diff. (M) | [5 empty] | 0.0000
7 | 666436 | G - 1306 Kitchen & Balcony Flooring Qty Diff. (M) | Sq.Ft | 1.0000 | 1.0000 | 1 | 666430 | 4 | 34700 | G - Kitchen & Balcony Flooring Qty Diff. (M) | [5 empty] | 0.0000
8 | 666437 | G - 1307 Kitchen & Balcony Flooring Qty Diff. (M) | Sq.Ft | 1.0000 | 1.0000 | 1 | 666430 | 4 | 34700 | G - Kitchen & Balcony Flooring Qty Diff. (M) | [5 empty] | 0.0000
9 | 666438 | G - 1308 Kitchen & Balcony Flooring Qty Diff. (M) | Sq.Ft | 1.0000 | 1.0000 | 1 | 666430 | 4 | 34700 | G - Kitchen & Balcony Flooring Qty Diff. (M) | [5 empty] | 0.0000
10 | 666439 | G - 1309 Kitchen & Balcony Flooring Qty Diff. (M) | Sq.Ft | 1.0000 | 1.0000 | 1 | 666430 | 4 | 34700 | G - Kitchen & Balcony Flooring Qty Diff. (M) | [5 empty] | 0.0000
11 | 666440 | G - 1310 Kitchen & Balcony Flooring Qty Diff. (M) | Sq.Ft | 1.0000 | 1.0000 | 1 | 666430 | 4 | 34700 | G - Kitchen & Balcony Flooring Qty Diff. (M) | [5 empty] | 0.0000
12 | 666441 | G - 1311 Kitchen & Balcony Flooring Qty Diff. (M) | Sq.Ft | 1.0000 | 1.0000 | 1 | 666430 | 4 | 34700 | G - Kitchen & Balcony Flooring Qty Diff. (M) | [5 empty] | 0.0000
13 | 666442 | G - 1312 Kitchen & Balcony Flooring Qty Diff. (M) | Sq.Ft | 1.0000 | 1.0000 | 1 | 666430 | 4 | 34700 | G - Kitchen & Balcony Flooring Qty Diff. (M) | [5 empty] | 0.0000
14 | 666443 | G - 1313 Kitchen & Balcony Flooring Qty Diff. (M) | Sq.Ft | 1.0000 | 1.0000 | 1 | 666430 | 4 | 34700 | G - Kitchen & Balcony Flooring Qty Diff. (M) | [5 empty] | 0.0000
15 | 666444 | G - 1314 Kitchen & Balcony Flooring Qty Diff. (M) | Sq.Ft | 1.0000 | 1.0000 | 1 | 666430 | 4 | 34700 | G - Kitchen & Balcony Flooring Qty Diff. (M) | [5 empty] | 0.0000