## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - Lobby Painting Work | Selected Group :- C - Lobby Painting Work | Selected Group :- C - Lobby Painting Work | Selected Group :- C - Lobby Painting Work | Selected Group :- C - Lobby Painting Work | Selected Group :- C - Lobby Painting Work | Selected Group :- C - Lobby Painting Work | Selected Group :- C - Lobby Painting Work | Selected Group :- C - Lobby Painting Work | Selected Group :- C - Lobby Painting Work | Selected Group :- C - Lobby Painting Work | Selected Group :- C - Lobby Painting Work | Selected Group :- C - Lobby Painting Work | Selected Group :- C - Lobby Painting Work | Selected Group :- C - Lobby Painting Work | Selected Group :- C - Lobby Painting Work | Selected Group :- C - Lobby Painting Work
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 666501 | D - Lobby Painting Work | NA | 0.0000 | 0.0000 | 0 | 639654 | 31 | 0 | [6 empty] | 0.0000
2 | 666502 | D - Lobby Wall Painting Work | NA | 0.0000 | 0.0000 | 1 | 666501 | 31 | 0 | [6 empty] | 0.0000
3 | 666503 | D - GF Lobby Wall Painting Work | Sq.Ft | 2481.3000 | 2481.3000 | 2 | 666502 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
4 | 666504 | D - 1st Floor (Parking) Lobby Wall Painting Work | Sq.Ft | 7758.6200 | 7758.6200 | 2 | 666502 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
5 | 666505 | D - 2nd Floor (Parking) Lobby Wall Painting Work | Sq.Ft | 7758.6200 | 7758.6200 | 2 | 666502 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
6 | 666506 | D - 3rd Floor Lobby Wall Painting Work | Sq.Ft | 3064.6000 | 3064.6000 | 2 | 666502 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
7 | 666507 | D - 4th Floor Lobby Wall Painting Work | Sq.Ft | 3064.6000 | 3064.6000 | 2 | 666502 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
8 | 666508 | D - 5th Floor Lobby Wall Painting Work | Sq.Ft | 3064.6000 | 3064.6000 | 2 | 666502 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
9 | 666509 | D - 6th Floor Lobby Wall Painting Work | Sq.Ft | 3064.6000 | 3064.6000 | 2 | 666502 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
10 | 666510 | D - 7th Floor Lobby Wall Painting Work | Sq.Ft | 3064.6000 | 3064.6000 | 2 | 666502 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
11 | 666511 | D - 8th Floor Lobby Wall Painting Work | Sq.Ft | 2379.5000 | 2379.5000 | 2 | 666502 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
12 | 666512 | D - 9th Floor Lobby Wall Painting Work | Sq.Ft | 3064.6000 | 3064.6000 | 2 | 666502 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
13 | 666513 | D - 10th Floor Lobby Wall Painting Work | Sq.Ft | 3064.6000 | 3064.6000 | 2 | 666502 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
14 | 666514 | D - 11th Floor Lobby Wall Painting Work | Sq.Ft | 3064.6000 | 3064.6000 | 2 | 666502 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
15 | 666515 | D - 12th Floor Lobby Wall Painting Work | Sq.Ft | 3064.6000 | 3064.6000 | 2 | 666502 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
16 | 666516 | D - 13th Floor Lobby Wall Painting Work | Sq.Ft | 2379.5000 | 2379.5000 | 2 | 666502 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
17 | 666517 | D - 14th Floor Lobby Wall Painting Work | Sq.Ft | 3064.6000 | 3064.6000 | 2 | 666502 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
18 | 666518 | D - Refuge Area 8th &13th Floor Lobby Wall Painting Work | Sq.Ft | 5236.4200 | 5236.4200 | 2 | 666502 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
19 | 666519 | D - Lobby Ceiling Painting Work | NA | 0.0000 | 0.0000 | 1 | 666501 | 31 | 0 | [6 empty] | 0.0000
20 | 666520 | D - GF Lobby Ceiling Painting Work | Sq.Ft | 2528.4400 | 2528.4401 | 19 | 666519 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
21 | 666521 | D - 1st Floor (Parking) Lobby Ceiling Painting Work | Sq.Ft | 12017.6600 | 12017.6600 | 19 | 666519 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
22 | 666522 | D - 2nd Floor (Parking) Lobby Ceiling Painting Work | Sq.Ft | 12017.6600 | 12017.6600 | 19 | 666519 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
23 | 666523 | D - 3rd Floor Lobby Ceiling Painting Work | Sq.Ft | 1731.4900 | 1731.4900 | 19 | 666519 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
24 | 666524 | D - 4th Floor Lobby Ceiling Painting Work | Sq.Ft | 1731.4900 | 1731.4900 | 19 | 666519 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
25 | 666525 | D - 5th Floor Lobby Ceiling Painting Work | Sq.Ft | 1731.4900 | 1731.4900 | 19 | 666519 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
26 | 666526 | D - 6th Floor Lobby Ceiling Painting Work | Sq.Ft | 1731.4900 | 1731.4900 | 19 | 666519 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
27 | 666527 | D - 7th Floor Lobby Ceiling Painting Work | Sq.Ft | 1731.4900 | 1731.4900 | 19 | 666519 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
28 | 666528 | D - 8th Floor Lobby Ceiling Painting Work | Sq.Ft | 1405.8800 | 1405.8801 | 19 | 666519 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
29 | 666529 | D - 9th Floor Lobby Ceiling Painting Work | Sq.Ft | 1731.4900 | 1731.4900 | 19 | 666519 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
30 | 666530 | D - 10th Floor Lobby Ceiling Painting Work | Sq.Ft | 1731.4900 | 1731.4900 | 19 | 666519 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
31 | 666531 | D - 11th Floor Lobby Ceiling Painting Work | Sq.Ft | 1731.4900 | 1731.4900 | 19 | 666519 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
32 | 666532 | D - 12th Floor Lobby Ceiling Painting Work | Sq.Ft | 1731.4900 | 1731.4900 | 19 | 666519 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
33 | 666533 | D - 13th Floor Lobby Ceiling Painting Work | Sq.Ft | 1405.8800 | 1405.8801 | 19 | 666519 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
34 | 666534 | D - 14th Floor Lobby Ceiling Painting Work | Sq.Ft | 1731.4900 | 1731.4901 | 19 | 666519 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
35 | 666535 | D - Refuge Area 8th &13th Floor Lobby Ceiling Painting Work | Sq.Ft | 6804.9500 | 6804.9501 | 19 | 666519 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000