## Sheet1
Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI | Project :-SRA MORWADI
Selected Group :- C - Staircase Painting Work | Selected Group :- C - Staircase Painting Work | Selected Group :- C - Staircase Painting Work | Selected Group :- C - Staircase Painting Work | Selected Group :- C - Staircase Painting Work | Selected Group :- C - Staircase Painting Work | Selected Group :- C - Staircase Painting Work | Selected Group :- C - Staircase Painting Work | Selected Group :- C - Staircase Painting Work | Selected Group :- C - Staircase Painting Work | Selected Group :- C - Staircase Painting Work | Selected Group :- C - Staircase Painting Work | Selected Group :- C - Staircase Painting Work | Selected Group :- C - Staircase Painting Work | Selected Group :- C - Staircase Painting Work | Selected Group :- C - Staircase Painting Work | Selected Group :- C - Staircase Painting Work
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 666536 | D - Staircase Painting Work | NA | 0.0000 | 0.0000 | 0 | 639654 | 31 | 0 | [6 empty] | 0.0000
2 | 666537 | D - Staircase 1 Painting Work | NA | 0.0000 | 0.0000 | 1 | 666536 | 31 | 0 | [6 empty] | 0.0000
3 | 666538 | D - GF Staircase 1 Painting Work | Sq.Ft | 547.0600 | 547.0600 | 2 | 666537 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
4 | 666539 | D - 1st Floor Staircase 1 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 2 | 666537 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
5 | 666540 | D - 2nd Floor Staircase 1 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 2 | 666537 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
6 | 666541 | D - 3rd Floor Staircase 1 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 2 | 666537 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
7 | 666542 | D - 4th Floor Staircase 1 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 2 | 666537 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
8 | 666543 | D - 5th Floor Staircase 1 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 2 | 666537 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
9 | 666544 | D - 6th Floor Staircase 1 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 2 | 666537 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
10 | 666545 | D - 7th Floor Staircase 1 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 2 | 666537 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
11 | 666546 | D - 8th Floor Staircase 1 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 2 | 666537 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
12 | 666547 | D - 9th Floor Staircase 1 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 2 | 666537 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
13 | 666548 | D - 10th Floor Staircase 1 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 2 | 666537 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
14 | 666549 | D - 11th Floor Staircase 1 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 2 | 666537 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
15 | 666550 | D - 12th Floor Staircase 1 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 2 | 666537 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
16 | 666551 | D - 13th Floor Staircase 1 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 2 | 666537 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
17 | 666552 | D - 14th Floor Staircase 1 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 2 | 666537 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
18 | 666553 | D - Staircase 2 Painting Work | NA | 0.0000 | 0.0000 | 1 | 666536 | 31 | 0 | [6 empty] | 0.0000
19 | 666554 | D - GF Staircase 2 Painting Work | Sq.Ft | 547.0600 | 547.0600 | 18 | 666553 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
20 | 666555 | D - 1st Floor Staircase 2 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 18 | 666553 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
21 | 666556 | D - 2nd Floor Staircase 2 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 18 | 666553 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
22 | 666557 | D - 3rd Floor Staircase 2 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 18 | 666553 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
23 | 666558 | D - 4th Floor Staircase 2 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 18 | 666553 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
24 | 666559 | D - 5th Floor Staircase 2 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 18 | 666553 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
25 | 666560 | D - 6th Floor Staircase 2 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 18 | 666553 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
26 | 666561 | D - 7th Floor Staircase 2 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 18 | 666553 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
27 | 666562 | D - 8th Floor Staircase 2 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 18 | 666553 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
28 | 666563 | D - 9th Floor Staircase 2 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 18 | 666553 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
29 | 666564 | D - 10th Floor Staircase 2 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 18 | 666553 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
30 | 666565 | D - 11th Floor Staircase 2 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 18 | 666553 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
31 | 666566 | D - 12th Floor Staircase 2 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 18 | 666553 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
32 | 666567 | D - 13th Floor Staircase 2 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 18 | 666553 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000
33 | 666568 | D - 14th Floor Staircase 2 Painting Work | Sq.Ft | 602.9800 | 602.9800 | 18 | 666553 | 4 | 32115 | A-Lobby Painting Work | [5 empty] | 0.0000