## Sheet1
Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW
Selected Group :- Lift 2 Granite Work | Selected Group :- Lift 2 Granite Work | Selected Group :- Lift 2 Granite Work | Selected Group :- Lift 2 Granite Work | Selected Group :- Lift 2 Granite Work | Selected Group :- Lift 2 Granite Work | Selected Group :- Lift 2 Granite Work | Selected Group :- Lift 2 Granite Work | Selected Group :- Lift 2 Granite Work | Selected Group :- Lift 2 Granite Work | Selected Group :- Lift 2 Granite Work | Selected Group :- Lift 2 Granite Work | Selected Group :- Lift 2 Granite Work | Selected Group :- Lift 2 Granite Work | Selected Group :- Lift 2 Granite Work | Selected Group :- Lift 2 Granite Work | Selected Group :- Lift 2 Granite Work
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 666595 | Lift 2 Granite Work | NA | 0.0000 | 0.0000 | 0 | 503804 | 31 | 0 | [6 empty] | 0.0000
2 | 666596 | A-Lift 2 Ground Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
3 | 666597 | A-Lift 2 1st Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
4 | 666598 | A-Lift 2 2nd Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
5 | 666599 | A-Lift 2 3rd Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
6 | 666600 | A-Lift 2 4th Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
7 | 666601 | A-Lift 2 5th Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
8 | 666602 | A-Lift 2 6th Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
9 | 666603 | A-Lift 2 7th Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
10 | 666604 | A-Lift 2 8th Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
11 | 666605 | A-Lift 2 9th Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
12 | 666606 | A-Lift 2 10th Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
13 | 666607 | A-Lift 2 11th Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
14 | 666608 | A-Lift 2 12th Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
15 | 666609 | A-Lift 2 13th Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
16 | 666610 | A-Lift 2 14th Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
17 | 666611 | A-Lift 2 15th Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
18 | 666612 | A-Lift 2 16th Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
19 | 666613 | A-Lift 2 17th Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000
20 | 666614 | A-Lift 2 18th Floor Granite Work | No. | 1.0000 | 1.0000 | 1 | 666595 | 4 | 31379 | A-Lift 1 Granite Work | [5 empty] | 0.0000