## Sheet1
Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW | Project :-TANGEWALA COLONY SRA PROJECT NEW
Selected Group :- A - Lift 2 AAC Blockwork | Selected Group :- A - Lift 2 AAC Blockwork | Selected Group :- A - Lift 2 AAC Blockwork | Selected Group :- A - Lift 2 AAC Blockwork | Selected Group :- A - Lift 2 AAC Blockwork | Selected Group :- A - Lift 2 AAC Blockwork | Selected Group :- A - Lift 2 AAC Blockwork | Selected Group :- A - Lift 2 AAC Blockwork | Selected Group :- A - Lift 2 AAC Blockwork | Selected Group :- A - Lift 2 AAC Blockwork | Selected Group :- A - Lift 2 AAC Blockwork | Selected Group :- A - Lift 2 AAC Blockwork | Selected Group :- A - Lift 2 AAC Blockwork | Selected Group :- A - Lift 2 AAC Blockwork | Selected Group :- A - Lift 2 AAC Blockwork | Selected Group :- A - Lift 2 AAC Blockwork | Selected Group :- A - Lift 2 AAC Blockwork
Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters] | Task Qty with Update Task Name [Task Name should not be more than 60 characters]
Task_SrNo | Task_No | Task Name | Unit | Vol. of Material | Vol. of Labour | Parent_TaskSrNo | Parent_TaskNo | Task Type | LibTask_No | LibTask_Name | Task Identification1 | Task Identification2 | Task Identification3 | Task Identification4 | Task_Description | Built-Up Area
1 | 670749 | A - Lift 2 AAC Blockwork | NA | 0.0000 | 0.0000 | 0 | 670550 | 31 | 0 | [6 empty] | 0.0000
2 | 670750 | A - G.F Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
3 | 670751 | A - 1st Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
4 | 670752 | A - 2nd Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
5 | 670753 | A - 3rd Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
6 | 670754 | A - 4th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
7 | 670755 | A - 5th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
8 | 670756 | A - 6th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
9 | 670757 | A - 7th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
10 | 670758 | A - 8th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
11 | 670759 | A - 9th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
12 | 670760 | A - 10th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
13 | 670761 | A - 11th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
14 | 670762 | A - 12th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
15 | 670763 | A - 13th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
16 | 670764 | A - 14th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
17 | 670765 | A - 15th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
18 | 670766 | A - 16th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
19 | 670767 | A - 17th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
20 | 670768 | A - 18th Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000
21 | 670769 | A - Terrace Floor Lift 2 AAC Blockwork | No. | 1.0000 | 1.0000 | 1 | 670749 | 4 | 34853 | A - G.F Lift 1 AAC Blockwork | [5 empty] | 0.0000