## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : GANGA DHAM TOWERS
Task Name : A Fire Staircase Flooring
Page 1 of 1
Total Records: 331 Records 1 to 331
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | A 1st Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0109 | 76.28 | 59.85 | 4565.36 | 68.291 | 0.011 | 10243.65 | 6878.29
2 | A 1st Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21.01 | 1866.9835 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
3 | A 1st Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.536 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
4 | A 1st Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.9984 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
5 | A 1st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
6 | A 1st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
7 | A 1st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.86 | 190.24 | 21.124 | 0 | -11216.86
8 | A 1st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
9 | A 1st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
10 | A 1st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
11 | A 2nd Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.28 | 59.85 | 4565.36 | 68.291 | 0.011 | 10243.65 | 6878.29
12 | A 2nd Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
13 | A 2nd Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
14 | A 2nd Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 221.81 | 35.83 | 7947.45 | 236.98 | 41.17 | 35547 | 31499.55
15 | A 2nd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
16 | A 2nd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
17 | A 2nd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.86 | 190.24 | 21.124 | 0 | -11216.86
18 | A 2nd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
19 | A 2nd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
20 | A 2nd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
21 | A 3rd Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.28 | 59.85 | 4565.36 | 68.291 | 0.011 | 10243.65 | 6878.29
22 | A 3rd Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
23 | A 3rd Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
24 | A 3rd Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 221.81 | 35.83 | 7947.45 | 236.98 | 41.17 | 35547 | 31499.55
25 | A 3rd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
26 | A 3rd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
27 | A 3rd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.86 | 190.24 | 21.124 | 0 | -11216.86
28 | A 3rd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
29 | A 3rd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
30 | A 3rd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
31 | A 4th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.28 | 59.85 | 4565.36 | 68.291 | 0.011 | 10243.65 | 6878.29
32 | A 4th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
33 | A 4th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
34 | A 4th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 221.81 | 35.83 | 7947.45 | 236.98 | 41.17 | 35547 | 31499.55
35 | A 4th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
36 | A 4th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
37 | A 4th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.86 | 190.24 | 21.124 | 0 | -11216.86
38 | A 4th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
39 | A 4th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
40 | A 4th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
41 | A 5th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 79.901 | 150 | 11985.15 | 79.901 | 150 | 11985.15 | 8 | 150 | 1200 | 79.901 | 59.9 | 4785.8574 | 76.29 | 59.85 | 4565.96 | 71.901 | 3.611 | 10785.15 | 7419.19
42 | A 5th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
43 | A 5th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
44 | A 5th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 504.01 | 150 | 75601.5 | 504.01 | 150 | 75601.5 | 50 | 150 | 7500 | 504.01 | 40.7 | 20511.792 | 262.98 | 35.7 | 9388.389 | 454.01 | 241.03 | 68101.5 | 66213.111
45 | A 5th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
46 | A 5th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
47 | A 5th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.86 | 190.24 | 21.124 | 0 | -11216.86
48 | A 5th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
49 | A 5th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
50 | A 5th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
51 | A 6th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
52 | A 6th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
53 | A 6th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
54 | A 6th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
55 | A 6th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
56 | A 6th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
57 | A 6th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.86 | 190.24 | 21.124 | 0 | -11216.86
58 | A 6th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
59 | A 6th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
60 | A 6th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
61 | A 7th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
62 | A 7th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
63 | A 7th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
64 | A 7th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
65 | A 7th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
66 | A 7th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
67 | A 7th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.86 | 190.24 | 21.124 | 0 | -11216.86
68 | A 7th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
69 | A 7th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
70 | A 7th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
71 | A 8th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
72 | A 8th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
73 | A 8th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
74 | A 8th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
75 | A 8th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
76 | A 8th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
77 | A 8th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.86 | 190.24 | 21.124 | 0 | -11216.86
78 | A 8th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
79 | A 8th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
80 | A 8th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
81 | A 9th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
82 | A 9th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
83 | A 9th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
84 | A 9th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
85 | A 9th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
86 | A 9th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
87 | A 9th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.86 | 190.24 | 21.124 | 0 | -11216.86
88 | A 9th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
89 | A 9th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
90 | A 9th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
91 | A 10th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
92 | A 10th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
93 | A 10th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
94 | A 10th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
95 | A 10th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
96 | A 10th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
97 | A 10th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.86 | 190.24 | 21.124 | 0 | -11216.86
98 | A 10th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
99 | A 10th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
100 | A 10th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
101 | A 11th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
102 | A 11th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
103 | A 11th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
104 | A 11th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
105 | A 11th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
106 | A 11th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
107 | A 11th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.86 | 190.24 | 21.124 | 0 | -11216.86
108 | A 11th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
109 | A 11th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
110 | A 11th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
111 | A 12th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
112 | A 12th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
113 | A 12th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
114 | A 12th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
115 | A 12th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
116 | A 12th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
117 | A 12th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.86 | 190.24 | 21.124 | 0 | -11216.86
118 | A 12th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
119 | A 12th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
120 | A 12th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
121 | A 13th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
122 | A 13th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
123 | A 13th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
124 | A 13th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
125 | A 13th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
126 | A 13th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
127 | A 13th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.86 | 190.24 | 21.124 | 0 | -11216.86
128 | A 13th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
129 | A 13th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
130 | A 13th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
131 | A 14th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
132 | A 14th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
133 | A 14th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
134 | A 14th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
135 | A 14th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
136 | A 14th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
137 | A 14th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.86 | 190.24 | 21.124 | 0 | -11216.86
138 | A 14th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
139 | A 14th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
140 | A 14th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
141 | A 15th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
142 | A 15th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
143 | A 15th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
144 | A 15th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
145 | A 15th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
146 | A 15th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
147 | A 15th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.86 | 190.24 | 21.124 | 0 | -11216.86
148 | A 15th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
149 | A 15th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
150 | A 15th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
151 | A 16th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
152 | A 16th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
153 | A 16th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
154 | A 16th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
155 | A 16th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 74.3175 | 8.85 | 657.7 | 89.09 | 24.7725 | 26660.183 | 28994.9825
156 | A 16th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 0 | 0 | 0 | 120.9287 | 133.9287 | 1451.144 | 1607.1444
157 | A 16th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 0 | 0 | 0 | 190.24 | 211.24 | 0 | 0
158 | A 16th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
159 | A 16th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 0 | 0 | 0 | 77.62 | 86.62 | 0 | 0
160 | A 16th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
161 | A 18th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
162 | A 18th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
163 | A 18th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
164 | A 18th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
165 | A 18th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
166 | A 18th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
167 | A 18th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 31.686 | 59 | 1869.48 | 190.24 | 179.554 | 0 | -1869.48
168 | A 18th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 74.3175 | 53.1 | 3946.27 | 89.09 | 24.7725 | 0 | -3946.27
169 | A 18th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
170 | A 18th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
171 | A 19th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
172 | A 19th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
173 | A 19th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
174 | A 19th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
175 | A 19th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
176 | A 19th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
177 | A 19th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 158.43 | 59 | 9347.38 | 190.24 | 52.81 | 0 | -9347.38
178 | A 19th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
179 | A 19th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
180 | A 19th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
181 | A 20th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
182 | A 20th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
183 | A 20th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
184 | A 20th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
185 | A 20th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
186 | A 20th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
187 | A 20th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.84 | 190.24 | 21.124 | 0 | -11216.84
188 | A 20th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
189 | A 20th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
190 | A 20th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
191 | A 21st Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
192 | A 21st Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
193 | A 21st Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
194 | A 21st Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
195 | A 21st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
196 | A 21st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
197 | A 21st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.84 | 190.24 | 21.124 | 0 | -11216.84
198 | A 21st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
199 | A 21st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
200 | A 21st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
201 | A 22nd Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
202 | A 22nd Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
203 | A 22nd Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
204 | A 22nd Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
205 | A 22nd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
206 | A 22nd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
207 | A 22nd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.84 | 190.24 | 21.124 | 0 | -11216.84
208 | A 22nd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
209 | A 22nd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
210 | A 22nd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
211 | A 23rd Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
212 | A 23rd Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
213 | A 23rd Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
214 | A 23rd Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
215 | A 23rd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
216 | A 23rd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
217 | A 23rd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.84 | 190.24 | 21.124 | 0 | -11216.84
218 | A 23rd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
219 | A 23rd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
220 | A 23rd Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
221 | A 24th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 59.85 | 4565.96 | 68.291 | 0.001 | 10243.65 | 6877.69
222 | A 24th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
223 | A 24th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
224 | A 24th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
225 | A 24th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 89.181 | 8.85 | 789.24 | 89.09 | 9.909 | 26660.183 | 28863.4425
226 | A 24th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 74.3175 | 17.7 | 1315.42 | 120.9287 | 59.6112 | 1451.144 | 291.7244
227 | A 24th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.84 | 190.24 | 21.124 | 0 | -11216.84
228 | A 24th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
229 | A 24th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
230 | A 24th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
231 | A 25th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.28 | 59.85 | 4565.36 | 68.291 | 0.011 | 10243.65 | 6878.29
232 | A 25th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
233 | A 25th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
234 | A 25th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
235 | A 25th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 74.3175 | 8.85 | 657.7 | 89.09 | 24.7725 | 26660.183 | 28994.9825
236 | A 25th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 0 | 0 | 0 | 120.9287 | 133.9287 | 1451.144 | 1607.1444
237 | A 25th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 59 | 11216.86 | 190.24 | 21.124 | 0 | -11216.86
238 | A 25th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 53.1 | 4735.53 | 89.09 | 9.909 | 0 | -4735.53
239 | A 25th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 64.965 | 35.4 | 2299.77 | 77.62 | 21.655 | 0 | -2299.77
240 | A 25th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 59 | 5261.69 | 89.09 | 9.909 | 0 | -5261.69
241 | A 26th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 59.85 | 4566.0174 | 76.29 | 70.8 | 5401.332 | 68.291 | 0.001 | 10243.65 | 6042.318
242 | A 26th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 88.88 | 150 | 13332 | 9 | 150 | 1350 | 88.88 | 21 | 1866.48 | 88.88 | 21 | 1866.48 | 79.88 | 0 | 11982 | 11465.52
243 | A 26th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 59.85 | 6087.3435 | 101.71 | 59.85 | 6087.34 | 91.71 | 0 | 13756.5 | 9169.16
244 | A 26th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 37.1 | 9755.8283 | 262.98 | 35.7 | 9388.389 | 236.98 | 0 | 35547 | 30058.611
245 | A 26th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 0 | 0 | 0 | 89.09 | 99.09 | 26660.183 | 29652.6825
246 | A 26th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 0 | 0 | 0 | 120.9287 | 133.9287 | 1451.144 | 1607.1444
247 | A 26th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 50 | 9505.8 | 190.24 | 21.124 | 0 | -9505.8
248 | A 26th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring Rate Diff | Sq.Ft | 211.24 | 12 | 2534.88 | 0 | 0 | 0 | 21 | 12 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 190.24 | 211.24 | 2282.88 | 2534.88
249 | A 26th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 45 | 4013.15 | 89.09 | 9.909 | 0 | -4013.15
250 | A 26th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L) (Rate Diff.) | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.62 | 86.62 | 0 | 0
251 | A 26th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 0 | 0 | 0 | 77.62 | 86.62 | 0 | 0
252 | A 26th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 50 | 4459.05 | 89.09 | 9.909 | 0 | -4459.05
253 | A 17th Floor + Fire Check Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 114.43 | 150 | 17164.5 | 114.43 | 150 | 17164.5 | 11 | 150 | 1650 | 114.43 | 59.85 | 6848.6355 | 114.43 | 59.85 | 6848.64 | 103.43 | 0 | 15514.5 | 10315.86
254 | A 17th Floor + Fire Check Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.37 | 150 | 13255.5 | 88.37 | 150 | 13255.5 | 9 | 150 | 1350 | 88.37 | 21 | 1855.77 | 88.37 | 21 | 1855.77 | 79.37 | 0 | 11905.5 | 11399.73
255 | A 17th Floor + Fire Check Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 152.58 | 150 | 22887 | 152.58 | 150 | 22887 | 15 | 150 | 2250 | 152.58 | 59.85 | 9131.913 | 152.58 | 59.85 | 9131.91 | 137.58 | 0 | 20637 | 13755.09
256 | A 17th Floor + Fire Check Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 139.81 | 150 | 20971.5 | 139.81 | 150 | 20971.5 | 14 | 150 | 2100 | 139.81 | 35.7 | 4991.217 | 139.81 | 35.7 | 4991.22 | 125.81 | 0 | 18871.5 | 15980.28
257 | A 17th Floor + Fire Check Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 148.63 | 7.5 | 1114.73 | 0 | 0 | 0 | 15 | 7.5 | 112.5 | 148.63 | 8.85 | 1315.385 | 111.4725 | 8.85 | 986.52 | 133.63 | 37.1575 | 1002.225 | 128.205
258 | A 17th Floor + Fire Check Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 148.63 | 15 | 2229.45 | 0 | 0 | 0 | 15 | 15 | 225 | 148.63 | 17.7 | 2630.75 | 0 | 0 | 0 | 133.63 | 148.63 | 2004.45 | 2229.45
259 | A 17th Floor + Fire Check Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 133.15 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 133.15 | 59 | 7855.86 | 0 | 0 | 0 | 120.15 | 133.15 | 0 | 0
260 | A 17th Floor + Fire Check Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 148.63 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 148.63 | 53.1 | 7892.25 | 133.767 | 53.1 | 7103.02 | 133.63 | 14.863 | 0 | -7103.02
261 | A 17th Floor + Fire Check Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 87.11 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 87.11 | 35.4 | 3083.7 | 0 | 0 | 0 | 78.11 | 87.11 | 0 | 0
262 | A 17th Floor + Fire Check Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 148.63 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 148.63 | 59 | 8769.18 | 111.4725 | 59 | 6576.89 | 133.63 | 37.1575 | 0 | -6576.89
263 | A 27th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 70.8 | 5401.4028 | 76.29 | 70.8 | 5401.332 | 68.291 | 0.001 | 10243.65 | 6042.318
264 | A 27th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 0 | 0 | 0 | 9 | 150 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 79.88 | 88.88 | 11982 | 13332
265 | A 27th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 70.8 | 7201.068 | 101.71 | 70.8 | 7201.068 | 91.71 | 0 | 13756.5 | 8055.432
266 | A 27th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 42.82 | 11259.7001 | 0 | 0 | 0 | 236.98 | 262.98 | 35547 | 39447
267 | A 27th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 0 | 0 | 0 | 89.09 | 99.09 | 26660.183 | 29652.6825
268 | A 27th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 0 | 0 | 0 | 120.9287 | 133.9287 | 1451.144 | 1607.1444
269 | A 27th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 50 | 9505.8 | 190.24 | 21.124 | 0 | -9505.8
270 | A 27th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring Rate Diff | Sq.Ft | 211.24 | 12 | 2534.88 | 0 | 0 | 0 | 21 | 12 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 190.24 | 211.24 | 2282.88 | 2534.88
271 | A 27th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 45 | 4013.15 | 89.09 | 9.909 | 0 | -4013.15
272 | A 27th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L) (Rate Diff.) | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.62 | 86.62 | 0 | 0
273 | A 27th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 0 | 0 | 0 | 77.62 | 86.62 | 0 | 0
274 | A 27th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 50 | 4459.05 | 89.09 | 9.909 | 0 | -4459.05
275 | A 28th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 70.8 | 5401.4028 | 76.29 | 70.8 | 5401.332 | 68.291 | 0.001 | 10243.65 | 6042.318
276 | A 28th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 0 | 0 | 0 | 9 | 150 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 79.88 | 88.88 | 11982 | 13332
277 | A 28th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 70.8 | 7201.068 | 101.71 | 70.8 | 7201.068 | 91.71 | 0 | 13756.5 | 8055.432
278 | A 28th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 42.82 | 11259.7001 | 0 | 0 | 0 | 236.98 | 262.98 | 35547 | 39447
279 | A 28th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 0 | 0 | 0 | 89.09 | 99.09 | 26660.183 | 29652.6825
280 | A 28th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 0 | 0 | 0 | 120.9287 | 133.9287 | 1451.144 | 1607.1444
281 | A 28th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 50 | 9505.8 | 190.24 | 21.124 | 0 | -9505.8
282 | A 28th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring Rate Diff | Sq.Ft | 211.24 | 12 | 2534.88 | 0 | 0 | 0 | 21 | 12 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 190.24 | 211.24 | 2282.88 | 2534.88
283 | A 28th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 45 | 4013.15 | 89.09 | 9.909 | 0 | -4013.15
284 | A 28th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L) (Rate Diff.) | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.62 | 86.62 | 0 | 0
285 | A 28th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 0 | 0 | 0 | 77.62 | 86.62 | 0 | 0
286 | A 28th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 50 | 4459.05 | 89.09 | 9.909 | 0 | -4459.05
287 | A 29th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 70.8 | 5401.4028 | 76.29 | 70.8 | 5401.332 | 68.291 | 0.001 | 10243.65 | 6042.318
288 | A 29th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 0 | 0 | 0 | 9 | 150 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 79.88 | 88.88 | 11982 | 13332
289 | A 29th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 70.8 | 7201.068 | 101.71 | 70.8 | 7201.068 | 91.71 | 0 | 13756.5 | 8055.432
290 | A 29th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 42.82 | 11259.7001 | 0 | 0 | 0 | 236.98 | 262.98 | 35547 | 39447
291 | A 29th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 0 | 0 | 0 | 89.09 | 99.09 | 26660.183 | 29652.6825
292 | A 29th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 0 | 0 | 0 | 120.9287 | 133.9287 | 1451.144 | 1607.1444
293 | A 29th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 50 | 9505.8 | 190.24 | 21.124 | 0 | -9505.8
294 | A 29th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring Rate Diff | Sq.Ft | 211.24 | 12 | 2534.88 | 0 | 0 | 0 | 21 | 12 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 190.24 | 211.24 | 2282.88 | 2534.88
295 | A 29th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 45 | 4013.15 | 89.09 | 9.909 | 0 | -4013.15
296 | A 29th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L) (Rate Diff.) | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.62 | 86.62 | 0 | 0
297 | A 29th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 0 | 0 | 0 | 77.62 | 86.62 | 0 | 0
298 | A 29th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 50 | 4459.05 | 89.09 | 9.909 | 0 | -4459.05
299 | A 30th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 70.8 | 5401.4028 | 76.29 | 70.8 | 5401.332 | 68.291 | 0.001 | 10243.65 | 6042.318
300 | A 30th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 0 | 0 | 0 | 9 | 150 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 79.88 | 88.88 | 11982 | 13332
301 | A 30th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 70.8 | 7201.068 | 101.71 | 70.8 | 7201.068 | 91.71 | 0 | 13756.5 | 8055.432
302 | A 30th Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 42.82 | 11259.7001 | 0 | 0 | 0 | 236.98 | 262.98 | 35547 | 39447
303 | A 30th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 0 | 0 | 0 | 89.09 | 99.09 | 26660.183 | 29652.6825
304 | A 30th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 0 | 0 | 0 | 120.9287 | 133.9287 | 1451.144 | 1607.1444
305 | A 30th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 50 | 9505.8 | 190.24 | 21.124 | 0 | -9505.8
306 | A 30th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring Rate Diff | Sq.Ft | 211.24 | 12 | 2534.88 | 0 | 0 | 0 | 21 | 12 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 190.24 | 211.24 | 2282.88 | 2534.88
307 | A 30th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 45 | 4013.15 | 89.09 | 9.909 | 0 | -4013.15
308 | A 30th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L) (Rate Diff.) | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.62 | 86.62 | 0 | 0
309 | A 30th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 0 | 0 | 0 | 77.62 | 86.62 | 0 | 0
310 | A 30th Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 50 | 4459.05 | 89.09 | 9.909 | 0 | -4459.05
311 | A 31st Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Riser 60"x9" (59"x7") | Sq.Ft | 76.291 | 150 | 11443.65 | 76.291 | 150 | 11443.65 | 8 | 150 | 1200 | 76.291 | 70.8 | 5401.4028 | 76.29 | 70.8 | 5401.332 | 68.291 | 0.001 | 10243.65 | 6042.318
312 | A 31st Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Skirting Polished 24"x3" (23"x3") | R.Ft | 88.88 | 150 | 13332 | 0 | 0 | 0 | 9 | 150 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 79.88 | 88.88 | 11982 | 13332
313 | A 31st Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Tappa 60"x12" (59"x11") | Sq.Ft | 101.71 | 150 | 15256.5 | 101.71 | 150 | 15256.5 | 10 | 150 | 1500 | 101.71 | 70.8 | 7201.068 | 101.71 | 70.8 | 7201.068 | 91.71 | 0 | 13756.5 | 8055.432
314 | A 31st Floor Fire Staircase Flooring | 10 | Started | Material | (M)Kota Uncut Polished 24"x18" (22"x16") | Sq.Ft | 262.98 | 150 | 39447 | 262.98 | 150 | 39447 | 26 | 150 | 3900 | 262.98 | 42.82 | 11259.7001 | 0 | 0 | 0 | 236.98 | 262.98 | 35547 | 39447
315 | A 31st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 10 | 299.25 | 2992.5 | 99.09 | 8.85 | 876.955 | 0 | 0 | 0 | 89.09 | 99.09 | 26660.183 | 29652.6825
316 | A 31st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 13 | 12 | 156 | 99.09 | 17.7 | 1753.89 | 0 | 0 | 0 | 120.9287 | 133.9287 | 1451.144 | 1607.1444
317 | A 31st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 211.24 | 59 | 12463.16 | 190.116 | 50 | 9505.8 | 190.24 | 21.124 | 0 | -9505.8
318 | A 31st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Flooring Rate Diff | Sq.Ft | 211.24 | 12 | 2534.88 | 0 | 0 | 0 | 21 | 12 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 190.24 | 211.24 | 2282.88 | 2534.88
319 | A 31st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 53.1 | 5261.67 | 89.181 | 45 | 4013.15 | 89.09 | 9.909 | 0 | -4013.15
320 | A 31st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L) (Rate Diff.) | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77.62 | 86.62 | 0 | 0
321 | A 31st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 86.62 | 35.4 | 3066.34 | 0 | 0 | 0 | 77.62 | 86.62 | 0 | 0
322 | A 31st Floor Fire Staircase Flooring | 10 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 99.09 | 59 | 5846.32 | 89.181 | 50 | 4459.05 | 89.09 | 9.909 | 0 | -4459.05
323 | A 31st to Terrace Floor Fire Staircase Flooring | 0 | Started | Labour | (L)Kota Champher | R.Ft | 99.09 | 299.25 | 29652.68 | 0 | 0 | 0 | 0 | 299.25 | 0 | 99.09 | 7.5 | 743.175 | 0 | 0 | 0 | 99.09 | 99.09 | 29652.683 | 29652.6825
324 | A 31st to Terrace Floor Fire Staircase Flooring | 0 | Started | Labour | (L)Kota Champher & Edge Polish | R.Ft | 133.9287 | 12 | 1607.14 | 0 | 0 | 0 | 0 | 12 | 0 | 133.9287 | 15 | 2008.9305 | 0 | 0 | 0 | 133.9287 | 133.9287 | 1607.144 | 1607.1444
325 | A 31st to Terrace Floor Fire Staircase Flooring | 0 | Started | Labour | (L)Kota Flooring (L)- BCO | Sq.Ft | 211.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211.24 | 68 | 14364.32 | 211.24 | 68 | 14364.32 | 211.24 | 0 | 0 | -14364.32
326 | A 31st to Terrace Floor Fire Staircase Flooring | 0 | Started | Labour | (L)Kota Flooring Rate Diff | Sq.Ft | 211.24 | 12 | 2534.88 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211.24 | 211.24 | 2534.88 | 2534.88
327 | A 31st to Terrace Floor Fire Staircase Flooring | 0 | Started | Labour | (L)Kota Riser (L)- BCO | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99.09 | 55 | 5449.95 | 0 | 0 | 0 | 99.09 | 99.09 | 0 | 0
328 | A 31st to Terrace Floor Fire Staircase Flooring | 0 | Started | Labour | (L)Kota Skirting (L) (Rate Diff.) | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86.62 | 86.62 | 0 | 0
329 | A 31st to Terrace Floor Fire Staircase Flooring | 0 | Started | Labour | (L)Kota Skirting (L)- BCO | R.Ft | 86.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86.62 | 40 | 3464.8 | 0 | 0 | 0 | 86.62 | 86.62 | 0 | 0
330 | A 31st to Terrace Floor Fire Staircase Flooring | 0 | Started | Labour | (L)Kota Tread (L) - DSP | R.Ft | 99.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99.09 | 60 | 5945.4 | 0 | 0 | 0 | 99.09 | 99.09 | 0 | 0
331 | A Fire Staircase Balance Kota Skirting Work 1st to 25th Floo | 0 | Tentative | Labour | (L)Kota Skirting (L) (Rate Diff.) | R.Ft | 270.321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270.321 | 270.321 | 0 | 0